## Instructions
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Annual Performance Report (APR) - Section I
Budget Period: August 1, 2020 - July 31, 2021(Budget Year 4)
Reporting Period: February 1, 2020 - January 31, 2021.
Instructions Please use this workbook to document progress for your Budget Year 4 Work Plan as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section I of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)." The Work Plan tab includes the Year 4 plan you submitted in your 2020 APR. Columns I-L, with the orange Continuation Report (Section I) banner, are where you should enter information about your progress. For each activity, select the Current Status from the dropdown menu (not started, complete, in progress, or behind schedule) and provide relevant information under Successes, Challenges, and CDC Support Needed.
Technical Support If you need technical support when using this template, email your project officer.

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
Iowa Department of Public Health Project Narrative Budget Year 4
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan." Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
SCIENCE AND CONTENT | Project 1- Substance Use Morbidity Measures
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| This project is directed at the development and incorporation of state specific substance use morbidity measures for display on the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee will collaborate with the substance abuse program to define state specific measures and extract and transform the exisiting Hospital and ED discharge data for use on the Iowa Tracking Portal, and the establishment of standard descriptive summaries for use in validating the data. Messaging and content for the substance use morbidity measures will be developed and promoted through multiple channels. |  | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 4
|  |  | 12 | 7 | 2 | 2 | 23
Project 2- Prescription Monitoring Measures
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development and incorporation of state specific prescription monitoring measures for display on the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee will collaborate with the substance abuse program to define state specific measures and extract and transform the exisiting prescription monitoring program data for use on the Iowa Tracking Portal, and the establishment of standard descriptive summaries for use in validating the data. Messaging and content for the substance use morbidity measures will be developed and promoted through multiple channels.
TECHNOLOGY AND INFORMATICS
Project 3- Extreme Cold Morbidity Measures
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development and incorporation of the optional NCDM extreme cold measures for display on the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee will utilize the optional NCDM documentation for extreme cold measures to extract and transform the exisiting Hospital and ED discharge data for use on the Iowa Tracking Portal, and the establishment of standard descriptive summaries for use in validating the data. Messaging and content for the extreme cold measures will be developed and promoted through multiple channels. This is a continuation of a Year 3 project.
COMMUNICATIONS
Project 4- Fall Injury Morbidity Measures
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development and incorporation of state specific fall injury measures for display on the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee will collaborate with the injury prevention program to define state specific measures and extract and transform the exisiting Hospital and ED discharge data for use on the Iowa Tracking Portal, and the establishment of standard descriptive summaries for use in validating the data. Messaging and content for the substance use morbidity measures will be developed and promoted through multiple channels.
Project 5- Private Water Quality Testing Measure
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development and incorporation of a private water quality testing measure of state interest for private well water quality for display on the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee has previously published optional NCDM and state specific measures of private well water quality. Current efforts will emphasize the development of a measure that capture testing frequency for use on the Iowa Tracking Portal, and the establishment of standard descriptive summaries for use in data validation. Messaging and content for the new measure will be developed and promoted through multiple channels. This is an evolution of a Year 3 project.
PROGRAM SERVICES
Project 6- Immunization Profile
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development of immunization profile reports for display on the Iowa Tracking portal. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. Grantee will collaborate with the immunization program to develop a composite data connection to support a county based snapshot of multiple measures, and the development of a standard letter size Immunization profile visual for use on the Iowa portal. Messaging and content for the new Immunization profile will be developed and promoted through multiple channels. This is a continuation of a Year 3 project.
Project 7- Environmental Health Profile
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development of updated environmental health (EH) profile reports for display on the Iowa Tracking portal. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. The previous iteration of the Iowa Tracking portal included an EH Profile report that provided a county based snapshot of multiple NCDM across multiple content areas; the current effort will be to transition the EH profile to the new tableau platform. Emphasis will be on the creation of a composite data connection to support the multiple measures to be included, and the development of a standard letter size EH profile visual for use on the Iowa portal. Messaging and content for the new EH profile will be developed and promoted through multiple channels. This is a continuation of a Year 3 project.
Project 8- Public Water WIIN Data
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the incorporation of data collected in Iowa as part of the Water Infrastructure Improvements for the Nation Act. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. Grantee will collaborate with Iowa DNR share data, develop data visualizations, and messaging.
Project 9- Injury Morbidity Data External Cause Matrix
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development of procedures to apply the External Cause-of-injury Framework for Categorizing Mechanism and Intent of Injury to exisiting Hospital and ED discharge data. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. Grantee will collaborate with the injury prevention program to define scripts to code Hospital and ED discharge data using the matrix for use on the Iowa Tracking Portal, and the establishment of standard descriptive summaries for use in validating the data.
Project 10- Implement Geocoding Standards
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the implementation of the National EPHT Geocoding Standards within the Iowa Department of Public Health. Specific activities within this project target the Science and Content, and Technology and Informatics strategies and outcomes. Grantee will coordinate with the data management and information management programs to integrate the EPHT geocoding standards into department data sets that already include address information. Emphasis will be on developing a geodatabase infrastructure that would support efforts to geocode data. This is a continuation of a Year 3 project.
Project 11- Data Call Participation
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the ongoing submission of Tracking data flows from the grantee. Specific activities within this project target Science and Content, and Technology and Informatics strategies and outcomes. Grantee will maintain active accounts and expertise in the systems and tools needed to submit data to CDC, and will complete fall and spring data submissions during the scheduled time frames.
Project 12- Portal Technical Maintenance
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at maintaining the compliant operation of the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Communications, and Program Services strategies and outcomes. Grantee maintains an Iowa Tracking Portal compliant with the "Tracking Grantee Portal Requirements and Recommendations". Maintenance activities include the collection and monitoring of website function and use metrics, a rotating review of content and messaging, and collaboration with the University of Iowa to develop additional messaging components.
Project 13- Annual Data Load
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the maintenance and update of existing data and measures as additional years of data are collected and released by the data owner/steward. Specific activities within this project target Science and Content strategies and outcomes. Grantee has an established data load schedule for the major datasets based on anticipated release schedules. As new years of data are received the data are appended to prior year’s data and descriptive summaries are generated to assist with validation and quality assurance. Following validation the published data visualizations are updated to include the new year of data at the next quarterly portal update.
Project 14- Portal Data and Measure Maintenance
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the maintenance and update of existing data and measures as additional years of data are published on the Iowa Tracking Portal. Specific activities within this project target Science and Content, and Communications strategies and outcomes. Grantee has an established portal update schedule for the publication of new and updated content. The availability of a new and updated content is then promoted through multiple channels.
Project 15- Monitor Performance of Program Activities
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the monitoring and evaluation of the program through administrative reporting to CDC. Specific activities within this project target the Program Services strategies and outcomes. The use of CDC provided forms and templates will be used to report Public Health Actions, evaluation metrics, and portal statistics.
Project 16- Partner and Network Engagement
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at sustaining the Tracking Network in Iowa through engagement with partners, communications, and professional development; and align Tracking needs and priorities with organizational strategic and capacity planning. Specific activities within this project target Science and Content, Technology and Informatics, Communications, and Program Services strategies and outcomes. Grantee will update and implement partnership and communications plans to promote and expand Tracking in Iowa. Beyond the administrative tasks related to partnership and communications; efforts under this project also serve to meet participation with National EPHT workgroups and the continued evaluation of the Iowa Tracking portal; and ensure representation by Tracking in regular meetings with Department Leadership, Information Management, and Data Management is the primary mechanism to accomplish integration with the Department Strategic Planning Process.
Project 17- Training and Capacity Building
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development and conduct of training opportunities. Specific activities within the project target the Communications and Program Services strategies and outcomes. Activities will include the delivery of both in-person and online training to support use of the Tracking Portal.
Project 18- Portal Promotion
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the promotion of the Tracking Network. Specific activities within the project target the Communications and Program Services strategies and outcomes. Activities will include participation in national and regional coordinated campaigns, and participation as an exhibitor at state conferences.
Project 19- Sub-County Asthma Evaluation
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development of a routine analysis to discovery spatial and demographic patterns in Asthma Hospitalizations data for dissemination to local health departments. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. The implementation of the Geocoding Standards will allow the grantee to pursue more advanced analysis of existing data sets. The analysis of Asthma Hospitalizations at a census tract level will be a pilot that can later be applied to other health outcomes. Emphasis will be on the creation of a report that incorporates this analysis together with interpretive messaging for local health departments to use as part of the Coummunity Health Needs Assessment process. Use of the report will be tracked and documented.
Project 20- Sub-County Private Well Evaluation
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is directed at the development of a routine analysis to discovery spatial and demographic patterns in Private Well Water Testing data for dissemination to local health departments. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. Private Well data already included the sub-county Township identifier, by adding this Township identifier as a display layer grantee will beable to conduct more advanced analysis at the Township level. Emphasis will be on the creation of a report that incorporates this analysis together with interpretive messaging for local health departments to use as part of the Coummunity Health Needs Assessment process. Use of the report will be tracked and documented.
Project 21- COVID-19 Case and Hospital Resource Tracking
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project was identified and added to the work plan after the initial submission. This project is directed at the development of data visualizations for publication to assist in the COVID-19 response effort. Visualizations include of cases of COVID-19 and Hospital Resource use/availablity. Specific activities withing this project target the Science and Content, Technology and Informatics, and Program Services strategies and outcomes. The need to evaluate and share detailed COVID-19 surveillance and resource data in near real time represents a unique challenge to how IDPH has historically handled outbreak data dissemination.
Project 22- COVID-19 Vaccine Priority Group Planning and Distribution
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project was identified and added to the work plan after the initial submission. This project is directed at the development of data visualizations for distribution to Local Public Health agencies to assist in the COVID-19 response effort. Visualizations include of crosstabs of population estimates for a variety of population groups needed for vaccine planning prioritization. Specific activities withing this project target the Science and Content, Technology and Informatics, and Program Services strategies and outcomes. The need to provide planning tools and data to local partners is an essential aspect of the COVID-19 vaccine distribution planning process.
Project 23- Seasonal Influenza Surveillance Report
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project was identified and added to the work plan after the initial submission. This project is directed at the development of data visualizations for publication to increase efficiency and timliness of data analysis and reporting for seasonal influenza. Visualizations include of updates to the Seasonal Influenza Surveillance report used internally and new visualizations targeted at the general public. Specific activities withing this project target the Technology and Informatics, Program Services, and Communications strategies and outcomes. Emphasis will be on leveraging Tracking infrastructure and tools to improve the ability for providers, partners, and the public to use seasonal flu data to help them make organizational policy decisions and individual actions.
Project 24-
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project 25-
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project 26-
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)

## Work Plan
EH17-1702 Budget Period: |  |  | August 1, 2020 - July 31, 2021
Date Submitted: |  |  | 2021-03-26
No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activity description. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project. | Continuation Report (Section I)
Project Title | Activity Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline | Status | Successes | Challenges | CDC Program Support Needed
Substance Use Morbidity Measures | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform Hospital and ED discharge data to generate Substance Use Morbidity measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. |  |  | Q1-Q4 | Not Started | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | No additional support is needed from CDC.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Substance Use Morbidity measures from the Hospital and ED Discharge Data. |  |  | Q1-Q4 | Not Started | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | No additional support is needed from CDC.
| Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of Substance Use Morbidity measures. |  |  | Q1-Q4 | Not Started | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | No additional support is needed from CDC.
| Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of Substance Use Morbidity measures. |  |  | Q1-Q4 | Not Started | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | No additional support is needed from CDC.
| Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of Substance Use Morbidity measures. |  |  | Q1-Q4 | Not Started | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | No additional support is needed from CDC.
| Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the Substance Use Morbidity measures. |  |  | Q1-Q4 | Not Started | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | No additional support is needed from CDC.
| Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published Substance Use Morbidity measures via listserv. |  |  | Q1-Q4 | Not Started | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | No additional support is needed from CDC.
| Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published Substance Use Morbidity measures via Social Media channels. |  |  | Q1-Q4 | Not Started | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | Substance Abuse Program decided to focus on development of additional measures from the Prescription Monitoring Program data at this time. The Substance Abuse Morbidity measures remain on the list of projects to be completed. | No additional support is needed from CDC.
Prescription Monitoring Measures | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform Prescription Monitoring Program Data data to generate Prescription Monitoring measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. |  |  | Q1-Q3 | Complete | Business requirements were developed and built for three categories of Controlled Substances from the Prescription Monitoring Program data. Additional PMP measures are under development in lieu of the Substance Use Morbidity Measures Project as of the APR Submission. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Prescription Monitoring measures from the Prescription Monitoring Program Data. |  |  | Q1-Q3 | Complete | A data connection to the PMP data source was established. SOPs and routine processes established to load and transform the data. Additional PMP measures are under development in lieu of the Substance Use Morbidity Measures Project as of the APR Submission. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of Prescription Monitoring measures. |  |  | Q1-Q3 | Complete | Descriptive analyses were developed and used as part of the validation and quality assurance process for incorporating the PMP data that contributed to the new measures published on the Iowa Portal. Additional PMP measures are under development in lieu of the Substance Use Morbidity Measures Project as of the APR Submission. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of Prescription Monitoring measures. |  |  | Q1-Q3 | Complete | Visualizations were published on the Iowa Portal. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of Prescription Monitoring measures. |  |  | Q1-Q3 | Complete | Portal users were engaged to identify targeted data bite infographics to highlight the PMP data and measures on the portal. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the Prescription Monitoring measures. |  |  | Q1-Q3 | Complete | Developed content was published on the Iowa portal | There were no challenges related to this activity. | No additional support from CDC is needed.
| Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published Prescription Monitoring measures via listserv. |  |  | Q1-Q3 | Complete | New or updated PMP data and measures were published during the Winter and Spring quarterly portal updates that occurred during the reporting period, and relevant information was included in the listserv message distributed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published Prescription Monitoring measures via Social Media channels. |  |  | Q1-Q3 | Complete | New or updated PMP data and measures were published during the Winter and Spring quarterly portal updates that occurred during the reporting period, and relevant information was included in the social media posting. | There were no challenges related to this activity. | No additional support from CDC is needed.
Extreme Cold Morbidity Measures | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform Hospital and ED discharge data to generate Extreme Cold Measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. |  |  | Q1-Q2 | Not Started | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | Continued support of the Extreme Cold CWG team and Dissemination of approved Extreme Cold NCDM.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Extreme Cold Measures from the Hospital and ED Discharge Data. |  |  | Q1-Q2 | Not Started | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | Continued support of the Extreme Cold CWG team and Dissemination of approved Extreme Cold NCDM.
| Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of Extreme Cold Measures. |  |  | Q1-Q2 | Not Started | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | Continued support of the Extreme Cold CWG team and Dissemination of approved Extreme Cold NCDM.
| Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of Extreme Cold Optional NCDM. |  |  | Q1-Q2 | Not Started | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | Continued support of the Extreme Cold CWG team and Dissemination of approved Extreme Cold NCDM.
| Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of Extreme Cold Optional NCDM. |  |  | Q1-Q2 | Not Started | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | Continued support of the Extreme Cold CWG team and Dissemination of approved Extreme Cold NCDM.
| Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the Extreme Cold Optional NCDM documentation. |  |  | Q1-Q2 | Not Started | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | Continued support of the Extreme Cold CWG team and Dissemination of approved Extreme Cold NCDM.
| Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published Extreme Cold Optional NCDM via listserv. |  |  | Q1-Q2 | Not Started | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | Continued support of the Extreme Cold CWG team and Dissemination of approved Extreme Cold NCDM.
| Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published Extreme Cold Optional NCDM via Social Media channels. |  |  | Q1-Q2 | Not Started | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | As of the end of the reporting period CDC has not yet released the final requirements for the newly developed optional NCDM for cold related illness. The Extreme Cold CWG team will resume actrivities in February 2021, | Continued support of the Extreme Cold CWG team and Dissemination of approved Extreme Cold NCDM.
Fall Injury Morbidity Measures | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform Hospital and ED discharge data to generate Fall Injury Morbidity measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. |  |  | Q1-Q2 | Complete | Developed SOPs and routine processes supported the efficient implementation of new state specific measures for Fall Injuries. | IT staff turnover created delays in progress on this project, pushing completion to Q3-Q4 | No additional support from CDC is needed.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Fall Injury Morbidity measures from the Hospital and ED Discharge Data. |  |  | Q1-Q2 | Complete | Developed SOPs and routine processes supported the efficient implementation of new state specific measures for Fall Injuries. | IT staff turnover created delays in progress on this project, pushing completion to Q3-Q4 | No additional support from CDC is needed.
| Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of Fall Injury Morbidity measures. |  |  | Q1-Q2 | Complete | Descriptive analyses were developed and used as part of the validation and quality assurance process for incorporating the new Fall Injury Morbidity measures published on the Iowa Portal. | IT staff turnover created delays in progress on this project, pushing completion to Q3-Q4 | No additional support from CDC is needed.
| Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of Fall Injury Morbidity measures. |  |  | Q1-Q2 | In Progress | Visualizations are currently in draft form for review and approval prior to publication. | IT staff turnover created delays in progress on this project, pushing completion to Q3-Q4 | No additional support from CDC is needed.
| Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of Fall Injury Morbidity measures. |  |  | Q1-Q2 | In Progress | Developed content has been apporved for publication. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the Fall Injury Morbidity measures. |  |  | Q1-Q2 | In Progress | Developed content has been apporved for publication. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published Fall Injury Morbidity measures via listserv. |  |  | Q1-Q2 | Not Started | Anticipated as part of the Spring 2021 portal update. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published Fall Injury Morbidity measures via Social Media channels. |  |  | Q1-Q2 | Not Started | Anticipated as part of the Spring 2021 portal update. | There were no challenges related to this activity. | No additional support from CDC is needed.
Private Water Quality Testing Measure | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform Private Well Tracking System data to generate a new private well testing measure and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. |  |  | Q1-Q2 | Behind Schedule | No successes, it is unlikely this project will be completed in the current funding year. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been delayed for multiple reasons: 1. technical issues with the source data connection, 2. IT staff turnover, 3. COVID-19 response efforts. | No additional support from CDC is needed.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of a new private well testing measure from the Private Well Tracking System Data. |  |  | Q1-Q2 | Behind Schedule | No successes, it is unlikely this project will be completed in the current funding year. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been delayed for multiple reasons: 1. technical issues with the source data connection, 2. IT staff turnover, 3. COVID-19 response efforts. | No additional support from CDC is needed.
| Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of a new private well testing measure. |  |  | Q1-Q2 | Not Started | Dependent on above delayed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been delayed for multiple reasons: 1. technical issues with the source data connection, 2. IT staff turnover, 3. COVID-19 response efforts. | No additional support from CDC is needed.
| Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of a new private well testing measure. |  |  | Q1-Q2 | Not Started | Dependent on above delayed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been delayed for multiple reasons: 1. technical issues with the source data connection, 2. IT staff turnover, 3. COVID-19 response efforts. | No additional support from CDC is needed.
| Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of a new private well testing measure. |  |  | Q1-Q2 | Not Started | Dependent on above delayed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been delayed for multiple reasons: 1. technical issues with the source data connection, 2. IT staff turnover, 3. COVID-19 response efforts. | No additional support from CDC is needed.
| Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the new private well testing measure. |  |  | Q1-Q2 | Not Started | Dependent on above delayed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been delayed for multiple reasons: 1. technical issues with the source data connection, 2. IT staff turnover, 3. COVID-19 response efforts. | No additional support from CDC is needed.
| Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published Private Well Testing measure via listserv. |  |  | Q1-Q2 | Not Started | Dependent on above delayed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been delayed for multiple reasons: 1. technical issues with the source data connection, 2. IT staff turnover, 3. COVID-19 response efforts. | No additional support from CDC is needed.
| Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published Private Well Testing measure via Social Media channels. |  |  | Q1-Q2 | Not Started | Dependent on above delayed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been delayed for multiple reasons: 1. technical issues with the source data connection, 2. IT staff turnover, 3. COVID-19 response efforts. | No additional support from CDC is needed.
Immunization Profile | Measure Identification | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will collaborate with the immunization program to identify the measures to be included in a County level profile of immunization measures to assist in the Community Health Needs Assessment and Health Improvement Planning process. |  |  | Q1-Q3 | Not Started | No successes, it is unlikely this project will be completed in the current funding year. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Profile Development | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will collaborate with the immunization program to design a County level profile of immunization measures to assist in the Community Health Needs Assessment and Health Improvement Planning process. |  |  | Q1-Q3 | Not Started | No successes, it is unlikely this project will be completed in the current funding year. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Immunization data for use in the Immunization profile. |  |  | Q1-Q3 | Not Started | Dependent on above postponed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Content Development | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop an immunization profile report to assist in the Community Health Needs Assessment and Health Improvement Planning process. |  |  | Q1-Q3 | Not Started | Dependent on above postponed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Profile Publishing | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will make the county level immunization profile available to local public health agencies. |  |  | Q1-Q3 | Not Started | Dependent on above postponed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| PHA Development | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will track use of the disseminated profile and work with users to demonstrate impact through Public Health Actions. |  |  | Q1-Q4 | Not Started | Dependent on above postponed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
Environmental Health Profile | Measure Identification | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will identify the measures to be included in a County level profile of environmental measures to assist in the Community Health Needs Assessment and Health Improvement Planning process. |  |  | Q1-Q4 | Behind Schedule | No successes, it is anticipated that staff capacity will be in place and effort will resume before end of current funding year. | Work on this activity has been delayed due to EPHT program staff vacancies, which have been exarcerbated by delays in filling caused by the COVID-19 response effort. | No additional support from CDC is needed.
| Profile Development | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will design a County level profile of environmental measures to assist in the Community Health Needs Assessment and Health Improvement Planning process. |  |  | Q1-Q4 | Behind Schedule | No successes, it is anticipated that staff capacity will be in place and effort will resume before end of current funding year. | Work on this activity has been delayed due to EPHT program staff vacancies, which have been exarcerbated by delays in filling caused by the COVID-19 response effort. | No additional support from CDC is needed.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of environmental data for use in the Environmental Health profile. |  |  | Q1-Q4 | Not Started | Dependent on above delayed activities. | Work on this activity has been delayed due to EPHT program staff vacancies, which have been exarcerbated by delays in filling caused by the COVID-19 response effort. | No additional support from CDC is needed.
| Content Development | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop an environmental health profile report to assist in the Community Health Needs Assessment and Health Improvement Planning process. |  |  | Q1-Q4 | Not Started | Dependent on above delayed activities. | Work on this activity has been delayed due to EPHT program staff vacancies, which have been exarcerbated by delays in filling caused by the COVID-19 response effort. | No additional support from CDC is needed.
| Profile Publishing | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will make the county level environmental health profile available to local public health agencies. |  |  | Q1-Q4 | Not Started | Dependent on above delayed activities. | Work on this activity has been delayed due to EPHT program staff vacancies, which have been exarcerbated by delays in filling caused by the COVID-19 response effort. | No additional support from CDC is needed.
| PHA Development | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will track use of the disseminated profile and work with users to demonstrate impact through Public Health Actions. |  |  | Q1-Q4 | Not Started | Dependent on above delayed activities. | Work on this activity has been delayed due to EPHT program staff vacancies, which have been exarcerbated by delays in filling caused by the COVID-19 response effort. | No additional support from CDC is needed.
Public Water WIIN Data | Data Evaluation | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Grantee will coordinate with the Iowa DNR to evaluate the WIIN data to identify and derive measures and content for addition to the portal. |  |  | Q1-Q4 | Not Started | No successes, COVID-19 response efforts have superceded interest in initiating this project.It is unlikely this project will begin before the end of the current funding year. Effort has been redirected to COVID-19 response projects added to the workplan. | Work on this activity has been postponed as the Department is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Data Integration | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will establish a data sharing agreement and coordinate with Information Management to integrate the WIIN data. |  |  | Q1-Q4 | Not Started | No successes, COVID-19 response efforts have superceded interest in initiating this project.It is unlikely this project will begin before the end of the current funding year. Effort has been redirected to COVID-19 response projects added to the workplan. | Work on this activity has been postponed as the Department is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform WIIN data to generate measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. |  |  | Q1-Q4 | Not Started | No successes, COVID-19 response efforts have superceded interest in initiating this project.It is unlikely this project will begin before the end of the current funding year. Effort has been redirected to COVID-19 response projects added to the workplan. | Work on this activity has been postponed as the Department is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations based on WIIN data and measures. |  |  | Q1-Q4 | Not Started | No successes, COVID-19 response efforts have superceded interest in initiating this project.It is unlikely this project will begin before the end of the current funding year. Effort has been redirected to COVID-19 response projects added to the workplan. | Work on this activity has been postponed as the Department is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
Injury Morbidity Data External Cause Matrix | Matrix Development | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to transform and classify Hospital and ED discharge data utilizing the recommendation for classifying injuries by cause and intent. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. |  |  | Q1-Q2 | Complete | Developed SOPs and routine processes supported the efficient implementation of of the external cause of injury matrix in support of the Fall Injury Morbidity project. | IT staff turnover created delays in progress on this project, but the effort was completed on schedule. | No additional support from CDC is needed.
| Matrix Scripting | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the transformation and classification of Injuries from the Hospital and ED Discharge Data. |  |  | Q1-Q2 | Complete | Developed SOPs and routine processes supported the efficient implementation of of the external cause of injury matrix in support of the Fall Injury Morbidity project. | IT staff turnover created delays in progress on this project, but the effort was completed on schedule. | No additional support from CDC is needed.
Implement Geocoding Standards | Adopt Standards | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will present and advocate for the incorporation of the Tracking adopted Geocoding Standards into department data standards |  |  | Q1-Q2 | Complete | The geocoding standards have been accepted and will be implemented for all geocoded datasets | There were no challenges related to this activity. | No additional support from CDC is needed.
| Geodatabase Development | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will collaborate with Information Management to develop a geodatabase from the outputs of all address level geocoding conducted on department data sets to facilitate future geocoding efforts. |  |  | Q1-Q2 | In Progress | Efforts to implement the geocoding standards have switched to determining the feasibility of using the Melissa Address Verification tool to geocode address information contatined in appropriate data sources IDPH utilizes. | Work on this activity has been delayed due to IT staff turnover, and COVID-19 response efforts. | No additional support from CDC is needed.
| Geocoding Process | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will collaborate with Information Management to identify tools and processes to implement address level geocoding for appropriate data sets consistent with the adopted Geocoding Standards. |  |  | Q1-Q3 | In Progress | Efforts to implement the geocoding standards have switched to determining the feasibility of using the Melissa Address Verification tool to geocode address information contatined in appropriate data sources IDPH utilizes. | Work on this activity has been delayed due to IT staff turnover, and COVID-19 response efforts. | No additional support from CDC is needed.
Data Call Participation | Fall Required Flows | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will submit new years of data available for required data flows during the Fall Data Call. |  |  | Q1-Q2 | Complete | During the Fall 2020 data call Iowa submitted 2018 and 2019 data for all 5 Hospital and all 4 ED required data flows; revised birth defects required data for 2000-2014 and new birth defects required data for 2015-2016. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Fall Optional Flows | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will submit new years of data available for optional data flows during the Fall Data Call. |  |  | Q1-Q2 | Complete | During the Fall 2020 data call Iowa did not have any data for the optional data flows. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Spring Required Flows | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will submit new years of data available for required data flows during the Spring Data Call. |  |  | Q1-Q3 | Complete | During the Spring 2020 data call Iowa submitted the required 2019 WQL and PWS Inventory data flows. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Spring Optional Flows | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will submit new years of data available for optional data flows during the Spring Data Call. |  |  | Q1-Q3 | Complete | During the Spring 2020 data call Iowa did not have any data for the optional data flows. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Submission Accounts | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Grantee will maintain active accounts for SAMS and CDC Join. |  |  | Q1-Q4 | Complete | Iowa staff maintained active SAMS and CDC-Join accounts during the reporting period. | There were no challenges related to this activity. | No additional support from CDC is needed.
Portal Technical Maintenance | Portal Maintenance | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements | Grantee will use Siteimprove quality assurance reports to monitor the function and operation of the Iowa Tracking Portal. Weekly reports will be tracked and monitored to ensure consistent operation. |  |  | Q1-Q4 | Complete | Weekly reports were monitored and one significant issues with operation of the portal was experienced. The portal team worked with Tableau support to trouble shoot and resolve the issue. | The implementation of DynaTrace caused a loading error with embedded Tableau visualizations in the Chrome web browser. Users were directed to use Firefox or Edge until the issue was identified and resolved. | No additional support from CDC is needed.
| Portal Review | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | Grantee will facilitate and assist CDC when conducting annual portal reviews. |  |  | Q1-Q4 | Complete | Portal review was conducted in July 2020 | There were no challenges related to this activity. | No additional support from CDC is needed.
| Webstats Submission | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | Grantee will collect and submit portal statistics using the reporting template provided by CDC. |  |  | Q1-Q4 | Complete | Webstats report successfully submitted. | There were no challenges related to this activity. | No additional support from CDC is needed.
Annual Data Load | Air Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the EPA Air Now data repository. |  |  | Q1-Q2 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Air Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. |  |  | Q1-Q2 | Complete | Data validation completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Climate Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Iowa State University Climate Science Program. |  |  | Q1-Q2 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Climate Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. |  |  | Q1-Q2 | Complete | Data validation completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Private Water Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the Private Well Tracking System data connection. |  |  | Q1-Q2 | Complete | Data load completed. | Data connection issues were experienced with the DNR during the transition to AWS. | No additional support from CDC is needed.
| Private Water Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. |  |  | Q1-Q2 | Complete | Data validation completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Public Water Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Iowa DNR. |  |  | Q1-Q2 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Public Water Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. |  |  | Q1-Q2 | Complete | Data validation completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Discharge Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Iowa Hospital Association. |  |  | Q1-Q4 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Discharge Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. |  |  | Q1-Q4 | Complete | Data validation completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| BD Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Iowa Registry of Congenital and Inherited Disorders. |  |  | Q1-Q3 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| BD Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. |  |  | Q1-Q3 | Complete | Data validation completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Cancer Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the SEER program. |  |  | Q1-Q3 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Cancer Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. |  |  | Q1-Q3 | Complete | Data validation completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Lead Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the HHLPSS data connection. |  |  | Q1-Q4 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Lead Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. |  |  | Q1-Q4 | Complete | Data validation completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| ACS Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the American Communities Survay Data Download site. |  |  | Q1-Q2 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Population Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the NCHS Bridged-race Population Estimates website. |  |  | Q1-Q4 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Vital Records Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the Vital Records Program data connection. |  |  | Q1-Q2 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Vital Records Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. |  |  | Q1-Q2 | Complete | Data validation completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| IDSS Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the Iowa Disease Surveillance System data connection. |  |  | Q1-Q3 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| IRIS Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the Immunization Registry Information System data connection. |  |  | Q1-Q2 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
| PMP Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Board of Pharmacy. |  |  | Q1-Q3 | Complete | Data load completed. | There were no challenges related to this activity. | No additional support from CDC is needed.
Portal Data and Measure Maintenance | Winter Portal Update | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will publish new and updated data visualizations and content. |  |  | Q1-Q3 | Complete | The Winter 2020 portal update was published the first week of February. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Winter Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published updates via listserv. |  |  | Q1-Q3 | Complete | Listserve message was sent. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Winter Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published updates via Social Media channels. |  |  | Q1-Q3 | Complete | Promoted Facebook post was made. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Spring Portal Update | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will publish new and updated data visualizations and content. |  |  | Q1-Q4 | Complete | The Spring 2020 portal update was published the third week of May. | The update was delayed two weeks due to delays created by staff vacancies. | No additional support from CDC is needed.
| Spring Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published updates via listserv. |  |  | Q1-Q4 | Complete | Listserve message was sent. | The update was delayed two weeks due to delays created by staff vacancies. | No additional support from CDC is needed.
| Spring Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published updates via Social Media channels. |  |  | Q1-Q4 | Complete | Promoted Facebook post was made. | The update was delayed two weeks due to delays created by staff vacancies. | No additional support from CDC is needed.
| Summer Portal Update | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will publish new and updated data visualizations and content. |  |  | Q1-Q2 | Complete | The Summer 2020 portal update was published the first week of August. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Summer Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published updates via listserv. |  |  | Q1-Q2 | Complete | Listserve message was sent. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Summer Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published updates via Social Media channels. |  |  | Q1-Q2 | Complete | Promoted Facebook post was made. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Fall Portal Update | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will publish new and updated data visualizations and content. |  |  | Q1-Q2 | Complete | The Fall 2020 portal update was published the first week of November. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Fall Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published updates via listserv. |  |  | Q1-Q2 | Complete | Listserve message was sent. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Fall Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published updates via Social Media channels. |  |  | Q1-Q2 | Complete | Promoted Facebook post was made. | There were no challenges related to this activity. | No additional support from CDC is needed.
Monitor Performance of Program Activities | Evaluation Plan | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Grantee will collect and submit Performance Metrics using the reporting template provided by CDC. |  |  | Q1-Q3 | Complete | The PM Collection Tool was submitted as part of the APR process | There were no challenges related to this activity. | No additional support from CDC is needed.
| Winter PHAR | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will submit public health actions based on project results using the PHAR in the first quarter. |  |  | Q1-Q2 | Complete | The FY2020 Q2 PHAR was not requested by CDC due to COVID-19 response | The FY2020 Q2 PHAR was not requested by CDC due to COVID-19 response | No additional support from CDC is needed.
| Spring PHAR | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will submit public health actions based on project results using the PHAR in the second quarter. |  |  | Q1-Q2 | Complete | The FY2020 Q3 PHAR was submitted with 1 PHA: "Iowa Tracking Supports Dissemination of COVID-19 Data" | There were no challenges related to this activity. | No additional support from CDC is needed.
| Summer PHAR | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will submit public health actions based on project results using the PHAR in the third quarter. |  |  | Q2-Q3 | Complete | The FY2020 Q4 PHAR was submitted with no PHAs | There were no challenges related to this activity. | No additional support from CDC is needed.
| Fall PHAR | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will submit public health actions based on project results using the PHAR in the fourth quarter. |  |  | Q3-Q4 | Complete | The FY2021 Q1 PHAR was submitted with 1 revised PHA based on feedback from CDC: "Iowa Tracking Supports Dissemination of COVID-19 Data" | There were no challenges related to this activity. | No additional support from CDC is needed.
| IM Meetings | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Grantee will attend monthly meetings with Information Management to ensure alignment of objectives. |  |  | Q1-Q4 | Complete | Monthly meetings were conducted throughout the reporting period. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Executive Meetings | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Grantee will attend quarterly meetings with Department Leadershipto ensure alignment of objectives. |  |  | Q1-Q4 | Complete | Quarterly meetings were conducted throughout the reporting period. | There were no challenges related to this activity. | No additional support from CDC is needed.
Partner and Network Engagement | CWG Participation | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Grantee will participate on the Content Work Group bimonthly calls, and specific CWG teams as appropriate. Proposals for CWG activities will be developed, submitted, reviewed, and ranked when solicited. |  |  | Q1-Q4 | Complete | Iowa staff participated on the CWG calls, and provided input as requested on CWG teams. No teams met during the reporting period due to the COVID-19 response. | The COVID-19 response disrupted normal CWG operations, and staff vacancies limited the number of staff available. | No additional support from CDC is needed.
| PI Forum Participation | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will participate on the PI Forum bimonthly calls. |  |  | Q1-Q4 | Complete | Iowa staff participated on the PI Forum calls when held. Several were cancelled during the reporting period due to the COVID-19 response. | The COVID-19 response disrupted normal PI Forum Scheduling. | No additional support from CDC is needed.
| SND Participation | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will participate on the Standards and Network Development Group calls, and specific SND teams as appropriate. |  |  | Q1-Q4 | Complete | Iowa staff participated on the SND calls when held. Several were cancelled during the reporting period due to the COVID-19 response. | The COVID-19 response disrupted normal SND call Scheduling, and staff vacancies limited the number of staff available. | No additional support from CDC is needed.
| PMO Participation | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will participate on the Program Marketing and Outreach Group calls, and specific PMO teams as appropriate. |  |  | Q1-Q4 | Complete | Iowa staff participated on the PMO calls when held. Several were cancelled during the reporting period due to the COVID-19 response. | The COVID-19 response disrupted normal PMO call Scheduling, and staff vacancies limited the number of staff available. | No additional support from CDC is needed.
| Data Request Tracking | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will track and respond to requests for data not readily accessible on the tracking portal. |  |  | Q1-Q4 | Complete | Iowa Tracking staff assisted in fulfilling 98 data requests during the reporting period. | Staff vacancies occasionally increased response time. | No additional support from CDC is needed.
| Data Request Evaluation | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will evaluate requests for data not readily accessible on the tracking portal to identify and prioritize public health concerns and priorities. |  |  | Q1-Q4 | Complete | Data requests were evaluated to inform future projects. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Partnership Plan | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Grantee will review and update the Partnership Plan. |  |  | Q1-Q2 | Complete | Partnership Plan submitted and feed back received | There were no challenges related to this activity. | No additional support from CDC is needed.
| External Partner Engagement | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Grantee will collaborate with the Data Management program to identify and engage external partners involved with the state specific content under development. |  |  | Q1-Q4 | Complete | Three new partners were engaged during the reporting period as reported in the PM Collection tool. | There were no challenges related to this activity. | No additional support from CDC is needed.
| TAG Engagement | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Grantee will engage the Tracking Advisory Group of existing partners in ongoing review and expansion of Iowa Tracking Portal. |  |  | Q1-Q4 | Complete | TAG was engaged throughout the year. | The COVID-19 Response created numerous scheduling and time commitment issues while engaging with partners. | No additional support from CDC is needed.
| TAG Priority Review | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will engage the Tracking Advisory Group of existing partners to identify and prioritize public health concerns and priorities. |  |  | Q1-Q4 | Complete | TAG is part of the team preparing to conduct a followup portal evaluation to the one completed in 2017 | The COVID-19 Response created numerous scheduling and time commitment issues while engaging with partners. | No additional support from CDC is needed.
| University Collaboration | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Grantee wil maintain the existing relationship with the University of Iowa in support of the Iowa Tracking portal. Collaborative efforts are spread through the proposed projects. |  |  | Q1-Q4 | Complete | University of Iowa continues to assist the tracking program with Training, Content Review, and Portal evaluation processes. | The COVID-19 Response created numerous scheduling and time commitment issues while engaging with partners. | No additional support from CDC is needed.
| Media Collaboration | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | Grantee will coordinate with the department Public Information Officer to promote Tracking and the Tracking Portal through earned media. Media contacts with the Iowa Department of Public Health are established and maintained through the department Public Information Officer. |  |  | Q1-Q4 | Complete | Tracking worked with the Public Information Office for each portal update. | Work on this activity has been delayed due to PIO staff turnover, and COVID-19 response efforts. | No additional support from CDC is needed.
| National Presentation | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | Grantee will seek opportunities to present at national or regional conferences. |  |  | Q1-Q4 | Complete | No presentations were made during the current reporting period. Multiple presentations were made in previous reporting periods. | The COVID-19 Pandemic limited opportunities for such presentations. | No additional support from CDC is needed.
| National Co-Presentation | Communications 2 (C2) | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner | Grantee will seek opportunities to co-present with other grantees at national or regional conferences. |  |  | Q1-Q4 | Complete | No presentations were made during the current reporting period. Multiple presentations were made in previous reporting periods. | The COVID-19 Pandemic limited opportunities for such presentations. | No additional support from CDC is needed.
| Communications Plan | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Grantee will review and update the Communications Plan. |  |  | Q1-Q2 | Complete | Communications Plan submitted and feed back received | Staff vacancies resulted in maintaining status quo. | No additional support from CDC is needed.
| Tracking Priority Review | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will engage existing and new partners to maintain and enhance the influence of Tracking in Iowa through the proposed projects. |  |  | Q1-Q4 | Complete | New and existing partners were engaged during the reporting period as reported in the PM Collection tool. | The COVID-19 Response created numerous scheduling and time commitment issues while engaging with partners. | No additional support from CDC is needed.
| Staff Development | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Grantee will use departmental staff evaluation tools to identify staff capacity, resource, and training needs/opportunities. |  |  | Q1-Q4 | Complete | Staff evaluation tools were completed as part of the annual evaluation process, and led to the identification of staff that participated in Tableau trainings. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Management Meetings | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will attend monthly meetings with Data Management to ensure alignment of objectives with public health concerns and priorities. |  |  | Q1-Q4 | Complete | Monthly meetings were conducted throughout the reporting period. | Staff vacancies and the COVID-19 response presented unique challenges, but were overcome. | No additional support from CDC is needed.
| Executive Meetings | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will attend quarterly meetings with Department Leadership to ensure alignment of objectives with public health concerns and priorities. |  |  | Q1-Q4 | Complete | Quarterly meetings were conducted throughout the reporting period. | Staff vacancies and the COVID-19 response presented unique challenges, but were overcome. | No additional support from CDC is needed.
| IM Meetings | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | Grantee will coordinate with Information Management to Evaluate gaps or barriers to effective use of data. |  |  | Q1-Q4 | Complete | Monthly meetings were conducted throughout the reporting period. | Staff vacancies, Administrative transitions, and the COVID-19 response presented unique challenges, but were overcome. | No additional support from CDC is needed.
Training and Capacity Building | Visualize This Training Development | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Grantee will collaborate with the U of I to develop a Data Visualization training course. |  |  | Q1-Q2 | Complete | The first session of the "Visualize This: Storytelling With Data" course was held in November/December. | The course was originally conceived as a hybrid in person/online training, however the COVID-19 Pandemic led to the planned in person portions beoing conducted through online Zoom sessions. | No additional support from CDC is needed.
| Visualize This Training Scheduling | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Grantee will collaborate with the University of Iowa to schedule and conduct Data Visualization training sessions. |  |  | Q1-Q4 | Complete | The first session of the "Visualize This: Storytelling With Data" course was held in November/December. | The course was originally conceived as a hybrid in person/online training, however the COVID-19 Pandemic led to the planned in person portions beoing conducted through online Zoom sessions. | No additional support from CDC is needed.
| Visualize This Listserve | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of scheduled trainings via listserv. |  |  | Q1-Q4 | Complete | Listserve message was sent. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Visualize This Materials | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will distribute tracking communication products at Data Visualization training. |  |  | Q1-Q2 | Complete | Materials distributed as part of the course materials | There were no challenges related to this activity. | No additional support from CDC is needed.
| Tackling Data Scheduling | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Grantee will collaborate with the University of Iowa to schedule and conduct Tackling Data training sessions. This is based on continued interest and demand from partners. |  |  | Q1-Q2 | Complete | Four "Tackling Data" trainings were conducted during the reporting period. | The COVID-19 Pandemic excelerated the intent to transistion the course from a single day in person training to a hybrid in person/online training, and also led to the planned in person portions being conducted through online Zoom sessions. | No additional support from CDC is needed.
| Tackling Data Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of scheduled trainings via listserv. |  |  | Q1-Q2 | Complete | Listserve message was sent. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Tackling Data Materials | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will distribute tracking communication products at Tackling Data training. |  |  | Q1-Q2 | Complete | Materials distributed as part of the course materials | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data COP Curriculum Development | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Grantee will coordinate with the Data and Informatics Community of Practice to include Tracking principles in the curriculum for training. |  |  | Q1-Q2 | Complete | Iowa coordinated with the Data and Informatics Community of Practice to incorporate tracking into trainings. | Due to the COVID-19 Pandemic the IDPH Data Day was transitioned from a one day in person event, into a series of online sessions. | No additional support from CDC is needed.
| IDPH Data Day Materials | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will distribute tracking communication products at IDPH Data Day. |  |  | Q1-Q2 | Complete | Materials distributed as part of multiple sessions. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Training Video Development | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Grantee will collaborate with the University of Iowa to develop video tutorials targeted at both the use of the Iowa Tracking Portal and the data and measures published. |  |  | Q1-Q4 | Complete | Iowa collaborated with the Univesity of Iowa to develop 3 training videos. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Training Video Publishing | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Grantee will publish video tutorials on the department YouTube channel and link or embed on Iowa Tracking portal. |  |  | Q1-Q4 | Complete | Iowa published the videos on the department YouTube channel as well as on the tracking portal. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Training Video Promotion | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will include new tutorial videos in quarterly announcement of published updates via listserv. |  |  | Q1-Q4 | Complete | Iowa distibuted the portal videos via the Tracking listserv. | There were no challenges related to this activity. | No additional support from CDC is needed.
Portal Promotion | TAW Participation | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Grantee will participate in Tracking Awareness Week planning activities as part of the PMO group work. |  |  | Q1-Q4 | Complete | Iowa participated in the 2020 Tracking Awareness Week. | There were no challenges related to this activity. | No additional support from CDC is needed.
| TAW Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate Tracking Awareness Week materials through Social Media. |  |  | Q1-Q4 | Complete | Iowa promoted the 2020 Tracking Awareness Week via social media channels. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Midwest PMO Participation | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity | Grantee will participate in efforts by the Midwest PMO group to develop coordinated outreach materials. |  |  | Q1-Q4 | Complete | Iowa participated on the PMO Midwest workgroup | Staff vacancies resulted in less active participation on the Midwest PMO group than in previous years. | No additional support from CDC is needed.
| PMO Winter Activity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate coordinated materials through Social Media. |  |  | Q1-Q2 | Complete | Iowa disseminated messaging on Water Quality and Health Equity via social media channels | There were no challenges related to this activity. | No additional support from CDC is needed.
| PMO Spring Activity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate coordinated materials through Social Media. |  |  | Q1-Q2 | Not Started | No success | The 2020 Spring coordinated activity was made optional and Iowa was unable to participate due to the COVID-19 Response effort. | No additional support from CDC is needed.
| PMO Summer Activity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate coordinated materials through Social Media. |  |  | Q1-Q3 | Not Started | No success | The 2020 Summer coordinated activity was made optional and Iowa was unable to participate due to the COVID-19 Response effort. | No additional support from CDC is needed.
| PMO Fall Activity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate coordinated materials through Social Media. |  |  | Q1-Q4 | Complete | Iowa disseminated messaging on Carbon monoxide data and the time change via social media channels | There were no challenges related to this activity. | No additional support from CDC is needed.
| Gov Conference Networking | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Grantee will network at the Iowa Governor's conference to engage potential partners. |  |  | Q1-Q3 | Not Started | The Iowa Governor's Conference was cancelled due to the COVID-19 Pandemic | The Iowa Governor's Conference was cancelled due to the COVID-19 Pandemic | No additional support from CDC is needed.
| Gov Conference Materials | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will distribute tracking communication products at Iowa Governor's conference. |  |  | Q1-Q3 | Not Started | The Iowa Governor's Conference was cancelled due to the COVID-19 Pandemic | The Iowa Governor's Conference was cancelled due to the COVID-19 Pandemic | No additional support from CDC is needed.
Sub-County Asthma Evaluation | Asthma Geocoding | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Grantee will geocode Asthma Hosp Discharge data to the census tract level. |  |  | Q1-Q4 | Not Started | Efforts to implement a geocoding process have delayed the start of this project. | Work on this activity has been delayed due to IT staff turnover, and COVID-19 response efforts. | No additional support from CDC is needed.
| Sub-county Asthma Analysis | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Grantee will develop a script to analyze sub-county data to identify spatial and demographic patterns of asthma. |  |  | Q1-Q4 | Not Started | Dependent on above delayed activities. | Work on this activity has been delayed due to IT staff turnover, and COVID-19 response efforts. | No additional support from CDC is needed.
| Sub-County Asthma Visualization | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop a visualization of the sub-county data that highlights patterns and inequities identified. |  |  | Q1-Q4 | Not Started | Dependent on above delayed activities. | Work on this activity has been delayed due to IT staff turnover, and COVID-19 response efforts. | No additional support from CDC is needed.
| Sub-County Asthma Report | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will integrate the visualization into a report template to assist in the Community Health Needs Assessment and Health Improvement Planning process. |  |  | Q1-Q4 | Not Started | Dependent on above delayed activities. | Work on this activity has been delayed due to IT staff turnover, and COVID-19 response efforts. | No additional support from CDC is needed.
| Sub-County Asthma Evaluation | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will track use of the disseminated report and work with users to demonstrate impact through Public Health Actions. |  |  | Q1-Q4 | Not Started | Dependent on above delayed activities. | Work on this activity has been delayed due to IT staff turnover, and COVID-19 response efforts. | No additional support from CDC is needed.
Sub-County Private Well Evaluation | Sub-County Private Water Township Join | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will procure and integrate a shapefile and geodatabase that represents the Township level of sub-county data. |  |  | Q1-Q4 | Not Started | No successes, it is unlikely this project will be completed in the current funding year. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been delayed for multiple reasons: 1. technical issues with the source data connection, 2. IT staff turnover, 3. COVID-19 response efforts. | No additional support from CDC is needed.
| Private Water Township Analysis | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Grantee will develop a script to analyze sub-county data to identify spatial and demographic patterns of private well testing. |  |  | Q1-Q4 | Not Started | Dependent on above postponed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Private Water Township Visualization | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop a visualization of the sub-county data that highlights patterns and inequities identified. |  |  | Q1-Q4 | Not Started | Dependent on above postponed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Private Water Township Report | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will integrate the visualization into a report template to assist in the Community Health Needs Assessment and Health Improvement Planning process. |  |  | Q1-Q4 | Not Started | Dependent on above postponed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
| Private Water Township Evaluation | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will track use of the disseminated report and work with users to demonstrate impact through Public Health Actions. |  |  | Q1-Q4 | Not Started | Dependent on above postponed activities. Effort has been redirected to COVID-19 response projects that have been added to the workplan. | Work on this activity has been postponed as the Immunization Program is overwhelmed by the COVID-19 response effort. | No additional support from CDC is needed.
COVID-19 Case and Hospital Resource Tracking | Data Evaluation | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | Grantee will work with the IDPH COVID-19 Incident Management Structure to evaluate data needs and available data to make recommendations for improvements to data collection instruments and measures. |  |  | Q2-Q4 | Complete | Tracking worked to integrate data flows for case reporting, deaths reporting, hospital bed capacity and PPE stock, and LTC facility reporting. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Query | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will work with the IDPH COVID-19 Incident Management Structure to identify needed data sources. |  |  | Q2-Q4 | Complete | Tracking worked to integrate data flows for case reporting, deaths reporting, hospital bed capacity and PPE stock, and LTC facility reporting. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Connection | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will coordinate with Information Management to establish data connections and import processes to ensure accessibility of COVID-19 Case and Hospital Resource data from relevent data sources. |  |  | Q2-Q4 | Complete | Developed SOPs and routine processes supported the efficient integration of data flows to support COVID-19 surveillance. | IT staff turnover challenged the ability to complete work, however it was completed in April and continues to be used. | No additional support from CDC is needed.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of COVID-19 Case and Hospital Resource data from relevent data sources. |  |  | Q2-Q4 | Complete | Developed SOPs and routine processes supported the efficient integration of data flows to support COVID-19 surveillance. | IT staff turnover challenged the ability to complete work, however it was completed in April and continues to be used. | No additional support from CDC is needed.
| Data Sharing | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will work with the IDPH COVID-19 Incident Management Structure to develop and publish data visualizations. |  |  | Q2-Q4 | Complete | Data visualizations were published and used in April and early May. | On May 7th, the Iowa COVID-19 data visualization was transitioned to a third party contractor procured through the Governor’s office to manage the dissemination of publicly shared data and allowed IDPH to focus resources on other aspects of the response effort. | No additional support from CDC is needed.
| PHA Development | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will track implementation and use of data visualizations to demonstrate the impact. |  |  | Q2-Q4 | In Progress | A PHA was developed and submitted surronding the impact of this effort. | The initial submission was returned by CDC with request for additional details on impact. A revised PHA was submitted in Januaryt 2021. | No additional support from CDC is needed.
COVID-19 Vaccine Priority Group Planning and Distribution | Data Evaluation | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | Grantee will work with the IDPH COVID-19 Incident Management Structure to evaluate data needs and available data to make recommendations for improvements to data collection instruments and measures. |  |  | Q2-Q4 | Complete | Tracking worked to integrate data flows for multiple categories of population groups (demographics, occupation, chronic illness) to assist in vaccine priority group planning. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Query | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will work with the IDPH COVID-19 Incident Management Structure to identify needed data sources. |  |  | Q2-Q4 | Complete | Tracking worked to identify and integrate data flows for multiple categories of population groups (demographics, occupation, chronic illness) to assist in vaccine priority group planning. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Connection | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will coordinate with Information Management to establish data connections and import processes to ensure accessibility of COVID-19 Vaccine and risk group population data from relevent data sources. |  |  | Q2-Q4 | Complete | Developed SOPs and routine processes supported the efficient integration of data flows to support COVID-19 vaccine planning. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of COVID-19 Vaccine and risk group population data from relevent data sources. |  |  | Q2-Q4 | Complete | Developed SOPs and routine processes supported the efficient integration of data flows to support COVID-19 vaccine planning. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Sharing | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will work with the IDPH COVID-19 Incident Management Structure to develop and publish data visualizations. |  |  | Q2-Q4 | In Progress | Data visualizations were disseminated to state and local partners in November, and continue to be updated and used as the state works through Phase 1 of the vaccine distribution. A public report was published in January and is updated daily. | There were no challenges related to this activity. | No additional support from CDC is needed.
| PHA Development | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will track implementation and use of data visualizations to demonstrate the impact. |  |  | Q2-Q4 | In Progress | Tracking continues to monitor and evaluate the use of the developed tools to drive action. A PHA will be developed. | There were no challenges related to this activity. | No additional support from CDC is needed.
Seasonal Influenza Surveillance Report | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will coordianate with the Center for Acute Disease Epidemiology to develop the process to load and transform Seasonal Influenza Surveillance data to generate measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. |  |  | Q3-Q4 | In Progress | Tracking was approached by CADE to initiate this project in December 2020. The project scope and business requirements are currently under development. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Seasonal Influenza Surveillance measures from the appropriate data sources. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of Seasonal Influenza Surveillance measures. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Internal Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and disseminate data visualizations of Seasonal Influenza Surveillance measures for use by IDPH staff. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Internal Data Evaluation | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will coordinate with the Center for Acute Disease Epidemiology to track and evaluate the use of the internal reports to demonstrate impact. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.
| PHA Development | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will document and report impact. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.
| External Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of Seasonal Influenza Surveillance measures on the Tracking Portal for partners and the general public. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of Seasonal Influenza Surveillance measures. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the Seasonal Influenza Surveillance measures. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published Seasonal Influenza Surveillance measures via listserv. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.
| Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published Seasonal Influenza Surveillance measures via Social Media channels. |  |  | Q3-Q4 | Not Started | Dependent on above in progress activities. | There were no challenges related to this activity. | No additional support from CDC is needed.

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year