## Instructions
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Annual Performance Report (APR) - Section I
Budget Period: August 1, 2019 - July 31, 2020 (Budget Year 3)
Reporting Period: February 1, 2019 - January 31, 2020.
Instructions Please use this workbook to document progress for your Budget Year 3 Work Plan as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section I of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)." The Work Plan tab includes the Year 3 plan you submitted in your 2019 APR. Columns I-L, with the orange Continuation Report (Section I) banner, are where you should enter information about your progress. For each activity, select the Current Status from the dropdown menu (not started, complete, in progress, or behind schedule) and provide relevant information under Successes, Challenges, and CDC Support Needed.
Technical Support If you need technical support when using this template, email your project officer.

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
Arizona Project Narrative Budget Year 3
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan." Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
SCIENCE AND CONTENT | Project 1- Conduct Program Marketing and Outreach
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Grantee will update and implement annual communication plan for year 3. Communication activites implemented for year 3 will include regular updates to stakeholders and the general public on on Tracking activites including new data uploads and other new features on the Data Explorer. This will be done through call out boxes on the website, newsletter updates, and social media posts. Grantee will also participate in program wide communcation activities including Tracking Awareness week 2020. Grantee will continue to promote and market the Tracking Network (local & national) to appropriate audiences. These presentations will include content on data avaliable on both networks, how to use the Data Explorer and potential uses for the data. Additional tracking communication messags will be developed and disseminated to appropriate audiences. These communication products may include community profiles, factsheets, infographics, and other products that could be developed from needs assessments. Efforts wil be led by our EPHT health education team (lead: health educator, risk communication specialist, and IT web designer). The group will communicate by in-person meetings at least bi-weekly, telephone, and email. Overall team meetings with other EPHT teams including science and content, and technology and informatics, and program services will occur at least monthly to ensure a shared vision. | Activity 1) Update communication plan according to CDC guidelines. (Complete) Activity 2) Grantee will participate in Tracking Awareness Week by posting social media posts (In Progress) Activity 3) Post announcements on Tracking website to call attention to new data, new features, and new communication products on Arizona's Data Explorer. Distribute newsletters communicating new data and applications to relevant audiences. (In Progress) Activity 4) Grantee will post social media to Facebook and Twitter regarding grantee NCDM portal updates, PHAs, Tracking Awareness Week, and other multi collaborative grantee communication activities. (Complete) Activity 5) Present on Tracking portal both local and national to relevant stackholders. Distribute existing and new communication materials in year 2. (Complete) Activity 6) Grantee will post website updates regarding new and optional NCDM added to the website. Specifically, the relation between environment and health for the NCDM as well as supporting resource websites (internal and external to the agency). (In Progress) Activity 7) Hand out Tracking materials at presentations and other outreach events (Complete) Activity 8)The Grantee will participate with PMO West in Lead Poisoning Awareness Week and other topics brought up by the group. The Program will post social media, blogs, and email newsletter to listserv. (In Progress) Activity 9) Conduct needs assessment with stakeholders (i.e tribes or county health departments) and develop new communication tools for them. (Complete) Activity 10) Science & Content team will provide Tracking required/optional/non-NCDM written updates on Data Explorer. (Complete) Activity 11) AZ PMO, Science & Content, and Program Services will meet with technology & informatics team to address feedback and improve Data Explorer with recommendations by users of the data. (Complete) Activity 12) PMO will do outreach to university students and health department staff about EPHT trainings and internship opportunities. (Complete) | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 2
|  |  | 2 | 2 | 2 | 2 | 8
Project 2- Initiate, Maintain, and Expand Partnerships
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Grantee will update and implement partnership plan to develop and maintain relationship with previous and new partners. In year 3, Grantee will continue to communicate with ADHS tribal liason to ensure Tribal connections are maintained and enhanced. We will continue to maintain and expand our internal partners including : Childhood Lead Poisoning Prevention Program, Enviromental Toxicology, Climate and Health Program, Office of Cancer Registry, Birth Defects Program, Safe WATCH, Biomonitoring Program, Public Health Emergency Prepardeness Program, and Arizona Radiation Regulatory Agency. We will also expand our external partnerships with traditonal partners like county health departments (e.g.) Maricopa County Public Health Department, universities (Arizona State University and University of Arizona), and Arizona Department of Enviromental Quality as well as non-traditional partners like Arizona Department of Transportation, non-profit organizations, healthcare organizations, and tribal governments. The grantee will send out press releases and EPHT training materials (e.g. how-to-video) to media and provide responses and interviews to reporters regarding data, PHAs, and other partner activities. The grantee will also partner on national conferences and webinars with PMO West or EPHT content workgroups. Efforts wil be led by our EPHT health education team (lead: health educator, risk communication specialist, /health educator, and IT web designer). The group will communicate by in-person meetings at least bi-weekly, telephone, and email. Overall team meetings with other EPHT teams including science and content, and technology and informatics, and program services will occur at least monthly to ensure a shared vision. | Activity 1) Update partnership plan for year 3. Continue to meet and collaborate with internal partners to guide Tracking program activities. (In Progress) Activity 2) Hold at least 2 TAG meetings per year, one of which will be in person. (In Progress) Activity 3) Lecture and host intern from local Universities. Continue to maintain relationship with University of Arizona College of Public Health Program and Arizona State University. (Complete) Activity 4) Send out press release through agency media channels (print news, tv, and radio) regarding PHAs and NCDM updates to Data Explorer and respond to media requests by providing subject matter expert interview. Outreach to media partners with use of EPHT Data Explorer training materials (web-based or in person). (In Progress) Activity 5) Co-present at a national or regional meeting or webinar (e.g. Council of State and Territorial Epidemiologists annual meeting or CSTE webinar, or AMS, or NEHA, or APHA) regarding Tracking related project with PMO West or EPHT Content Workgroups. (Complete) Activity 6) Grantee will gather feedback from AZ stakeholders (e.g. users, TAG) on potential new NCDM or non-NCDM. Feedback can be provided via content workgroups and locally new data sets and indicators will be explored based on feedback. (Complete) Activity 7) AZ Technology and Informatics will enlist PMO help for guidance on additional features to add to the public Data Explorer based on stakeholder feedback of Data Explorer. (Complete) Activity 8) AZ PMO will work with Science & Content team to create trainings and content for public health & non-public health stakeholders regarding how to use AZ Data Explorer to support their work. (Complete)
TECHNOLOGY AND INFORMATICS
Project 3- Identify and Integrate Public Health and Environmetnal Data
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The grantee will continue to evaluate each dataset as per CDC recommendations through the CDC Metadata Creation Tool for NCDM. NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC Secure Access Management System (SAMS). Optional NCDM will be collected, formatted, and submitted as per CDC guidance document. NCDM will be uploaded into grantee Data Explorer. The program will identify additional indicators by engaging local partners through TAG meetings, presentations, and outreach. Science and Content Workgroup Staff will participate in grantee CWG. Arizona Content and Science Workgroup staff will participate in grantee meetings. The Program has partnered with MCDPH and the ADEQ through a sub-contract in order to gather perspectives in display of air and water quality data and for novel data element additions to Tracking. Analysis will reduce data gap by creating datasets at sub-county scale (primary care area or other small geographical area). Delegation of work will be led by the Science and Content Capacity Team (PI, Epidemiologist, Risk Communication Specialist, Agency Liaison/Policy Advisor, GIS Developer, GIS Supervisor, IT Manager). | Activity 1) Grantee will continue to identify and evaluate NCDM data and projects done in collaboration with CWG. (Complete) Activity 2) Grantee will continue to prepare NCDM for CDC data submissions and upload NCDM to the grantee Tracking Portal as per CDC requirements. (Complete) Activity 3) Grantee will continue to maintain NCDMs as per CDC guidance and disseminate via grantee network. (Complete) Activity 4) Grantee will continue to engage local partners throgh the TAG, outreach, and presentations and participate in CWG in order to identify additional indicators. (Complete) Activity 5) Grantee will continue collaboration with partners to improve existing and adopt new NCDM developed by CWG. (Complete) Activity 6) The Program will partner with the Arizona Department of Environmental Quality (ADEQ) through a sub-contract in order to gather their perspectives the display of air and water quality data from ADEQ (such as representativeness, data granularity, time scale, and accuracy). The program will also work with the TAG to identify limitations and solutions for data in environmental or public health data sets (e.g. sub-county). (Complete) Activity 7) Technology and Informatics team will ensure that programmers and software are available that science and content team can use to create existing & new NCDM in XML for submission. (Complete) Activity 8) AZ PMO will create website plain messaging language to accompany new NCDM datasets on state portal and meet with AZ Science and Content Team to ensure accuracy of website information. (Complete)
COMMUNICATIONS
Project 4- Analyze and Apply Data to Translate Science into Action
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program’s Epidemiologist with support from the PI will conduct routine analysis and data-cleaning of required and optional NCDM to evaluate quality and completeness of data using SAS and the CDC DIVE validation tool. Pilot analyses will also be done on CWG indicators under development. The Epidemiologist will develop SAS programs and protocols to routinely use Tracking data to identify vulnerable populations using numbers, rates, and percentages to identify elevated risk areas. Results will be shared with stakeholders via email, media, and meetings. From this information, health education material will be developed to aid in prevention efforts for priority areas. The Program has partnered with MCDPH through a sub-contract to gain a program epidemiologist. Data on heat illness in children will also be used in an advanced time-series analysis to inform the development of recommendations for schools on how to mitigate the effects of extreme heat among students. Delegation of work will be led by the Science and Content Capacity Team (PI, Epidemiologist, Risk Communication Specialist, Agency Liaison/Policy Advisor, GIS Developer, GIS Supervisor). | Activity 1) Grantee will continue to conduct routine analyses of NCDM to evaluate data quality and completeness. (Complete) Activity 2) The Epidemiologist will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-NCDM data in the data explorer. For example, age-adjusted rates, report on trends in numbers, crude rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. (In Progress) Activity 3) Grantee will continue to develop SAS programs and protocols for conducting routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards. (In Progress) Activity 4) Grantee will continue to apply and interpret Tracking Data to inform the development and evaluation of public health actions, including useing tracking data on heat-illness in children to inform the development of recommendations for schools on how to mitigate the effects of extreme heat on students. (In Progress) Activity 5) Science & Content will work with PMO, Program Services, and Technology and Informatics to develop new Data Explorer tools to answer analysis questions by EPHT users for PHAs. (Complete) Activity 6) PMO will do a news release and social media regarding EPHT data. (In Progress) Activity 7) Science & Content will work with PMO, Program Services, and Technology and Informatics to develop new portal tools to answer analysis questions by EPHT users for PHAs. The Epidemiologist and PI will also use SAS for data analyses and informing the development and evaluation of public health actions. Tracking data will be used to notify stakeholders regarding changes in environmental and health outcome NCDM at workshops, workgroup meetings, teleconferences, and email. (In Progress)
Project 5- Increase Organizational Capacity to Support the Tracking Network
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program will lead, support, and maintain existing Environmental Public Health Tracking Program within state jurisdiction by staffing appropriately to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the Data Explorer, data analysis support, and data updates. The Program will continue to hold Technical Advisory Group Meetings at least once a year and will encourage Working Groups to meet regularly to address priority projects (e.g. development of a secure Data Explorer, development of community profile reports). The Program will facilitate presentations and webinars with stakeholders that describe how to use the Data Explorer and how to find locally-relevant data. In Years 3-5 The Program will work with Arizona State University School of Geographical Sciences and Urban Planning and other local universities to develop web-based or in-person training program-specific training modules regarding use case. The program will develop a sub-contract with a university stakeholder to formalize the partnership using an interagency service agreement. Internships would be offered working in either program aspects of epidemiology, communications or GIS. ADHS has a formal internship process established with required documentation for insurance purposes. Local universities are familiar with the ADHS internship coordinator. | Activity 1) Grantee will maintain appropriate staffing to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the AZ Data Explorer, data analysis support, and data updates. (Complete) Activity 2) Hold Technical Advisory Group Meetings at least twice a year. Additionally, tracking program staff will meet at least once a month to discuss technical capacity and needs. (Complete) Activity 3) Develop materials and trainings on how to use the Data Explorer. Continue partnerships with University of Arizona to support integration of EPHT into the public health course curriculum (Complete) Activity 4) Deliver web-based or in-person EPHT trainings for public health staff (such as ADHS "How to trainings") and students (Complete) Activity 5) EPHT Program staff will meet with and teach other internal and external partners about EPHT NCDM collection and formatting guidance with programs such as ADEQ, CLPPP, Climate and Health, biomonitoring, toxicology, birth defects, SafeWATCH in order to gather data on existing and new NCDM. (Complete) Activity 6) Technology and Informatics Teams and Science and Content team will develop scripts and SOPs (e.g. SAS Programs) to help partner programs which support AZ EPHT to help expedite data call uploads (e.g. WQL,CLP2,CLP4,BD, PWS). (Complete) Activity 7) Science and Content Team (epidemiologist and PI) will establish relationship with university for assisting on collaborative public health project using EPHT data and teaching university students about EPHT. (Complete)
PROGRAM SERVICES
Project 6- Monitor the Impact and Performance of Program Activities
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program will submit public health actions twice per year to the project officer through email. PHAs will also be described in an evaluation report & the APR. The PI will assume responsibility for the document. The Program will develop and implement annual evaluation plans, based on the CDC recommendations. The evaluation plan will be coordinated through the Program Service Workgroup led by the Policy Advisor/Liaison and supported by the Principal Investigator. The evaluation plan will also include success stories to document program successes which can be shared on the National Portal. The Science and Content Workgroup, Communications Workgroup and Technology and Informatics Workgroup assigned staff from AZ will participate in workgroups based on area of expertise using teleconferences, webinars, and providing reviews during in-person grantee meetings. The IT Web Designer will provide website statistics and clicks for various subpages of the Tracking Program to identify the most used through Google Analytics which is standard practice for the agency’s websites. Website statistics will be submitted to the project officer by email twice per year and documented in the evaluation plan/ annual progress report. | Activity 1) AZ Science and Content team will use tracking data to help jurisdictions and partners identify public health concerns and develop plans to monitor intervention effectiveness. Data can contribute to local and state health assessment plans and improvement plans. (Complete) Activity 2) Technology and Informatics Team will work with IT leadership to ensure data metrics help align with needs for state health improvement plan and county health improvement plan metrics that may use tracking data to help monitor effectiveness. (In Progress) Activity 3) AZ PMO will post updates and announcements about grantee tracking activities to Tracking listserv and on social media about the impact of program activities on public health in AZ. (Complete) Activity 4) Evaluator assists Science and Content Team on identifying PHA opportunities and writing up quarterly PHAs to CDC. (Complete) Activity 5) Evaluator will lead program services team in finalizing results of year 2 evaluation an dimplementing a plan to impelment recommended improvements along with a timeline. The evaluator will also lead the development of a year 3 evaluation plan. (In Progress) Activity 6) AZ Science and Content, Technology and Informatics, Program Marketnig and Outreach, and Program Services teams formed in year 1 will meet by webinar, in person, or teleconference to assist in Data Explorer review and updates and give feedback on new tools and data sets. (In Progress) Activity 7) AZ PMO Team led by health educator will ask technology and informatics team to use Google Analytics to capture web statistics to submit to CDC and help inform program evaluation. (Complete)
Project 7- Maintain and enhance information technology infrastructure
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Arizona EPHT Data Explorer follows guidance from CDC Tracking Grantee Portal Standards and Recommendations (version 1.) The Data Explorer will continue to be improved by adding additional features and data visuzaliation options based on user feedback and requests. At the request of the TAG, development of a secure Data Explorer will be further explored with the Data and Research Indicators workgroup of the TAG. The TI team will continue to support ADHS goals of streamlining data applications by migrating the Hospital Compare application to the EPHT Data Explorer. Delegation of work will be led by the EPHT Technology and Informatics Team (GIS Supervisor, GIS Developer, and Web Media Specialist). The GIS Developer will handle a majority of efforts at 1 FTE and rely on the GIS Supervisor and for following state standards and procurement of hardware and software. The GIS Developer will communicate at least weekly by email, phone, and in person meetings with PI to ensure science and content updates are incorporated. The TI team will meet monthly for team website meetings with PI and Science and Content Team staff for exchanging updates. | Activity 1) Grantee Data Explorer will continue to be maintained and updated with new NCDM indicators, and grantee will evaluate developing a secure Data Explorer and support multiple dataset analysis. (In Progress) Activity 2) New reporting tools will be created to dynamically display relevant information including dyamically generated community profile reports. (Complete) Activity 3) Statistics of use patterns for the Data Explorer will be analyzed to determine improvement areas and content areas of high interest. The program will maintain a feedback survey for the Data Explorer users and will gather feedback on the Data Explorer and informatics needs from the TAG. (Complete) Activity 4) The PI and the GIS Developer have access to the CDC EPHT SharePoint Site for downloading newest version of the data validation program (DIVE) and indicator templates, CDC’s Secure Access Management System (SAMS) for secure file transfer and metadata creation tool (MCT) and capability to convert SAS datasets to XML. (Complete) Activity 5) The Hospital Compare application will be migrated to the EPHT platform. (In Progress) Activity 6) Sub County data will continue to be added to allow for community based analysis. The state will work with data stewards to determine what advanced options (i.e. age, gender, race/ethnicity, season) can be displayed for each indicator at the sub-county level. (Complete) Activity 7) SAS and SQL and Python scripting will be used to automate the process of validating and updating data. (Complete) Activity 8) Technology and Informatics team will ensure secure and public portal are available for science and content team to conduct routine descriptive epidemiology of NCDM/Non-NCDM to discover patterns of disease, exposure, and hazards in a timely manner (In Progress) Activity 9) .Technology and Informatics team will participate in TAG to hear feedback and disseminate technology updates to AZ TAG. (Complete) Activity 10) Technology and Informatics team will ensure users have access to public and private portal and that internal program staff have access to IT resources for performing NCDM updates/queries. (Complete)
Project 8-Supporting Public Health Emergency Response
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
Project Summary below (200 word max)
| The grantee will support the Department's public health emergency response activations for environmental health hazards (heat, wildfires, etc.) and other public health issues (COVID-19, other emergent pathogens, etc.). The grantee will support the Health Emergency Operations Center (HEOC) by providing technical assistance and personnel. This need will be met by providing IT capacity and GIS mapping capabilities; providing staff to track resources and volunteers; providing epidemiological experitise to manage cases and provide support to local and county health departments in response. Communicating risk of health and environmental hazards will be crafted for social media messaging and through phone calls, emails, and webinars as needed. NCDM and non-NCDM data will be used to help evaluate risk in the community. | Activity 1) Support the Health Emergency Operations Center with EPHT expertise; such as environmental epidemiology, GIS mapping, and health education for public health emergencies such as COVID-19, wildfires, and heat. (In Progress) Activity 2) Sharing key messaging about emergent environmental health issues of public health concern through EPHT listserv and social media messages. For example, share information on heat related mortality before the beginning of heat season or address community members or stakeholder concerns regarding chemicals levels in their drinking water (PFAS, lead, etc.) or hazardous waste sites. (In Progress) Activity 3) Utilize NCDM and non-NCDM data to assess the initial impact that COVID-19 had on public health and the environment by assessing air quality measures and transportation utilization. (In Progress) Activity 4) TI resources will be deployed to ensure effective response to the COVID-19 pandemic, opioid crisis, and revamped hospital compare application. (In Progress) Activity 5) COVID-19 data will be routinely processed, geocoded, and analysed. Data will be dissemnated to stakeholders and the public. (In Progress)

## Work Plan
EH17-1702 Budget Period: |  |  | August 1, 2019 - July 31, 2020
Date Submitted: |  |  | 2019-04-10
No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activity description. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project. | Continuation Report (Section I)
Project Title | Activity Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline | Status | Successes | Challenges | CDC Program Support Needed
Project 1- Conduct Program Marketing and Outreach | 1 | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Review previous year's communication plan and re-evaluate metrics. Update communication plan according to CDC guidance. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2 | Complete
| 2 | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Participate in Tracking Awareness Week (2020) by posting social media posts. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4 | In Progress
| 3 | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Post announcements on Tracking Website and Data Explorer to call attention to new data, new features, and new communication products. Distribute quarterly newsletters communicating new data and applications to relevant audiences. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | In Progress | New inforgraphics posted to website including Environmental Public Health Tracking for professionals and PFAS in drinking water. 5 newsletters sent to EPHT listserv and posted to website.
| 4 | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will post social media to Facebook and Twitter regarding grantee portal updates, PHAs, Tracking Awareness Week, and other multi-collaborative grantee communication activities. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete | 93 social media posts with 316 total engagements and 18.2 M Facebook reach.
| 5 | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | Present on tracking program to local and nationally relevant stakeholders. Distribute existing and new communictions materials during year 3. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete
| 6 | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will post website updates regarding new and and optional NCDM added to the Data Explorer. Content will highlight the relationship between the environment and health as well as supporting resources websites (internal and external to the agency) | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | In Progress
| 7 | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Hand out tracking materials at presentations and other outreach events | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete
| 8 | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity | The grantee will participate in the PMO West-led quarerly communication campaign, Tracking Awareness Week, and other topics brought up by the group. The program will post social media posts and email newsletters to the listserv. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | In Progress | EPHT participated in Lead Poisoning Prevention Week and all other PMO Quarterly Communication Activites.
| 9 | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Conduct a needs assessment with a target audience (i.e. tribal partners, county health departments) and develop a new communication tool for them. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4 | Complete | Arizona Tracking conducted needs assessment of county health directors and TAG members to determine what communication gaps should be addressed in the Tracking program. This resulted in developing a septic system brochure and audience based infographics to explain the tracking program.
| 10 | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Science & Content team will provide Tracking required/optional/non-NCDM written updates on the Data Explorer and information to AZ PMO team for outreach efforts. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete
| 11 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | AZ PMO, Science & Content, and Program Services will meet with technology & informatics team to address feedback and improve Data Explorer with recommendations by users of the data. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Team held weekly meetings to address ongoing feedback, including feedback from TAG meeting, spatial epidemiology class, and data portal feedback survey results.
| 12 | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | PMO will do outreach to university students and health department staff about EPHT trainings and internship opportunities. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete
Project 2- Initiate, Maintain, and Expand Partnerships | 1 | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Update partnership plan for year 3. Continue to meet and collaborate with internal partners to guide Tracking program activities. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | In Progress
| 2 | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Hold at least 2 TAG meetings per year, at least 1 of which will be an in-person meeting. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | In Progress | Completed first TAG meeting in November 2019 as a webinar. Second meeting is scheduled to be summer of 2020.
| 3 | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Lecture at local universities and host at least one intern. Continue to maintain relationship with University of Arizona College of Public Health Program and Arizona State University. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete | Tracking PI has presented at 2 universities on Tracking. One internship completed with graduate student to develop infectious disease indicators for the Data Explorer.
| 4 | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | Send out press release through agency media channels (print news, tv, and radio) regarding Data Explorer updates, PHA's, or trends found in data. Respond to any media requests by providing subject matter expert interview. Outreach to media partners with use of EPHT data explorer training materials (web-based or in person). | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | In Progress |  | Press release was delayed due to Program Information Office not able to review due to competing priorities.
| 5 | Communications 2 (C2) | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner | Co-present at a national or regional meeting or webinar (e.g. Council of State and Territorial Epidemiologists annual meeting or CSTE webinar, or AMS, or NEHA, or APHA) regarding Tracking related project with PMO West or EPHT Content Workgroups | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete | EPHT epidemiologist partnered with Arizona's BRACE program to present at the American Meteorological Society annual meeting in January 2020. Heat-related illness and death data from the EPHT Data Explorer was used in part to describe the health and economic burden of extreme heat in Arizona for years 2008-2018. EPHT epidemiologist was asked to present at the National Birth Defects Annual Conference in Washington DC to discuss how EPHT addresses environmental community concerns utilizing the Data Explorer and other tools/resources. The presentation was given shortly after the reporting period in March 2020.
| 6 | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Grantee will gather feedback from AZ stakeholders (e.g. users, TAG) on potential new NCDM or non-NCDM. Feedback can be provided via content workgroups and locally new data sets and indicators will be explored based on feedback. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | Received feedback from TAG during spring 2019 and fall 2019 meetings on datasets that should be added; sucessfully identified and added two infectious disease indicators --West Nile virus and Valley Fever to the Data Explorer | Infectious disease case counts are small, so we had to aggregate to 3-year groupings to display new infectious disease measures. The process to identify a novel data source or measure is time consuming, from identification of data sources, working with partners, managing data sharing agreements, if necessary, deciding upon indicators and measures, and producing metadata. | Potentially develop a master list of novel data sources (non-NCDM data) that grantee states include on state Data Explorers. This might allow an easy reference to identify a state that has sucessfully published novel data sources or non-NCDM's requested by local stakeholders.
| 7 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | AZ Technology and Informatics will enlist tracking team help for guidance on additional features to add to the Data Explorer based on stakeholder feedback of Data Explorer. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Data explorer enhanced with new capabilities based on feedback results from TAG, spatial epidemiology class, and feedback surveys, such as easier access to the application, bulk downloads, search function, and advanced chart options.
| 8 | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | AZ PMO will work with Science & Content team to create trainings and content for public health & non-public health stakeholders regarding how to use AZ Data Explorer to support their work. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete | Infographic was developed for public health professionals on how to use the Data Explorer and answer questions. AZ EPHT mentored Federated States of Micronesia and conducted 3-day onsite training on EPHT and data analysis tools through the ASTHO EPHT Fellowship program.
Project 3- Identify and Integrate Public Health and Environmental Data | 1 | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Evaluate each dataset using criteria (CDC EPHTN Tracking Network Profile Version 1.2 for metadata standards) in metadata reports through the CDC Metadata Creation Tool for NCDM. We will participate in projects regarding CWG. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | Entered into data sharing agreement with Office of Economic Opportunity to model new food swamp indicator for Coomunity Design Workgroup. |  | Integrate sub-county metadata specific questions on geocoding standards into the metadata creation tool as standard questions
| 2 | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC. In conjunction, NCDM will be uploaded into grantee Tracking Portal supported by ESRI GIS software and SAS for data analysis. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | To improve and standardize data validation during fall data call, we utilized CDC's sample data validation code to check for data quality and completeness for all NCDMs. Submission of sub-county datasets for asthma and heart disease for years 2010-2018 were validated and accepted. | Data is still withheld in our hospital discharge database due to poor data quality for 2017 in some counties. We plan to resubmit data when the problem is resolved.
| 3 | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Required and optional NCDM will be collected, formatted, and submitted using the guide “Standards for Nationally Consistent Data and Measures within the CDC’s National Environmental Public Health Tracking Network Version 4.0.” Data will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC Secure Access Management System (SAMS). | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete
| 4 | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | The program will identify indicators needed by local stakeholders by engaging with local partners through TAG meetings and presentations with partners and universities. Science and Content Workgroup Staff will participate in grantee Content Working Groups. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | Developed two new infectious disease indicators requested by stakeholders, West Nile virus and Valley Fever incidence.
| 5 | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Arizona Content and Science Workgroup staff will participate in grantee teleconference, webinars, and in-person grantee meetings to provide input on improvement and development of NCDMs. A budget was requested to send 3 staff to the 2 required annual grantee meetings described in the FOA. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | 2 staff attended PI/PM spring meeting; 3 staff attended in-person grantee fall meeting
| 6 | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | The Program will partner with the Arizona Department of Environmental Quality (ADEQ) through a sub-contract in order to gather their perspectives the display of air and water quality data from ADEQ (such as representativeness, data granularity, time scale, and accuracy). The program will also work with the TAG to identify limitations and solutions for data in environmental or public health data sets (e.g. sub-county). | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | Collaborated with ADEQ to develop new air quality indicator for PM 10 and service area boundary file for community water systems. | Different competing work priorities and plans prevented the development of a proposed air quality indicator with ADEQ
| 7 | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Technology and Informatics team will ensure that programmers and software are available that science and content team can use to create existing & new NCDM in XML for submission. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | All data submissions were met, with the support of IT team where needed to create xmls and submit data.
| 8 | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | AZ PMO will create website plain messaging langugage to accompany new NCDM datasets on state portal and meet with AZ Science and Content Team to ensure accuracy of website information. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete
Project 4- Analyze and Apply Data to Translate Science Into Action | 1 | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | The Program’s Epidemiologist with support from the PI will conduct routine descriptive analysis of NCDM to evaluate quality and completeness of data using SAS and epidemiological analysis as well as use the CDC DIVE validation tool. The statistic will also use data as talking points for 3 planned workshops with local partners. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | Complete
| 2 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | The Epidemiologist will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-ncdm data in the data explorer. For example, age-adjusted rates, report on trends in numbers, crude rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress | Routine descriptive analysis and reports are conducted for heat- and cold-related illnesses and deaths.
| 3 | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | The Program will partner with (MCDPH) through a sub-contract to gain a program epidemiologist. Scope of work will include developing SAS programs and protocols for conducting routine analysis using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards at the county and sub-county scale. Timely reporting of the epidemiologist's findings will help the program's coordination efforts for further investigation with other state and local partners as well as new insights/solutions. The program's epidemiologist will analyze Tracking Data NCDM and report back quarterly of findings through email, teleconference, or in person meetings. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress | Epidemiologist spent time updating surveillance reports, examining health costs associated with heat related illness and death (stakeholder request), and validating sub-county datasets during sub-county submission. | Need more time to develop code and processes to conduct routine analysis of NCDMs and non-NCDMs | Support from journal club to provide processes and sample code for routine analysis of NCDMs
| 4 | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Tracking data on heat-illness in children will be used to inform the development of recommendations for schools on how to mitigate the effects on students. Impacts of the recommendations will be tracked through evaluation efforts that include a state-wide survey on current school heat policies. The program will respond to inquiries from partners for new public health action data needed as requested. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress |  | Analysis of heat-illness in children is still being finalized and recommendations are in development
| 5 | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Science & Content will work with PMO, Program Services, and Technology and Informatics to develop new tools for the Data Explorer that enhance data display and utility. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Based on collaborative efforts with PMO and science team, IT has created new tools to enhance the data explorer, including search functionality, advanced charts, advanced downloads, zoom to selection and quick reports.
| 6 | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | PMO team will do a news release and social media regarding EPHT data. Science and Content team will ensure accurate messages. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | In Progress
| 7 | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Science & Content will work with PMO, Program Services, and Technology and Informatics to develop tools to track program activities and analyses that support external partners and health outcomes of the jurisdiction. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | In Progress | Internally implemented cloud based tracking tools to monitor PHA progress and evaluation | PHA outcomes may take several years to develop quantitative results | Better examples of outputs instead of outcomes for PHAs
Project 5- Maintain and Enhance Information Technology Infrastructure | 1 | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements | Grantee will continue to maintain and update the Data Explorer with new NCDM indicators, and grantee will explore a secure portal based on TAG input | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | In Progress | All portal content was updated in a timely manner. New indicators were created for Cold related illness, Infectious diseases, Drought, Food safety, Wildfires, and SHELDUS all-hazards cost data.
| 2 | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | The epidemiologist will develop code for routine data cleaning (i.e de-deuplication, checking completeness) of tracking data sets for identification of data quality concerns, which will be addressed with the data steward. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Data cleaning processes have been developed. Geocoding processes have been enhanced with imputation.
| 3 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | The program will maintain a feedback survey for Data Explorer users and will gather feedback from the TAG on the informatics needs for the Data Explorer. That TAG will also provide input on how to best address informatics needs to make data readily avaialble for decision makers. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Evaluation results addressed. CDC Api integrated to fill gap in statewide datasets. | Intermittent CDC API failed requests | CDC support was provided to ensure application had appropriate Token access.
| 4 | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | The PI and the GIS Developer have access to the CDC EPHT SharePoint Site for downloading newest version of the data validation program (DIVE) and indicator templates, CDC’s Secure Access Management System (SAMS) for secure file transfer and metadata creation tool (MCT) and capability to convert SAS datasets to XML. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Geocoding & Imputation processes have been enhanced with auto assignment of high low precision for sub county submissions.
| 5 | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | TI team is integrated in to organization technology and infrastructure team and contributes towards organization-wide initiatives and decision-making. The EPHT TI team will migrate the existing Hospital Compare application to the EPHT Data Explorer in alightment with the ADHS strategy to consolidate application infrastructure. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | In Progress | Community profiles dashboard data has been integrated into data explorer. | Working with stakeholders to ensure the hospital compare application meets all needs.
| 6 | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Sub County data will continue to be added to allow for community based analysis. The state will work with data stewards to determine what advanced options (i.e. age, gender, race/ethnicity, season) can be displayed for each indicator at the sub-county level. Dynamically generated local reports will be made available in year 3. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | The quick reports tool was developed to provide insight on relevant local data. Search functionality developed to allow searching for data locally relevant.
| 7 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | SAS and SQL and Python scripting will be maintained and developed as needed to ensure that the process of validating and updating data continues to run smoothly. Data and scripts will be integrated into a new EPHT admin site which will serve as the content management system for managing all measures and indicators. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | The epht admin site has been created and serves as a content management system for epht datasets. New scripts created to automate the process of moving data from dev to production. Cocreated CDC subcounty geocoding standards.
| 8 | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Technology and Informatics team will ensure secure and public Data Explorer are available for science and content team to conduct routine descriptive epidemiology of NCDM/Non-NCDM to discover patterns of disease, exposure, and hazards in a timely manner. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress | Public Data Explorer continues to be enhanced and data added/updated annually. | Secure data portal is still under review. It has been requested by TAG members
| 9 | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | TAG will be asked for feedback during presentations and webinars. Interim emails and surveys to TAG listserve will be conducted as needed to seek input on program decisions. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete
| 10 | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Technology and Informatics team will ensure users have access to the Data Explorer and that internal program staff have access to IT resources for performing NCDM updates/queries. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete
Project 6- Increase Organizational Capacity to Support the Tracking Network | 1 | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will maintain appropriate staffing to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the AZ Data Explorer, data analysis support, and data updates. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete | We are fully staffed and respond to inquiries as they come
| 2 | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Hold Technical Advisory Group Meetings at least twice a year. Additionally, tracking program staff will meet at least once a month to discuss technical capacity and needs. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete | We held 2 TAG meetings: (1) webinar February 2019 and (2) in-person and webinar November 2019 | We are still trying to build membership within the TAG. Most representatives are internal state health dept staff.
| 3 | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Develop materials and trainings on how to use the Data Explorer. Continue partnerships with University of Arizona to support integration of EPHT into the public health course curriculum | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete | Made YouTube tutorial and lectured on spatial epidemology course at University of Arizona. Class project used EPHT data. | Students expected more granular data in the Data Explorer.
| 4 | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Deliver web-based or in-person EPHT trainings for public health staff (such as ADHS "How to trainings") and students | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete | We completed 6 in-person trainings to public health, academia, and other government organizations
| 5 | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | EPHT Program staff will meet with and teach other internal and external partners about EPHT NCDM collection and formatting guidance with programs such as ADEQ, CLPPP, Climate and Health, biomonitoring, toxicology, birth defects, SafeWATCH in order to gather data on existing and new NCDM. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | Complete | Connected with ADEQ, Arizona Office of Economic Opportunity (OEO), and within ADHS (EMS registry system, Office of Infectious Disease)
| 6 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Technology and Informatics Teams and Science and Content team will develop scripts and SOPs (e.g. SAS Programs) to help partner programs which support AZ EPHT to help expedite data call uploads (e.g. WQL,CLP2,CLP4,BD, PWS). | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | SOPs for each content area were documented with scripts and data sources needed to fulfill data calls.
| 7 | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Science and Content Team (epidemiologist and PI) will establish relationship with university for assisting on collaborative public health project using EPHT data and teaching university students about EPHT. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete | Students completed 4 ESRI storymaps during UA spatial epidemiology course using EPHT data. Tutorial on EPHT Program to Phoenix College students during STEAM Day. Two PH internships were completed to develop infectious disease indicators and school heat policy.
Project 7- Monitor the Impact and Performance of Program Activities | 1 | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Science and Content Team, TI team, and evaluator will document and track the metrics and impact of EPHT data and staff resources that contribute to measurable public health impact for outside programs, agencies, and jurisdictions. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Complete
| 2 | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Evaluator will perform data analysis on evaluation data (surveys) collected during year 2 and implement an action plan for implementation of recommended improvements that will include a timeline for the changes. The evaluator will also consider appropriate audiences to survey for year 3 evaluation and develop an evaluation plan | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | In Progress | Preventative medicine fellow developed a tribal engagement plan and documented progress. Improved tribal relations that lead to EPHT in Tribal Lands meeting and identified tribes who would like to partner with EPHT Program. Fellow also surveyed Arizona school districts on school heat policy practices and perceptions to guage interest. | Preventative Medicine Fellow ended after Year 2 which slowed tribal engagement
| 3 | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | AZ Science and Content, Technology and Informatics, Program Marketing and Outreach, and Program Services teams will meet to prepare for annual portal review | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Complete | AZ EPHT team meets weekly to review website updates
| 4 | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | AZ PMO Team led by health educator will ask technology and informatics team to use Google Analytics to capture web statistics to submit to CDC and help inform program evaluation. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Complete | Analytics tools used to drive new work projects- such as Air Quality and Water Quality Quick Reports infographics in new work plan. ADHS successfully completed webstats. | Webstats form is challenging for example differentiation between data query and content page is difficult to distinguish | Improve instructions on completing form
| 5 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | The Epidemiologist will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-ncdm data in the data explorer. For example, age-adjusted rates, report on trends in numbers, crude rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress | Routine descriptive analysis and reports are conducted for heat- and cold-related illnesses and deaths. Information is shared with internal and external partners.
| 6 | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Technology and Informatics Team will work with IT leadership to ensure data metrics help align with needs for state health improvement plan and county health improvement plan metrics that may use tracking data to help monitor effectiveness. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | In Progress | EPHT air quality data used in State Health Improvement Plan. We also expeditiously updated years of data in our Data Explorer for the Plan to use. | Short timelines to complete data request for State Health Improvement Plan
| 7 | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | AZ PMO will post updates and announcements about grantee tracking activites to Tracking listserv and on social media about the impact of program activities on public health in AZ. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete
Supporting Public Health Emergency Response | 1 | Technology and Informatics 1 (TI1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Support the Health Emergency Operations Center with EPHT expertise; such as environmental epidemiology, GIS mapping, and health education for public health emergencies such as COVID-19, wildfires, and heat. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | In Progress
| 2 | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Sharing key messaging about emergent environmental health issues of public health concern through EPHT listserv and social media messages. For example, share information on heat related mortality before the beginning of heat season or address community members or stakeholder concerns regarding chemicals levels in their drinking water (PFAS, lead, etc.) or hazardous waste sites. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | In Progress
| 3 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Utilize NCDM and non-NCDM data to assess the initial impact that COVID-19 had on public health and the environment by assessing air quality measures and transportation utilization. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | In Progress
| 4 | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | TI resources will be deployed to ensure effective response to the COVID-19 pandemic, opioid crisis, and revamped hospital compare application. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | In Progress
| 5 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | COVID-19 data will be routinely processed, geocoded, and analysed. Data will be dissemnated to stakeholders and the public. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | In Progress

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year