## Instructions
  Instructions
  Purpose of the Template
  Please use this workbook to document your Budget Year 4 Work Plan and Project Narrative as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section II of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)."
  This workbook includes tabs containing the finalized EH17-1702 Logic Model (blue tab), EH1702 Strategies & Activities (yellow tab) for reference, Project Narrative (purple tab) to provide greater detail regarding your planned projects, and the standardized Work Plan template (green tab). The only tabs which you should fill out are the Project Narrative tab and the Work Plan tab.
Filling out the Project Narrative tab:
  Required Reporting: Use the Project Narrative tab to provide details on how each project outlined in your work plan correspond to the specific strategies, activities, and tasks listed. In the Project Summary section, please provide an overview of the project; be sure to adhere to the 200 word limit for this section. There are no limits on the number of projects proposed. Please keep in mind that some of these projects may be an extension of the project proposed and approved in Budget Year 1 or 2 (i.e. initial EH17-1702 application). The planned projects must support the intent of the original EH17-1702 Notice of Funding Opportunity (NOFO).
  Optional Reporting: Use the right-hand side of each project area (Activity Description) to provide additional details which may not be captured in the work plan or in the project summary section. There is no word limit for this section. You may note comments pertaining to budgetary issues that might hamper the success or completion of the project as originally proposed and approved in Budget Year 1.
Filling out the Work Plan tab:
1. Project Title Create a short title for your project, no more than ten words. Examples include “Asthma Prevention”, “Improving Outdoor Air Quality,” "Improving Portal Infrastructure," "Expanding University Partnerships," etc. You may repeat the same project title in subsequent rows depending on the number of supporting strategies and activities for that project, or combine rows in that column to include the same title. You will provide a detailed description of each project on the Project Narrative tab.
2. Strategy Select a strategy from the drop-down list. Each project should fall into one primary strategy. While you can select supporting strategies and activities related to that primary strategy (ex. A Communications strategy/activity supporting the primary Science strategy/activity for that project), the first strategy you select will be the main focus of your project.
3. Activity Select an activity from the drop-down list. The activity should relate to the strategy you previously selected for that project. Each project should list at least two activities to be implemented in the budget year.
4. Activity Description In five sentences or less, describe the activity you are implementing in Column E.
5. Output Select a prospective output from the drop-down list. You may select one output per activity, or one overall output for the project. If you select multiple outputs for the project, you may find not all activities will correspond with an output.
6. Short-Term Outcome Select a prospective short-term outcome from the dropdown list. You may select one outcome per activity, or one outcome overall for the project.
7. Timeline Select when the specific activity will be accomplished from the drop-down list. Options include Quarter 1 (Q1) through Quarter 4 (Q4), meaning the activity will be accompished at the end of the budget year, or a specific time period (ex. Q1, Q2) .
Technical Support
If you need technical support when using this template, email your project officer.
            EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
      EH17-1702 Annual Performance Report (APR) - Section II only
      Budget Period: August 1, 2020 - July 31, 2021 (Budget Year 4)
      Reporting Period: August 1, 2020 - July 31, 2021
      <Enter Recipient Name>

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
[Recipient] Project Narrative Budget Year 4
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan" (green tab). Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
Air Quality
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program will conduct public health surveillance to better understand the health effects of air quality in Colorado. We will develop data visualizations based on NCDMs and provide supporting materials (interpretation, storytelling & communication) to ensure that public health information related to air quality NCDMs is easily understood by the customer. We will explore methods for improving both the quality and the timeliness of our measures of environmental exposure related to air quality. These activities also support our department’s strategic priorities ("Wildly Important Goals") to reduce emissions and improve air quality in Colorado. |  | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 2
|  | 4 | 1 | 1 | 1 | 7
PFAS
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking will take on a leadership role on PFAS at CDPHE and at the national level. We will display and interpret PFAS sample result data from a water sampling project and will conduct ecological surveillance of PFAS exposure and known health effects. We will apply our experience, knowledge, and connections to facilitate a multilaterial content work group or community of practice at the national level. These activities also support CDPHE's strategic priorities ("Wildly Important Goals") to aggressively address the growing issue of PFAS exposure in Colorado.
Real time and predictive data
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking program plans to work with local and national partners on several activities related to real-time data, predictive analytics and data workflow modernization. Our ultimate goal for this project is to modernize our data pipeline to allow more centralized access to our key health and environmental data sources, implement version control of software code and data pipeline endpoints, gain access to more timely health and environmental indicators, and to re-position our environmental public health surveillance workflow to focus more on prospective surveillance and rapid response to emerging environmental public health concerns. Through completion of this project we will gain greater access to real-time data feeds to help us monitor associations between environmental exposures and health outcomes in near-real time. We will also implement procedures to overcome inefficiencies in our current data workflow.
Environmental Health Response
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking program plans to improve its role in Environmental Health Response by using environmental public health surveillance to inform processes that create a translational science platform for use in communicating chronic and emerging environmental public health concerns. The Environmental Health Response project tasks align with Tracking goals and with new organization of Colorado Tracking. Colorado Tracking resides in the newly formed Disease Control and Public Health Response division. The new division is the result of combining the former Disease Control and Environmental Epidemiology division, Office of Emergency Preparedness and Response and the Laboratory Services Division. Leveraging Tracking resources under the Environmental Health Response project is a natural fit and positions Colorado Tracking to fulfill the goals of both National Tracking and the Colorado Department of Public Health and Environment. Tracking program will continuously improve its ability to respond to environmental health concerns by using quality assured surveillance data and well vetted communication materials under this project.
Strategic Planning
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program plans to work with state partners to think strategically about the future of the program and how we can better leverage our strengths and resources to address statewide priorities related to environmental public health. At the center of this project is an effort to place more emphasis on the Tracking program’s role as the foundational program for environmental public health surveillance. Activities in this project will help us leverage our broad public health authority to conduct public health surveillance on environmentally associated conditions and gain access to the full spectrum of tracking-related health outcomes and environmental exposures across our department to conduct surveillance activities. The ultimate goal is to adopt a more proactive and prospective footing for our environmental public health surveillance work, and facilitate rapid response to emerging environmental health concerns. We will also align this work with statewide environmental public health priorities, and strategize how we can create more customized and narrative communications products.
Promoting National and Local Tracking Networks and Engaging Partners
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program will continue to promote and engage state and national Tracking partners through a variety of activities. Overall, this will happen by developing and implementing an annual communications and dissemination plan focused on leveraging plain language for messages which are accessible to all. Firstly, Tracking will participate with PMO West state partners and the national program during Tracking Awareness Week and at select other times during the year. Tracking will engage its Technical Advisory Group each quarter via MailChimp newsletter and twice yearly at in-person or video conference meetings. Each month, Tracking will post to Colorado Department of Public Health and Environment social media pages about topics as outlined in the annual communications plan. Tracking will present program-related projects and methods at nearby universities and at state and national association conferences. Finally, Tracking will use webinars and partners’ communication networks to ensure Tracking data, messaging, and products reach appropriate audiences.
Building National and Local Environmental Public Health Tracking Networks
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program plans to work with local and national partners to improve data infrastructure (e.g., evaluate, strengthen and develop NCDMs), provide training of Tracking staff for expanded expertise of environmental and health hazards and data, continue to participate in National Tracking workgroups, and increase public awareness of the Tracking portal through engaging community stakeholders and partners in event-planning and outreach (i.e., which may lead to public health actions).

## Work Plan
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Colorado Y4 Work Plan
EH17-1702 Budget Period: |  |  |  | August 1, 2020 - July 31, 2021
Date Submitted to CDC:
REFERENCE NOTES | No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activty description. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project.
| Project Title | Activity Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline | Activity Lead
| Air quality | Surveillance: health effects of air quality | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct environmental public health surveillance on health outcomes in relation to air pollution exposures (e.g., traffic, oil & gas drilling activity, etc.). | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Paul
|  |  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities |  | SC-Generated & disseminated env. Public health evidence
|  |  | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational Science: Private air quality sensors | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products surrounding private air quality sensors. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Paul
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues |  | Mallory
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational Science: Health effects of air quality | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products from surveillance projects on health effects of air quality | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Paul
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues |  | Mallory
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal |  | Eric
|  | Data Creation/Acquisition: Private air quality sensors | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Research ways to leverage the growing network of citizen science/private air quality monitors in CO. Pilot the creation of portal-ready and/or analysis-ready data product from private air quality monitors in CO | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q3 | Paul
|  | Data Creation/Acquisition: Data from new State GHG reporting requirements | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Create infrastructure to collect, store, and analyze new State-mandated greenhouse gas emissions data. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Andy
SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness
|  | Translational Science: GHG reporting dashboard | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products using new state-mandated greenhouse gas emissions data. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Eric
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues |  | Mallory
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational science: Air toxics, HAPs, & AQI | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products using EPA data on air toxics, hazardous air pollutants, and air quality index. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q3 | Eric
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues |  | Paul
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
| PFAS | Surveillance: Health effects of PFAS exposure | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Explore environmental public health surveillance on health outcomes in relation to PFAS exposure | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4 | Margaret
|  |  |  | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities |  | SC-Generated & disseminated env. Public health evidence
|  | Translational science: health effects of PFAS exposure | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products from surveillance projects on health effects of PFAS exposure | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational science: PFAS-related CWG | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Develop/lead PFAS-related content work group. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | Data creation/acquisition: PFAS in private wells |  | SC1.D Disseminate additional indicators & measures to address grantee priorities | Collect, store, and analyze data on PFAS in private well water. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4
| Real-Time Data, Predictive Analytics, and Workflow Modernization | Data creation/acquisition: Predicted NCDMS | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Generate annual predicted cases of Hosp/ED visit NCDMs for Counties and Census Tracts | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2 | Kevin
|  |  | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards |  | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence |  | Margaret
|  |  | Communications 1 (C1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Data creation/acquisition: Syndromic surveillance NDCMS analogs | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Obtain access to NCDM-like (asthma, ami, copd, co poisoning, heat/cold-related illness) near-real time health outcomes from Tri-County Health Deapartment's statewide syndromic surveillance program to incorporate on tracking portal. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2 | Kevin
|  |  | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards |  | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence |  | Margaret
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal |  | Paul
|  | Data Creation/Acquisition: Oil & gas health concerns syndromic surveillance case definition | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Work with Tri-County Health Department's syndromic surveillance program to develop a case definition for syndromic surveillance of oil and gas health concerns | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Kevin
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal |  | Paul
Margaret
|  | Surveillance: prospective NCDM surveillance | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Adapt enhanced passive surveillance system developed for lead and asthma to other NCDMs | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2 | Kevin
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal |  | Paul
|  | Surveillance: Syndromic surveillance data | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Explore, develop, pilot environmental public health surviellance with EPHT-related syndromic surveillance data sets. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences |  | Kevin
|  | Translational science: Syndromic surveillance data | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create real-time/near-real-time data visualization, interpretation, storytelling, & communications products for EPHT-related syndromic surveillance data sets. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4 | Kevin
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues |  | Margaret
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal |  | Paul
|  | Workflow modernization: Integrated health and environment data warehouse | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Explore the creation of an integrated health and environment data warehouse that streamlines data pipeline for the purpose of addressing emerging environmetnal public health concerns and public health response. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Andy
|  |  |  | SC1.F Address gaps & limitations in data |  | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
TI1.B Develop tools and processes to improve data qualities
|  |  |  | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making |  |  |  |  | Kevin
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
|  | Workflow modernization: Git, version control | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Explore and implement git for version control of software code and data products | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Kevin
Margaret
Paul
| Environmental Health Response | Surveillance: Motor vehicle crashes and the built environment | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Conduct environmental public health surveillance on motor vehical crash data in relation to pilot built enviornment NCDMs. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Devon
|  |  |  | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work |  |  |  |  | Margaret
|  | Translational Science: Motor vehicle crashes and the built environment | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Priorites from the state health improvement plan. Create visualization, interpretation, storytelling, & communications products from surveillance projects on transportation related injuries and built environment factors. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Devon
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues |  | Margaret
|  | Translational Science: NCDMs | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Add interpretation and storytelling to NCDM pages. | SC-Generated & disseminated env. Public health evidence | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Everyone
|  | Surveillance: health disparities in lead poisoning | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct environmental public health surveillance to project trends for health disparities and lead exposure. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Hailey
|  | Translational Science: health disparities in lead poisoning | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products from surveillance projects on trends in health disparities of lead poisoning | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Surveillance: lead exposure from Superfund, brownfields, and other outdoor sources | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct environmental public health surveillance on lead exposure from Superfund, brownfields, and other outdoor sources of lead in Colorado. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4
|  | Translational Science: lead exposure from Superfund, brownfields, and other outdoor sources | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products from surveillance projects on lead exposure from Superfund, brownfields, and other outdoor sources of lead in Colorado. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational Science: WIN grant, lead in drinking water | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products on lead in drinking water sampling performed via WIN grant and legislative grant (in conjunction with WQD). Continue to develop and publish lead in drinking water as a state added measure. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q3
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational Science: Climate Change Indicators | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products to translate climate change indicators for the general public. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2 | Mallory
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues |  | Margaret
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Suveillance: Health effects and disparities of radon exposure | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct environmental public health surveillance to investigate health effects of radon (e.g., radon and lung cancer). Evaluate trends and disparities using BRFSS radon question. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Eric
|  | Translational Science: Health effects and disparities of radon exposure | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Create visualization, interpretation, storytelling, & communications products to communicate results from radon surveillance activities. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q2-Q3
|  | Translational Science: Groundwater vulnerability, water quality | Science and Content 2 (SC2) | SC1.F Address gaps & limitations in data | Improve and maintain the Groundwater Vulnerability Tool by collaborating with state and local agencies, shared resources. Publish to support Private Wells measure. Add well water results tool (NH / EPA) to Private Wells measure. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q3
|  | Translational Science: Environmental Public Health Response to emerging issues | Science and Content 2 (SC2) | SC1.D Disseminate additional indicators & measures to address grantee priorities | CO Tracking will respond to emerging enironmental and public health issues such as COVID-19. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | Everyone
| Strategic planning | Strategic Planning: Obtaining IRB designation for public health surveillance work | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Work with department, division, and branch leadership to officially designate CO Tracking's environmental public health surveillance work as "public health surveillance" by CDPHE's IRB | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q3 | Kevin
|  |  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction |  |  |  |  | Senior Epi
|  | Strategic Planning: Improving environmental exposure data access | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Explore the use of public health authority to grant access to relevant environmental exposure and biomonitoring data from lab services database for environmental public health surveillance. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q2-Q4 | Kevin
Senior Epi
|  | Strategic Planning: Improving sub-county health outcome data access | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Explore the use of public health authority to grant access to relevant sub-county health outcome data from CDPHE's Center for Health and Environmental Data for environmental public health surveillance. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q2-Q3 | Kevin
Devon
Kirk
|  | Strategic Planning: Future of Tracking | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Develop internal strategic plan for remaining years of current grant and contemplate the future goals of the Colorado Tracking program. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q2-Q3 | Everyone
|  |  |  | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction |  | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
|  | Strategic Planning: Future of Tracking | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Explore evaluation processes to capture users, products, etc. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Megan
| Promoting National and Local Tracking Networks and Engaging Partners | Communications | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Develop and implement communications plan on an annual basis. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2 | Mallory
|  | Communications | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Develop and imlement partnership plan | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q2
|  | Communications | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Maintain Technical Advisory Group (TAG) to inform decisions about the Colorado Tracking program work plan, goals, and objectives. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | Communications | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Colorado Tracking will participate in Tracking Awareness week annually. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4
|  | Techincal Advisory Group (TAG) | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Communicate with the Techincal Advisory Group quarterly on program announcements and updates. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | Communications | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Post monthly to CDPHE social media pages about Colorado Tracking topic areas as outlined in the Communications Plan. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Outreach | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | CO Tracking Staff will present on Tracking program-related methods and findings at conferences such as CSTE, Public Health in the Rockies, or Colorado Environmental Health Network. Webinars will be used to share information with partners and stakeholders. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Everyone
|  | Communications | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Review content to ensure messaging is appropriate and written in plain language. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Mallory
|  | Communications | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Continuing work with Office of Communications and OPPI to disseminate messages and products to appropriate audiences. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Communications | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Develop dissemination plan for messaging to ensure appropriate audiences are being reached. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Communications | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity | Work with PMO West to collaborate on a quarterly communications activity and participate in Tracking Week. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Outreach | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Build onexisting public health strengths through the development of academic partnerships to utilize the knowledge, expertise, and perspective of experts affiliated with local institutions of higher education. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  |  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction |  | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
|  |  | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles
|  | Communication | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Use the Targeted Lead Outreach Tool to inform the need for a childhood lead poisioning prevention media campaign targeting new mothers and physicians. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2 | Mallory
|  |  | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media |  |  |  |  | Megan
| Building National and Local Environmental Public Health Tracking Networks | Building networks | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Work with CDC and other data partners to strengthen existing NCDMs. This work will occur in Content Work Groups, in collaboration with our data stewards, and in the CDC fall workshops. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Everyone
|  | Building networks | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Participate in National Tracking workgroups: i) SND ii) PMO iii) CWG . | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Everyone
|  | Building networks | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Maintain sufficient local Tracking Program staff and expertise by evaluating, identifying and supporting training opportunities for Tracking staff and partners. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Megan
|  | Building networks | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs
|  | Building networks | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles
|  | Evaluation | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | CO Tracking staff will use outreach and required management spreadsheets to document activities likely to lead to public health actions. We will use CDC template to share both completed public health actions and activities that may lead to public health actions. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Megan
|  | Evaluation | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Report annual evaluation results to CDC | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q2-Q3 | Megan
|  | Evaluation | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | Maintain portal aligned with CDC requirements and schedule annual portal review with CDC partners to ensure periodic evaluation | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Mallory
|  |  | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal |  | Megan
|  | Building networks | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | Work with Tracking web team to collect and submit analytics for Colorado Tracking portal | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q2 | Megan
|  | Building networks | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Maintain previous SAS code and XML software to gather and format our data into CDC-required format. Participate in required Data Calls with CDC and state partners | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Kevin
|  | Building networks | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Work with Department Web Team to continue to display and narrarate data on state portal | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Mallory
|  | Building networks | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | CO Tracking will extend the previous mini-grant deadlines to the 5 LPHAs who were awarded in Y3. Due to the COVID-19 response, these LPHAs will not be able to finish projects by the end of Y3 and will have by the end of Y4 to complete all deliverables. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q3 | Megan

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year