## Instructions
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Annual Performance Report (APR) - Section I
Budget Period: August 1, 2020 - July 31, 2021(Budget Year 4)
Reporting Period: February 1, 2020 - January 31, 2021.
Instructions Please use this workbook to document progress for your Budget Year 4 Work Plan as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section I of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)." The Work Plan tab includes the Year 4 plan you submitted in your 2020 APR. Columns I-L, with the orange Continuation Report (Section I) banner, are where you should enter information about your progress. For each activity, select the Current Status from the dropdown menu (not started, complete, in progress, or behind schedule) and provide relevant information under Successes, Challenges, and CDC Support Needed.
Technical Support If you need technical support when using this template, email your project officer.

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Y3 Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
[Recipient] Project Narrative Budget Year 4
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan." Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
Performance Management Tool and SMART Goals Template
SCIENCE AND CONTENT | Prepare for and track climate change-related impacts to environmental health
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking Program has established relationships with internal (i.e., within the Colorado Department of Public Health and Environment) and external stakeholders surrounding Climate Change. As the effects of climate change are unfolding and manifesting differently in the Rocky Mountain West than in other regions of the United States, Tracking aims to monitor trends relevant to Colorado's communities (e.g., wildfire incidence and nearby air quality). To support decision-making by policymakers, communities, and other leaders, surveillance data of air, water, and land will be shared on our public portal. Moreover, Tracking will generate communications materials related to this data, and engage partners in collaborative climate change readiness efforts. Currently, Tracking Program has several work streams which align with this priority area. First, team members participate as members of the National Tracking Climate Change Content Work Group. Second, we lead a subgroup of our Technical Advisory Group which has met during the past year to discuss suggested state-level climate change indicators, ongoing local preparedness efforts to align with, and potentially including broader audiences in these discussions at symposiums and other meetings. Finally, our new state leadership is prioritizing climate change initiatives (e.g., research, preparedness efforts), and Tracking continues to expand data to inform these initiatives. |  | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 2
|  |  | 5 | 1 | 1 | 1 | 8
Expand community design datasets, training, and communications products
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program has expanded its partnership building surrounding Community Design efforts, and has projects planned to continue building these relationships. Perhaps the most notable effort is establishing an internship with two schools at the University of Colorado: the Colorado School of Public Health and the College of Architecture and Planning. Graduate student interns are using Tracking data to help communities examine and plan for environmental and health issues in their regions. Tracking Program has also worked with toxicologists and risk assessment professionals to create a "Choose Safe Places" training which is an interactive course training childcare licensing and education professionals about preventing children’s' exposures to environmental health hazards. Finally, Tracking Program plans to expand partnerships with transportation agencies and nonprofits. The movement of a growing population introduces and increases environmental exposures, particularly to odor, particulates, noise, and vibrations, as well as associated health outcomes to a growing number of citizens; Tracking Program plans to survey these spatiotemporal trends.
TECHNOLOGY AND INFORMATICS
Improve spatial resolution and metadata for radon
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Radon is an odorless, colorless, naturally occurring element that is prevalent in all parts of Colorado. Colorado Department of Public Health and Environment has a robust radon program. Tracking Program has a long-standing partnership with the radon team, and plans to strategize how both may benefit from improved radon data. First, we are planning to work with internal and external stakeholders to record whether results of household-level radon are obtained before or after mitigation construction to be able to more accurately display radon data on the portal and to inform radon policies, programs, and communications. Secondly, radon data is a candidate for sub-county level data projects since we have address information and census-tract information for radon tests statewide. Finally, Tracking Program is working with the Center for Health and Environmental Data to add radon-related question(s) to the Behavioral Risk Factor Surveillance System questionnaire. These projects are all contributing to an overall effort to improve the spatial resolution and metadata for radon and increase targeted communications plans based on public perceptions of radon.
COMMUNICATIONS
Expand marijuana surveillance and associations with health outcomes
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Colorado is among a subset of Tracking grantee states with legal recreational marijuana, and it was one of the first to legalize, securing its status as a leader and bellwether state for tracking public health implications of regulating this substance. Other states, with and without Tracking portals, look to Colorado for guidance and data supporting policy measures surrounding the use of marijuana. Therefore, Tracking Program seeks to bolster the available environmental and health information about marijuana. First, we are working with colleagues within the Colorado Department of Public Health and Environment to create maps of retail marijuana stores called dispensaries. We are exploring epidemiological analyses with internal colleagues which geographically display marijuana and alcohol retail locations with the locations of various types of injuries (e.g., motor vehicle, cyclist, and pedestrian collisions) using new data sources. Tracking Program also will share marijuana-related information with other Tracking states that have legalized recreational marijuana to discuss surveillance and epidemiological evaluation of any potential related health outcomes.
Improve asthma data surveillance
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program is expanding its data analysis personnel and is therefore expanding its repertoire of data-related projects. First, Tracking continues to work with colleagues within Colorado Department of Public Health and Environment on asthma mapping. Second, Tracking plans to use a suite of data sources (e.g., all payer claims data, emergency medical services data, and hospitalization data) and compare their measurement of asthma-related contact with different health care providers across these sources. These datasets will be examined for sensitivity to environmental events (e.g., weather patterns such as low air quality days or dust storms) or locations (e.g., near sources in the built environment which may trigger asthma exacerbations) and prevalence/incidence of asthma exacerbations. Third, Tracking plans to create an asthma risk map similar to the lead risk assessment tool previously created. Finally, Tracking will create communications tools for educators about common potential asthma triggers in schools, daycare centers, and other childcare facilities.
PROGRAM SERVICES | Expand lead surveillance, outreach, and communications
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program has a long-standing relationship with the Lead Program, co-located in the Environmental Epidemiology branch and collaborating on multiple data and communications projects in the past. Historically, lead surveillance has been one of the major environmental justice projects of Tracking program, which created a lead screening tool to add to its portal recently based on age of housing and rates of poverty and lead testing. Going forward, Tracking Program plans to maintain and update this screening tool and work with partners to disseminate the tool and use the tool to inform public health and community design plans and priorities. Finally, Tracking Program plans to develop enhanced and prospective lead surveillance techniques to proactively plan for lead programming.
Promoting national and local tracking networks and engaging partners
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program will continue to promote and engage state and national Tracking partners through a variety of activities. Overall, this will happen by developing and implementing an annual communications and dissemination plan focused on leveraging plain language for messages which are accessible to all. Firstly, Tracking will participate with PMO West state partners and the national program during Tracking Awareness Week and at select other times during the year. Tracking will engage its Technical Advisory Group each quarter via MailChimp newsletter and twice yearly at in-person or video conference meetings. Each month, Tracking will post to Colorado Department of Public Health and Environment social media pages about topics as outlined in the annual communications plan. Tracking will present program-related projects and methods at nearby universities and at state and national association conferences. Finally, Tracking will use webinars and partners’ communication networks to ensure Tracking data, messaging, and products reach appropriate audiences.
Building national and local environmental public health tracking networks
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program plans to work with local and national partners to improve data infrastructure (e.g., evaluate, strengthen and develop NCDMs), provide training of Tracking staff for expanded expertise of environmental and health hazards and data, continue to participate in National Tracking workgroups, and increase public awareness of the Tracking portal through engaging community stakeholders and partners in event-planning and outreach (i.e., which may lead to public health actions).
Building Environmental Public Health Capacity at the Local Level
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Colorado Tracking is creating an environmental public health mini-grants project . We will release a Request for Applications (RFA) to local and tribal health departments; we ask applicants to propose a small-scale environmental project in their jurisdiction, that will either use Tracking data to inform the project or gather new data that theTracking program can add to the portal. Minor adjustments to the RFA are planned to clarify instructions and expectations. We are also planning to release a pre-announcement about 6-7 weeks prior to releasing the RFA, so interested applicants have additional time to explore possible projects and build the necessary partnerships prior to applying. This project is expected to lead to improved partnerships with local health departments, increased awareness of the Tracking Program, and increased quantity and quality of public health actions. | Based upon our budget, we will plan to fund four local or tribal health departments. If we have carryover funds (due to salary savings from the PI, PM, and Coordinator vacancy), we will adjust this activity with an aim to fund six local or tribal health departments. In addition, the scope of the project will be reduced if funding amounts decrease.

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year

## Y4 Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
[Recipient] Project Narrative Budget Year 4
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan" (green tab). Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
SCIENCE AND CONTENT | Air Quality
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking Program will conduct public health surveillance to better understand the health effects of air quality in Colorado. We will develop data visualizations based on NCDMs and provide supporting materials (interpretation, storytelling & communication) to ensure that public health information related to air quality NCDMs is easily understood by the customer. We will explore methods for improving both the quality and the timeliness of our measures of environmental exposure related to air quality. These activities also support our department’s strategic priorities ("Wildly Important Goals") to reduce emissions and improve air quality in Colorado. |  | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 2
|  |  | 4 | 1 | 1 | 1 | 7
PFAS
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking will take on a leadership role on PFAS at CDPHE and at the national level. We will display and interpret PFAS sample result data from a water sampling project and will conduct ecological surveillance of PFAS exposure and known health effects. We will apply our experience, knowledge, and connections to facilitate a multilaterial content work group or community of practice at the national level. These activities also support CDPHE's strategic priorities ("Wildly Important Goals") to aggressively address the growing issue of PFAS exposure in Colorado.
TECHNOLOGY AND INFORMATICS
Real time and predictive data
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking program plans to work with local and national partners on several activities related to real-time data, predictive analytics and data workflow modernization. Our ultimate goal for this project is to modernize our data pipeline to allow more centralized access to our key health and environmental data sources, implement version control of software code and data pipeline endpoints, gain access to more timely health and environmental indicators, and to re-position our environmental public health surveillance workflow to focus more on prospective surveillance and rapid response to emerging environmental public health concerns. Through completion of this project we will gain greater access to real-time data feeds to help us monitor associations between environmental exposures and health outcomes in near-real time. We will also implement procedures to overcome inefficiencies in our current data workflow.
COMMUNICATIONS
Environmental Health Response
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking program plans to improve its role in Environmental Health Response by using environmental public health surveillance to inform processes that create a translational science platform for use in communicating chronic and emerging environmental public health concerns. The Environmental Health Response project tasks align with Tracking goals and with new organization of Colorado Tracking. Colorado Tracking resides in the newly formed Disease Control and Public Health Response division. The new division is the result of combining the former Disease Control and Environmental Epidemiology division, Office of Emergency Preparedness and Response and the Laboratory Services Division. Leveraging Tracking resources under the Environmental Health Response project is a natural fit and positions Colorado Tracking to fulfill the goals of both National Tracking and the Colorado Department of Public Health and Environment. Tracking program will continuously improve its ability to respond to environmental health concerns by using quality assured surveillance data and well vetted communication materials under this project.
Strategic Planning
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program plans to work with state partners to think strategically about the future of the program and how we can better leverage our strengths and resources to address statewide priorities related to environmental public health. At the center of this project is an effort to place more emphasis on the Tracking program’s role as the foundational program for environmental public health surveillance. Activities in this project will help us leverage our broad public health authority to conduct public health surveillance on environmentally associated conditions and gain access to the full spectrum of tracking-related health outcomes and environmental exposures across our department to conduct surveillance activities. The ultimate goal is to adopt a more proactive and prospective footing for our environmental public health surveillance work, and facilitate rapid response to emerging environmental health concerns. We will also align this work with statewide environmental public health priorities, and strategize how we can create more customized and narrative communications products.
PROGRAM SERVICES
Promoting National and Local Tracking Networks and Engaging Partners
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program will continue to promote and engage state and national Tracking partners through a variety of activities. Overall, this will happen by developing and implementing an annual communications and dissemination plan focused on leveraging plain language for messages which are accessible to all. Firstly, Tracking will participate with PMO West state partners and the national program during Tracking Awareness Week and at select other times during the year. Tracking will engage its Technical Advisory Group each quarter via MailChimp newsletter and twice yearly at in-person or video conference meetings. Each month, Tracking will post to Colorado Department of Public Health and Environment social media pages about topics as outlined in the annual communications plan. Tracking will present program-related projects and methods at nearby universities and at state and national association conferences. Finally, Tracking will use webinars and partners’ communication networks to ensure Tracking data, messaging, and products reach appropriate audiences.
Building National and Local Environmental Public Health Tracking Networks
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Tracking Program plans to work with local and national partners to improve data infrastructure (e.g., evaluate, strengthen and develop NCDMs), provide training of Tracking staff for expanded expertise of environmental and health hazards and data, continue to participate in National Tracking workgroups, and increase public awareness of the Tracking portal through engaging community stakeholders and partners in event-planning and outreach (i.e., which may lead to public health actions).

## Y3 & Y4 Work Plans
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Colorado Y4 Work Plan
EH17-1702 Budget Period: |  |  |  | August 1, 2020 - July 31, 2021
Date Submitted to CDC:
Year 4
REFERENCE NOTES | No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activty description. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project. | Continuation Report (Section I)
| Project Title | Activity Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline | Status | Successes | Challenges | CDC Program Support Needed
| Air quality | Surveillance: health effects of air quality | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct environmental public health surveillance on health outcomes in relation to air pollution exposures (e.g., traffic, oil & gas drilling activity, etc.). | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | In Progress |  |  | Investigate a potential dataset for "extreme cold" that utilizes the NLDAS remote sensing data
|  |  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities |  | SC-Generated & disseminated env. Public health evidence
|  |  | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational Science: Private air quality sensors | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products surrounding private air quality sensors. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Not Started
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational Science: Health effects of air quality | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products from surveillance projects on health effects of air quality | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Complete | The Commerce City-North Denver translational science project encompasses a data narrative and a data dashboard, each available in English and Spanish. Through this project, we combine multiple data sources to tell a a story regarding the environmental health status of a dispropotionately impacted neighborhood in Colorado. Through the iterative feedback process during product development, the Commerce-City North Denver dashboards garnered support from departmental leaders and engagement with various stakeholder groups and community members. The community will use this information to guide a Supplemental Environmental Project funded by a settlement with a local refinery. | This project took signifcantly more time than expected due to the various levels of review, feedback, translation, and implementation.
|  | Data Creation/Acquisition: Private air quality sensors | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Research ways to leverage the growing network of citizen science/private air quality monitors in CO. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q3 | In Progress
|  | Data Creation/Acquisition: Data from new State GHG reporting requirements | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Create infrastructure to collect, store, and analyze new State-mandated greenhouse gas emissions data. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Not Started
SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness
|  | Translational Science: GHG reporting dashboard | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products using new state-mandated greenhouse gas emissions data. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Not Started
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational science: Air toxics, HAPs, & AQI | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products using EPA data on air toxics, hazardous air pollutants, and air quality index. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q3 | In Progress
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
| PFAS | Surveillance: Health effects of PFAS exposure | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Explore environmental public health surveillance on health outcomes in relation to PFAS exposure | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4 | In Progress | Identified potential data sources and analysis activities that may become available in the next year or so | The Tracking program does not have sufficient exposure or outcome data sources to conduct satisfactory surveillance activities at this time.
|  |  |  | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities |  | SC-Generated & disseminated env. Public health evidence
|  | Translational science: health effects of PFAS exposure | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products from surveillance projects on health effects of PFAS exposure | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4 | In Progress
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational science: PFAS-related CWG | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Develop/lead PFAS-related content work group. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | Not Started |  | A PFAS Content Work Group was not developed this grant cycle.
|  | Data creation/acquisition: PFAS in private wells |  | SC1.D Disseminate additional indicators & measures to address grantee priorities | Collect, store, and analyze data on PFAS in private well water. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4 | In Progress | The department has started a private well pilot project with a local public health department to sample for PFAS. The Tracking program is piloting a way to visualize and distribute these results using private well samples from previous sampling initiatives. | This project is not likely to produce data before the end of the grant cycle
| Real-Time Data, Predictive Analytics, and Workflow Modernization | Data creation/acquisition: Predicted NCDMS | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Generate annual predicted cases of Hosp/ED visit NCDMs for Counties and Census Tracts | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | In Progress | Tracking devleoped R code to produce predicted baselines for all 9 hospitalization and ED visit NCDMs. Work on this project also prompted a restructuring of our existing hospitalization and ED visit data pipleline. Previously, we accessed these data via large SAS flat files provided to us by CDPHE's Center for Health and Environmental Data. Querying from these files was inefficient and required significant processing tim. We were able to use this project as a chance to restrucutre our storage of this data onto a centralized google-based cloud platform that allows for more efficient storage and retrieval of our hosp/ED visit data. This process improvement will allow for greater efficiency in accessing and processing hosp/ED visit data for existing and ad-hoc data analysis projects. | Completion of this project was delayed by the COVID-19 response. While the design of the initial analysis is complete, we have not yet incorporated the results into our portal content related to hosp/ED visit NCDMs.
|  |  | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards |  | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence
|  |  | Communications 1 (C1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Data creation/acquisition: Syndromic surveillance NDCMS analogs | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Obtain access to NCDM-like (asthma, ami, copd, co poisoning, heat/cold-related illness) near-real time health outcomes from Tri-County Health Deapartment's statewide syndromic surveillance program to incorporate on tracking portal. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q3 | Not Started |  | Work on this project has been significantly delayed due to the COVID-19 response. The key partner in this project, Tri Couny Health Department, runs the statewide syndromic surveillance program. However, TCHD staff have been occupied by the ongoing pandemic response. We hope to resume this project toward the end of year 4 and plan to roll over completion to year 5.
|  |  | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards |  | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  |  | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Work with Tri-County Health Department's syndromic surveillance program to develop a case definition for syndromic surveillance of oil and gas health concerns | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4 | Not Started |  | Work on this project has been significantly delayed due to the COVID-19 response. The key partner in this project, Tri Couny Health Department, runs the statewide syndromic surveillance program. However, TCHD staff have been occupied by the ongoing pandemic response. We hope to resume this project toward the end of year 4 and plan to roll over completion to year 5.
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Surveillance: prospective NCDM surveillance | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Adapt enhanced passive surveillance system developed for lead and asthma to other NCDMs | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | In Progress | R code has been delevoped to adapt and apply the enhanced passive surveillance system developed for Colorado's CLPP program to a weekly data feed of asthma hospitalizations and emergency department visits from Children's Hospital Colorado. The next step will be to adapt this structure to our annually-updated statewide hospitalization and ED visit data sets. | This project has been slightly delayed due to the COVID-19 response. The predictive models used in this project have also been impacted by changes in the healthcare seeking behavior as a result of the pandemic. | Assistance from CDC and national tracking partners to understand the scope of the COVID-19 pandameic on hosptialization and emergency department visit rates will be needed to properly gauge the impact.
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Surveillance: Syndromic surveillance data | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Explore, develop, pilot environmental public health surviellance with EPHT-related syndromic surveillance data sets. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences |  | In Progress | We have obtained an ongoing weekly data feed of asthma hospitalizations and emergency department visits from Children's Hospital Colorado. We have also received approval to add EPHT-related indicators to a quarterly data feed from the agency that runs Colorado's Medicaid program (Dept. of Health Care Policy & Financing) through an interagency agreement and we are currently working on definitions for EPHT-related outpatient visits and pharmacy claims data. |  | Assistance from CDC and national tracking partners on defining or identifying outpatient visits (e.g., doctor's visits, urgent care) that are related to EPHT (e.g., asthma, copd, heat-related illiness, cold-related injury, etc.) and pharmarcy claims.
|  | Translational science: Syndromic surveillance data | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create real-time/near-real-time data visualization, interpretation, storytelling, & communications products for EPHT-related syndromic surveillance data sets. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4 | Not Started | Tracking has secured a data use agreement and begun receiving a weekly data feed of asthma hospitalizations and emergency department visits for use in syndromic surveillance projects. We are also in the process of indentifying non-emergent EPHT-related outpatient visits and pharmacy claims data from the state agency that runs Colorado's Medicaid program (HCPF). Per an interagency agreement, this data will be provided on a quarterly basis, and is currently planned to include date information that will allow monitoring daily event trends. Tracking is currently planning portal content around these efforts. The goal is to add visualization and comunications surrounding "real-time" surveillance content to Colorado's data portal. | The COVID-19 response has delayed portions of this project, specifcally all our planned projects involving the statewide syndromic surveillance data set (coordinated by Tri-County Health Department). | Assistance from CDC and national tracking partners on defining or identifying outpatient visits (e.g., doctor's visits, urgent care) that are related to EPHT (e.g., asthma, copd, heat-related illiness, cold-related injury, etc.) and pharmarcy claims. In addtion, providing resources for planning protal content around "near real-time" or on-going data sets would also be beneficial.
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Workflow modernization: Integrated health and environment data warehouse | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Explore the creation of an integrated health and environment data warehouse that streamlines data pipeline for the purpose of addressing emerging environmetnal public health concerns and public health response. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | In Progress | The tracking program authored an internal memorandum detailing the pain points in our data pipeline. Tracking also participated in a coordinated statewide strategic planning effort surrounding data modernization, led by the state's Office of Information Technology. Lastly, tracking began piloting short-term data pipeline improvements via Google File Stream that improves data integration and interoperability throughout the other programs housed within the Toxicology & Environmental Epidemiology Office. | This effort was somewhat delayed due to the COVID-19 response, as well as to the re-organization of the office that houses the Colorado tracking program to a different division within CDPHE. | It is a slow, difficult, and bureaucratic process to make improvements to the underlying data infrastructure of our program. Further, the department and the state are reluctant to implement one-off solutions that only benefits a small portion of a single state agency. Given CDC's increased emphasis on data modernizations initiatives, and National Tracking's central role in this process, guidance on best practices for increasing efficiencies in data pipelines would go along way toward acheiving the ultimate goal of timely and accurate data for environmental public health surveillance.
|  |  |  | SC1.F Address gaps & limitations in data |  | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
|  | Workflow modernization: Git, version control | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Explore and implement git for version control of software code and data products | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Complete | The Tracking program has created an organization on GitHub to manage shared projects and has written standard operating procedures to ensure a common work flow for all coding projects. | Due to COVID, normal work flows were interrupted (accessing network drives requires a VPN connection that can often slow down code). As a result, some staff have not yet transitioned to using GitHub for their projects.
| Environmental Health Response | Surveillance: Motor vehicle crashes and the built environment | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Conduct environmental public health surveillance on motor vehical crash data in relation to pilot built enviornment NCDMs. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Behind Schedule |  | The indicators are still under develpment by the Community Design content work group. Activity will run into Y5
SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work
|  | Translational Science: Motor vehicle crashes and the built environment | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Priorites from the state health improvement plan. Create visualization, interpretation, storytelling, & communications products from surveillance projects on transportation related injuries and built environment factors. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Behind Schedule |  | The indicators are still under develpment by the Community Design content work group.
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  | Translational Science: NCDMs | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Add interpretation and storytelling to NCDM pages. | SC-Generated & disseminated env. Public health evidence | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete |  | Due to programmatic and Department priorities, we piolted the climate change and CC-ND pages and not the NCDM pages. The CC-ND pages will be used by community memebers and stakeholders to decide on priority areas in their communities.
|  | Surveillance: health disparities in lead poisoning | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct environmental public health surveillance to project trends for health disparities and lead exposure. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | In Progress | Established on-going relationship with CDPHE Refugee Health Group. Have outlined collaborative goals and have identified areas for expanded partnerships and data sharing. Identified an additional analytical project on built environment, access to care and refugee health outcomes. | Both staff members from the Refugee Health Unit were deployed to COVID. This delayed the project by several months and has delayed progress towards a data sharing agreement (DSA) and lead surveillance joint project. Activity will run into Y5
|  | Translational Science: health disparities in lead poisoning | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products from surveillance projects on trends in health disparities of lead poisoning | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | In Progress | Established on-going relationship with CDPHE Refugee Health Group. Have outlined collaborative goals and have identified areas for expanded partnerships and data sharing. Identified an additional analytical project on built environment, access to care and refugee health outcomes. | Both staff members from the Refugee Health Unit were deployed to COVID. This delayed the project by several months and has delayed progress towards a data sharing agreement (DSA) and lead surveillance joint project. Activity will run into Y5
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Surveillance: lead exposure from Superfund, brownfields, and other outdoor sources | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct environmental public health surveillance on lead exposure from Superfund, brownfields, and other outdoor sources of lead in Colorado. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Not Started | Coordinating with Tom Simmons on Superfund, Brownfields, and other outdoor sources of lead in Colorado.
|  | Translational Science: lead exposure from Superfund, brownfields, and other outdoor sources | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products from surveillance projects on lead exposure from Superfund, brownfields, and other outdoor sources of lead in Colorado. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Not Started
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational Science: WIN grant, lead in drinking water | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products on lead in drinking water sampling performed via WIN grant and legislative grant (in conjunction with WQD). Continue to develop and publish lead in drinking water as a state added measure. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | In Progress | Organized several meetings to discuss WQCD needs and wants for data visualization. Created a pilot visualization in Tableau using existing lead in schools sampling data. Disseminated dashboard to WQCD staff. | COVID delayed WIIN grant activities by several months. WIIN grant manager went on extended leave of absence. WQCD decided to remove data from their website and no longer have the data be publically available. Further delayed due to COVID and the loss of the program manager until summer 2021. Activity will run into Y5
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Translational Science: Climate Change Indicators | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products to translate climate change indicators for the general public. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4 | In Progress | The climate change narrative describes the various climate indicators and why they matter, what Colorado's climate may look like in approx. 50 years using the NEPHT future climate projection datasets, and gives readers concrete actions they can take to mitigate the impacts of climate change. During the development process. we solicited feedback from the department's new Climate Change Unit and received feedback from the Unit's Climate Equity advisory group. | The various levels of review and feedback delayed the project more than expected.
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Suveillance: Health effects and disparities of radon exposure | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct environmental public health surveillance to investigate health effects of radon (e.g., radon and lung cancer). Evaluate trends and disparities using BRFSS radon question. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4 | Behind Schedule |  | Due to programmatic needs, the radon analysis project has shifted to evaluate spatial trends of free radon test kit distribution.
|  | Translational Science: Health effects and disparities of radon exposure | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Create visualization, interpretation, storytelling, & communications products to communicate results from radon surveillance activities. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q2-Q3 | In Progress
|  | Translational Science: Groundwater vulnerability, water quality | Science and Content 2 (SC2) | SC1.F Address gaps & limitations in data | Improve and maintain the Groundwater Vulnerability Tool by collaborating with state and local agencies, shared resources. Publish to support Private Wells measure. Add well water results tool (NH / EPA) to Private Wells measure. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q3 | Not Started |  | Eric Brown keft the CO Tracking program. This tool will be updated and maintained by the Water Quality Control Division (WQCD).
|  | Translational Science: Environmental Public Health Response to emerging issues | Science and Content 2 (SC2) | SC1.D Disseminate additional indicators & measures to address grantee priorities | CO Tracking will respond to emerging enironmental and public health issues such as COVID-19. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
| Strategic planning | Strategic Planning: Obtaining IRB designation for public health surveillance work | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Work with department, division, and branch leadership to officially designate CO Tracking's environmental public health surveillance work as "public health surveillance" by CDPHE's IRB | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q3 | Complete | The CDPHE Institutional Review Board (IRB) and its policies allow for "self-determination" of human subjects research by CDPHE employees. As a result, Tracking developed a memo template to be stored along with the files associated with public health surveillance projects for which IRB waiver is deemed necessary. Preparing and storing this memo for each potentially sensitive project increases transparency of our decisions to designate our work as public health surveillance.
|  |  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
|  | Strategic Planning: Improving environmental exposure data access | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Explore the use of public health authority to grant access to relevant environmental exposure and biomonitoring data from lab services database for environmental public health surveillance. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q2-Q4 | Behind Schedule |  | This project has been indefinitely delayed by the COVID-19 response. The work load and availability of staff at the CDPHE lab has been dramatically impacted by the COVID-19 pandemic, and it is uncertain when we will be able to resume these discussions. | In our short work on this project immediately prior to the onset of the COVID-19 pandemic, we became aware of hesitiancy on the part of the CDPHE lab to allow use of personally identifying infomration related to lab results related to other environmental exposures for public health surveillance projects. This is inspite of the fact that the CDPHE IRB regulations effectively allow us to make our own determination about what constitutes public health surveillance. We suspect that this hesitancy is a reflection of differences in instituational attitudes toward public health survieillance between the public health side of the agency and the environmental protection side. In short, the sensitive health data that we use routinely is arguably far more sensitive that an individual's water test kit results. Yet, there is an insitutional reluctance to share this information for environmental public health surveillance for fear that it would discourage participation in testing programs. This is a long way of saying that it could be usefulf to discuss these institutional differences at the national level and among grantees.
|  | Strategic Planning: Improving sub-county health outcome data access | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Explore the use of public health authority to grant access to relevant sub-county health outcome data from CDPHE's Center for Health and Environmental Data for environmental public health surveillance. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q2-Q3 | In Progress | Tracking developed a comprehensive data user agreement between our umbrella office (TEEO) and the data steward for a large proportion of the health outcome data we use in the tracking program (CHED). In this packet we cite our public health authority granted to our office by the Colorado Board of Health to access minimum necessary personally identifiable information that allows our program to compete the following tasks routinely: 1. Conduct descriptive analyses and assess spatial and temporal trends to better understand populations at risk. 2.Identify or examine state and local environmental health issues. Inform public health activities and policy. 3. Link data for the non-research purposes of responding to community concerns, investigating environmental health problems, and planning and conducting state and local specific public health activities. The aggreement is still pending; however, we are optimistic that our access to data for conducting routing public health surveillance will signficantly enhanced.
|  | Strategic Planning: Future of Tracking | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Develop internal strategic plan for remaining years of current grant and contemplate the future goals of the Colorado Tracking program. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q3-Q4 | Not Started |  | This project has been delayed by the COVID-19 response.
|  |  |  | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction |  | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
|  | Strategic Planning: Future of Tracking | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Explore evaluation processes to capture users, products, etc. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | In Progress
| Promoting National and Local Tracking Networks and Engaging Partners | Communications | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Develop and implement communications plan on an annual basis. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2 | Complete | Holly providing feedback on my first time completing the Comm plan was helpful
|  | Communications | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Develop and imlement partnership plan | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q2 | Complete | Holly providing feedback on my first time completing the Partner plan was helpful | A lot of partnership activities were on hold due to COVID19
|  | Communications | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Maintain Technical Advisory Group (TAG) to inform decisions about the Colorado Tracking program work plan, goals, and objectives. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Behind Schedule |  | Due to the COVID19 pandemic, TAG has not met
|  | Communications | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Colorado Tracking will participate in Tracking Awareness week annually. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4 | Not Started | CO Tracking page social media posts had great engagement and response | CO Tracking does not have individual social media so posts have to be scheduled between COVID19 information distribution
|  | Techincal Advisory Group (TAG) | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Communicate with the Techincal Advisory Group quarterly on program announcements and updates. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Behind Schedule |  | Due to the COVID19 pandemic, TAG has not been in use
|  | Communications | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Post monthly to CDPHE social media pages about Colorado Tracking topic areas as outlined in the Communications Plan. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | In Progress | Visits to website to showcase CO Tracking data | CO Tracking does not have individual social media so posts have to be scheduled between COVID19 information distribution
|  | Outreach | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | CO Tracking Staff will present on Tracking program-related methods and findings at conferences such as CSTE, Public Health in the Rockies, or Colorado Environmental Health Network. Webinars will be used to share information with partners and stakeholders. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Not Started
|  | Communications | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Review content to ensure messaging is appropriate and written in plain language. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | In Progress | Content that is in plain language helps expand our audience and inform more about CO Tracking program
|  | Communications | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Continuing work with Office of Communications and to disseminate messages and products to appropriate audiences. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | In Progress |  | Office of Comm. prioritized COVID19 data
|  | Communications | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Develop dissemination plan for messaging to ensure appropriate audiences are being reached. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | In Progress | Feedback from CCND for plain language and translation services
|  | Communications | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity | Work with PMO West to collaborate on a quarterly communications activity and participate in Tracking Week. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Not Started |  | Due to COVID-19 deployments, CDC PMO did not do a quarterly communications activity.
|  | Outreach | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Build on existing public health strengths through the development of academic partnerships to utilize the knowledge, expertise, and perspective of experts affiliated with local institutions of higher education. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Not Started |  | Due to COVID19, academic partnerships and presentations were not completed
|  |  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction |  | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
|  |  | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles
|  | Communication | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Use the Targeted Lead Outreach Tool to inform the need for a childhood lead poisioning prevention media campaign targeting new mothers and physicians. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | In Progress |  | Due to COVID, campaign will run into Y5
|  |  | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media
| Building National and Local Environmental Public Health Tracking Networks | Building networks | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Work with CDC and other data partners to strengthen existing NCDMs. This work will occur in Content Work Groups, in collaboration with our data stewards, and in the CDC fall workshops. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | In Progress
|  | Building networks | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Participate in National Tracking workgroups: i) SND ii) PMO iii) CWG . | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | In Progress
|  | Building networks | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Maintain sufficient local Tracking Program staff and expertise by evaluating, identifying and supporting training opportunities for Tracking staff and partners. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | In Progress
|  | Building networks | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs
|  | Building networks | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles
|  | Evaluation | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | CO Tracking staff will use outreach and required management spreadsheets to document activities likely to lead to public health actions. We will use CDC template to share both completed public health actions and activities that may lead to public health actions. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | In Progress
|  | Evaluation | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Report annual evaluation results to CDC | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q2-Q3 | In Progress
|  | Evaluation | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | Maintain portal aligned with CDC requirements and schedule annual portal review with CDC partners to ensure periodic evaluation | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | In Progress
|  |  | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Building networks | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | Work with Tracking web team to collect and submit analytics for Colorado Tracking portal | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q2 | Complete
|  | Building networks | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Maintain previous SAS code and XML software to gather and format our data into CDC-required format. Participate in required Data Calls with CDC and state partners | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | In Progress
|  | Building networks | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Work with Department Web Team to continue to display and narrarate data on state portal | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | In Progress
|  | Building networks | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | CO Tracking will extend the previous mini-grant deadlines to the 5 LPHAs who were awarded in Y3. Due to the COVID-19 response, these LPHAs will not be able to finish projects by the end of Y3 and will have by the end of Y4 to complete all deliverables. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q3 | In Progress
| Environmental Health Response | Surveillance: health disparities in access to care | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct environmental public health surveillance to project trends for health disparities and access to care. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | In Progress | Organized on-going meetings and identified project goals. Developed an analytical plan to deploy Enhanced Two-Step Floating Catchment Area method and identified necessary data sets.
|  | Translational Science: health disparities in access to care | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create visualization, interpretation, storytelling, & communications products from surveillance projects on trends in health disparities of access to care | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q3 | In Progress
|  |  | Technology and Informatics 1 (TI1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences |  | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
|  |  | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Oil and gas health information resposne program support | SC- Standardized & accessible env. & health surveillance data | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q2-Q3 | In Progress | Supported OGHIR data dashboard development and maintenance. This dashboard presents self-reported health concern data related to oil and gas activity. Tracking staff worked to update and maintain the dashboard while OGHIR staff were on extended leave. Tracking also provided technical assistance in a Tableau-based report for the OGHIR program.
|  |  | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Spatial analysis of free radon test kit distribution | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q2-Q4 | In Progress | Completed spatial analysis of free radon test kit distribution and demographic data related to LIRMA program qualifications to identify areas for future free test kit distribution activities. | Many of the communication platforms used for targeted outreach rely on target zip codes. From an analysis perspective, this is difficult to achieve due to data availability for ZCTAs and the imperfect crosswalk between ZCTAs and zip codes. Tracking staff assigned points to census tracts and used tract-to-ZCTA crosswalks to identify zip codes of interest.
[5 empty] | COVID and Air Manuscript etc. |  |  | Q1-Q3 | Complete | Tracking completed an extensive enviornmental public health surveillance project investigating the potential link between long-term PM2.5 exposure and increased risk of COVID-19 infection, hospitalization, and mortality. We found that, in general, an increase in long-term exposure to fine particle pollution is associated with more COVID-19 infections, hospitalizations, and deaths, but the lack of localized pollution data means the relationship is uncertain. However, our analysis clearly shows a significant association between communities of color and COVID-19 outcomes at the Colorado census-tract level. In addtion, Tracking authored and publicly released a white paper with our findings and we are currently the process of submitting the manuscript to a peer-reviewed journal. | A lack of an accepted standard for census tract level exposure to long-term PM2.5 data was a recurring challenge. | Developing ways to validate the accuracy of community-scale PM2.5 exposure data would greatly improve our ability to link this exposure to adverse health outcomes more definitively.
|  |  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Collaborate with Vector-borne and Zoonotic Disease Unit to display rabies case data. | SC- Standardized & accessible env. & health surveillance data | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q2 | Complete | Worked with Rabies program staff to improve their data dashboard and share best practices for maintenance. | This project was put on hold during Y3 due to Rabies' staff extended leave.
Year 3
| EH17-1702 Budget Period: |  | August 1, 2019 - July 31, 2020
| Date Submitted to CDC: |  | 2019-03-31
| No more than 10 words per project title. Describe full project in Project Narrative tab. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. There is a minimum of two activities for every project. | One task per row; no more than 5 sentences per task. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project. | Continuation Report (Section I)
| Project Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline | Status | Successes | Challenges | CDC Program Support Needed
| Prepare for and track climate change-related impacts to environmental health | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Develop state added measures such as wildfires, temp., heat island, or drought | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2 | Complete | CO Tracking implemented climate indicators in two places on the Tracking website: on the Environmental Public Health Snapshots (county profiles) and a Climate Indicators data portal page. The county profile shows temperature and severe drought over time. The data portal dashboard features extreme heat, extreme precipiation, severe drought, and historical wildfire perimeters. | Timely data -- current dashboard only goes to 2016 | Investigate a potential dataset for "extreme cold" that utilizes the NLDAS remote sensing data
|  | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work |  | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
|  | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG |  | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence
|  | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Create webpage with CDPHE to compile all climate change-related data from different departments. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q2-Q3 | Complete |  | The department created a new climate change team, which took several months. Colorado Tracking has yet to schedule a meeting with this group in the first 2 quarters of Y3
|  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities |  | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences
|  | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Leverage partnerships with local leaders such as Colorado Health Institute and local Universities to disseminate climate change communication materials | Comm- Targeted comm. products & messages | Comm- Engaged partners & users | Q2-Q4 | Behind Schedule |  | Finding the appropriate contacts at local universities has been difficult. | Due to COVID this project was not completed
|  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Continue leading TAG climate change subgroup discussions to inform national CWG with local perspectives. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q2 | Complete | Engaged TAG climate change group to inform CWG as well as the climate change dashboard. Receiving local input was valuable for our cimate change dashbaord development, as we were able to include indicators that were of intreset to locals. | The TAG climate change group had become increasingly less engaged over-time. Getting feedback and ideas from this group took several months and not every member provided input.
|  | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Participate in national climate change CWG's potential NCDM conversations, researching locally relevant indicators. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | Complete | Attended Climate Change CWG meetings at the end of 2019. Researched and implemented locally relevant climate indicators, including historical wildfire perimeters statewide, extreme heat days per year, and severe drought (weeks per year, % area affected). | Did not receive meeting information due to being a new Tracking staff member and as a result, missed many of the calls.
|  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Work with CDPHE Water Quality Control Division to update fish consumption advisory information. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2 | Complete | Established an action plan for improving the fish consumption advisory resources on the CDPHE website. | The fish consumption advisory program does not have any dedicated staff. As a result, getting the project off the ground has been difficult (competing priorities, complicated schedules, identifying data sources, etc.)
|  | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Display harmful algae blooms sampling information received from the Water Quality and Control Division. | Comm- Targeted comm. products & messages | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2 | Complete | Established an action plan for improving the public-facing resources for harmful algae blooms on the CDPHE website. This will include displaying sample results, posting a new FAQ document, and providing information on where the public can receive up-to-date information about a specific waterbody. | HAB response in Colorado involves multiple divisions within CDPHE and agencies around the state. Coordinating and building consensus across all parties has been an important but challenging process.
| Expand community design datasets, training, and communications products | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Recruit and host healthy community design intern from local university graduate programs about public health, urban planning, environmental health, and built environment. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q3-Q4 | Not Started |  | Due to COVID this activity had to be canceled as the depatment would not allow for new hires that were not apart of COVID response
|  | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs |  | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
|  | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles |  | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
|  | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities |  | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
|  | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Develop relationship with transportation agencies and professionals to expand Tracking portal and/or communication products. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q2-Q3 | Not Started | Identified Colorado Department of Transportation (CDOT) contacts through the CDPHE Injury Epidemiologist to inquire about motor vehicle crash data. | CDOT did not respond to contact attempts. Enrolled in a data symposium hosted by CDOT scheduled for May 2020 to participate in data symposium and meet CDOT contacts. However, this event was cancelled due to COVID-19.
|  | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Develop state added measures to help urban, rural, and frontier counties assess their built environment contribution to health outcomes. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4 | Complete | Developed a visualization tool for state active transportation data (BRFSS) and updated visualization tool for perceptions of access and safety for walking and biking.
|  | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Explore relationships with organizations increasing physical activity among children, such as Safe Routes to School. Informing them of the data on the Tracking portal, and seeking their input for developing state-added measures, may increase evidence-base for assessing physical activity among children. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q2-Q4 | Behind Schedule | Colorado Safe Routes to School program is currently conducting a census survey of all program in the state. When survey results are ready survey data will be presented with health data via a webinar.
|  | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Continue to provide CO Tracking data,GIS assistance, and health education resources to CO Choose Safe Places Pilot program. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2 | Complete | Used environmental facility data and clean-up data as a proxy to potential points of exposure. These data were deployed in an online web application. The application is used to perform an area search around a proposed early childcare facility location. This provides a screening tool for program staff to make recommendations based on a proposed facilities location as it relates to potential environmental hazard exposures and small children. | Obtaining granular environmental measurements associated to the potential points of exposure.
|  | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Support the National Community Design Work Group - Active Transportation project in mapping and measuring intersection density using Colorado OpenStreetMap data. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q2-Q4 | Complete | Created presentation with results of findings and communicated results to Project Workgroup - examining directions and process improvements
|  | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Explore the potential for development, implementation, and standardization of spatial and spatiotemoral surveillance techniques for marijuana usage from available data sources. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2 | Complete | Colorado tracking worked with Marijuana Health Monitoring and Research program to adapt cannabis indicator definitions for monthly county-level surveillance. This project is still in progress, but so far we have completed the development of SAS code to query hospital and emergency department discharge data sets. We are currently piloting the analysis and visualization of this data source.
| Improve spatial resolution and metadata for radon | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Develop routine analysis of radon concentration data at the sub-County level. Evaluate relationship to social determinants of health and identify statistically significant spatial clusters of elevated radon concentration. Assess quality of pre- and post-mitigation field in radon data set. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2 | Complete | Colorado Tracking adapted the Minnesota radon/social determinants of health analysis to identify demographic characteristics associated with radon testing. The results of this result were shared with the Colorado Radon program. Targeted outreach is scheduled for later in Spring 2020. | Quality of pre- and post- mitigation flags is poor. Approximately 60% of results were excluded from the analysis due to missing mitigation flags. Analysis project was going to be presented at CSTE in June 2020, but the conference was cancelled.
|  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Work with administrators of Behavioral Risk Factor Surveillance System to add radon question(s). Radon is high throughout Colorado, and Tracking will work with indoor air and risk assessment professionals to develop questions gauging the public's awareness of the need to reduce their indoor radon levels or other needed information to inform radon-related programs, plans, and priorities. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2 | Complete | Radon questions (4) are being asked on the 2020 BRFSS. These results will provide CDPHE with a fourth year of data to compare. Work projected for year 4 and 5 (?) includes evaluating the results of BRFSS radon quesitons to assess trends in health disparities.
|  | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Explore adding question to lab-reported radon information to discern whether test results are pre- or post-mitigation to inform prevalence of local radon testing, need for further radon mitigation, etc. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2 | Complete | Spatial resolution has been improved by geocoding locations to census tract level and posted to CO Tracking portal. | Continue to have challenges even getting an in with the labs to discuss adding these data elements. I've proposed in a recent email that we (Colorado Radon Program & Tracking) identify one lab that may be the most open or able to move this ahead. Once we've done that, if we get the OK to have the conversation, we will try to get on the card printing schedule. There are two issues. One is simply making an unfunded request to a private business and two, getting on the, often years out, bulk printing schedule.
|  |  | SC1.D Disseminate additional indicators & measures to address grantee priorities | Develop best practices for gathering and updating national lab radon dataset. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Complete | Working with limited set of lab parnters, Tracking with support from AARST and CDC, has successfully received an attempted national data set. Two subsequent partial data submissions have occurred. The best practices, including data transfer and data obfuscation, are set. The missing part is additional private lab support. Many of the best practices depolyed are either directly a result of Radon CWG or modeled after Tracking protocols.
|  | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Explore connecting CDC Tracking database with EPA Virtual Exchange Services radon database. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Complete |  |  | Unless there are significant program changes at either EPA or CDC between now and the scheduled completion date this may not be successful in the current timeframe. Tech and policy incompatibilities are the main challenge. Tech being very costly and moderately time intensive to shift. Policy being very slow or impossible to shift in the near term.
| Expand marijuana surveillance and associations with health outcomes | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Mapping marijuana dispensary locations and zoning boundaries to monitor adverse health outcomes and potentially overburdened populations with negative build environments through compounding with food desserts and/or alcohol outlets. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2 | Behind Schedule | Created a timelapse of retail dispensary locations over time, drafted a story map, and collaborated with other CDPHE staff to create a zoning/built environment map | Due to staffing changes, competing priorities and COVID, this project was unable to proceed.
|  | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Explore with CDPHE injury epidemiologists potential associations between policies (e.g., counties with and without retail marijuana permits given), built environment features (e.g., retail alcohol or marijuana outlets) with health outcomes (e.g., motor vehicle injury). | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q2-Q4 | Behind Schedule |  | Due to staffing changes, competing priorities and COVID, this project was unable to proceed.
|  | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data |  | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences |  |  |  | Due to staffing changes, competing priorities and COVID, this project was unable to proceed.
|  | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | Share marijuana Tracking information with other Tracking states that may have upcoming policies seeking to legalize medical or recreational marijuana use. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Behind Schedule |  | Due to staffing changes, competing priorities and COVID, this project was unable to proceed.
|  | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | Collaborate with Marijuana personnel to disseminate data and messages about marijuana data available on the Tracking portal | Comm- Targeted comm. products & messages | Comm- Engaged partners & users | Q1-Q4 | Behind Schedule |  | Due to staffing changes, competing priorities and COVID, this project was unable to proceed.
| Improving asthma data surveillance | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Expand data sources to improve sensitivity and timelinees of routine asthma surveillance (e.g., APCD, EMS, CORHIO, CHORDS, etc.) | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | Colorado tracking established a Data Use Agreement between our parent division within the health deparment and the Health Facilities and Emergency Medical Services Division to allow access to a weekly data feed for emergency medical services calls related to asthma. This data set will be used in a prospective asthma surveillance model. Colorado Tracking has also continued to develop subject matter expertise in working with the Colorado version of the All-Payer Claims Database, working on projects to improve data quality and optimize database design. Colorado Tracking also completed a data use agreement to receive weekly asthma surviellance data from Children's hospital Colorado for use in the surveillance of enterovirus D68/acute flaccid myelitus surveillance. Colorado Tracking has also begun working on a data use agreement with the Statewide Syndromic Surveillance program, operated by Tri-County Health Deparment, to obtain syndromic surveillance data for asthma-related emergency department visits. We have also begun working to amend our intra-agency agreement with Colorado's Medicaid program to allow direct access to Medicaid claims data for conducting environmental public health surveillance. | Developing data use agreements for individual projects is time consuming, and identifying best practices for data access and storage of real-time data pose many complicated logistical questions. | Use the tracking network to identify strategies and best practices for engaging data stewards from common sources of health outcome comes potentially associated with environmental exposures. Using tracking network resources to develop best practices for accessing and storing real-time and near-real-time surveillance data.
|  | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Develop, implement, and standardize enhanced/prospective asthma surveillance techniques. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2 | Complete | Colorado tracking created an R-markdown template for automatically generating reports from enhanced/prospective disease surveillance analysis projects. The tracking program collaborated with the Childhood Lead Poisoning Prevention program to conduct a literature review of prospective/enhanced disease surveillance methods. This work allowed us to identify and develop standardized analysis techniques for routine prospective surveillance of our environmental epidemiology-related health outcomes. The project was piloted on childhood lead poisoning BLL data and asthma emergency department visits, but can be adpated to fit other NCDM data feeds. | Obtaining access to timely data is an ongoing challenge with implementation of standard surveillance procedures. Our health and environmental data pipeline suffers from inefficiencies stemming from issues related to atomized data formats, outdated or sub-optimal data storage, separate/uneven/restricted access among staff to case level data, and lack of integration of data health and environmental data into one database platform. | Help develop strategies for engaging state and national data partners for obtaining real-time and timely health outcome data for public health surveillance. Use the tracking network to help develop strategies for data pipeline modernization.
|  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Develop and maintain prospective asthma surveillance tool to monitor circulation of enterovirus D-68 (EV-D68) and acute flaccid myelitus (AFM). | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | Complete | The Colorado Tracking program developed a prospective weekly surveillance tool that pairs passive asthma emergency department data and laboratory data for early detection of EV-D68 circulation. The results suggested prospective spatiotemporal analysis of asthma surveillance data complements existing clinical surveillance of EV-D68/AFM. As a result, Colorado Tracking worked to secure data use agreements with syndromic surveillance and emergency medical services data stewards to gain access to additional sources of near-real time passive asthma surveillance data to be used in the production version of the tool. Colorado Tracking submitted a breakout presenation on this project to CSTE, as well as a poster presentation to AAG. The tracking program will continue to use this tool to monitor asthma emergency department visits through out the late summer and fall seasons of 2020.
|  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Create communications plan for asthma surveillance project deliverables. | Comm- Targeted comm. products & messages | Comm- Engaged partners & users | Q1-Q4 | Not Started |  | Due to COVID this project was not completed.
|  | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Continue developing outdoor air data sources for environmental public health surveillance. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete | The Colorado Tracking Program collaborated with the Colorado Oil and Gas Health Information and Response Program to help analyze measurements of combined volatile organic compounds (VOCs) collected at local schools. The Colorado Tracking program developed a computer program to automatically download and process the reported data, display the results graphically, and send automatic email alerts if elevated levels of combined VOCs are detected. This automated data pipeline will allow the department to respond within 72 hours if elevated concentrations of VOCs are detected in the future. | Maintaining engagement in the outdoor air TAG sub-group.
|  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data |  | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
|  | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Create communications tool for educators about asthma triggers. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q2-Q4 | Not Started |  | Due to COVID this project was not completed.
|  | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Expand upon the feasibility analysis of using social media streams for environmental health issues. Tracking will hire a contractor to design a program and algorithm to aggregate Colorado-based tweets for keywords related to asthma using machine learning. The results will be used to help our new asthma surveillance system | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Complete | Colorado tracking has provided resources to develop an R script to scrape asthma-related Twitter data. Tracking has also worked with CDPHE's Perfomance Management and Data Visualization Specialist, the state office of information technology, and Google's State and Local Government liason to develope a Cloud Function/scheduler that makes regular calls to the Twitter data script to collect asthma-related tweets. We are also partnering with Google to develop machine learning tools for cleaning and analyzing the asthma-related Twitter data. | Complex subject matter, requires expertise beyond the scope of traditional enviromental epidemiology. Data quality of asthma-related tweets is an issue of concern. It is possible that continued training of a supervised machine learning algorithm could improve data quality, but this is a challenging area of data science/machine learning. | Use tracking network resources to explore text-mining and machine learning techniques for analyzing social media data sources for environmental public health.
| Expand lead surveillance, outreach, and communications | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Support CDPHE's Childhood Lead Poisoning Prevention program through the use of tracking program NCDMs and routine GIS and statistical analysis of blood lead data. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | Performed routine analysis of blood lead reports. Completed several descriptive analytical projects to examine follow-up, prioritization, and attributes of elevated cases.
|  | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | Develop, implement, and standardize enhanced/prospective blood lead surveillance techniques | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q2-Q4 | Complete
|  | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Maintain current Targeted Lead Screening tool for outreach and communication about childhood lead poisoning, and continue supporting lead program's outreach and communications efforts | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2 | Complete | Updated Targeted Lead Screening tool with updated data (2013-2017).
|  | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | Work with CDPHE Office of Communications to publish press releases and other information about lead screening tool to local media partners | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q2-Q4 | Behind Schedule |  | Due to COVID communitcation priorities, this activity was not completed
| Promoting National and Local Tracking Networks and Engaging Partners | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Develop and implement communications plan on an annual basis. | Comm- Targeted comm. products & messages | Comm- Engaged partners & users | Q1-Q2 | Complete | Submitted communications plan in October | Did not have a health eductor hired, wrote the communications plan vaguely
|  | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Colorado Tracking will participate in Tracking Awareness week annually. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4 | Complete
|  | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Communicate with the Techincal Advisory Group quarterly on program announcements and updates via MailChimp. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Not Started
|  | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Post monthly to CDPHE social media pages about Colorado Tracking topic areas as outlined in the Communications Plan. | Comm- Targeted comm. products & messages | Comm- Engaged partners & users | Q1-Q4 | In Progress | Have posted 6 social media posts | Did not have a health educator hired until March
|  | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | CO Tracking Staff will present on Tracking program-related methods and findings at conferences such as CSTE, Public Health in the Rockies, or Colorado Environmental Health Network. Webinars will be used to share information with partners and stakeholders. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete | Presented at CPHA and CEHA. Will present at CSTE in June
|  | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Review content to ensure messaging is appropriate and written in plain language. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete
|  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Develop dissemination plan for messaging to ensure appropriate audiences are being reached. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete
|  |  |  | Continuing work with Office of Communications and OPPI to disseminate messages and products to appropriate audiences. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete
|  | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activity with 1 or more Tracking grantees in addition to program-wide activity | Work with PMO West to collaborate on a quarterly communications activity and participate in Tracking Week. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete
|  | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | CO Tracking Staff will present on the Colorado and National Tracking programs at the Colorado School of Public Health and at the University of Colorado Denver. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q2-Q4 | Complete | Presented the Tracking program to three institutions of higher education (CU Boulder, CSU, Colorado School of Mines) in order to promote awareness of the Tracking program among students and faculty. This initiative is in line with the CDPHE's goal to become an academic public health department. | Unable to connect with the specific institutions listed.
|  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction |  | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
|  | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles |  | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
|  | Communications 2 (C2) | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner |  | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues
|  | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Present results, findings, or deliverables from enhanced/prospective blood lead and asthma surveillance projects at national and/or local conferences. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q2-Q4 | Complete
|  | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Collaborate with Colorado Healthy Housing coalition to disseminate and promote the use of results, findings, or deliverables from enhanced blood lead and asthma surveillance projects. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q2-Q4 | Complete | Regularly attended and participated in Colorado Health Housing coalition meetings. Connected Kevin Berg and Dr. Kate Johnston for collaboration around enhanced asthma surveillance work and work on healthy homes. Promoted enhanced blood lead and asthma surveillance system during Health Housing coalition meetings. | Due to COVID all meetings in early 2020 were post-poned or cancelled. Meetings in late 2020 were held virtually with lower attendence and capacity due to local and regional COVID deployments.
| Building National and Local Environmental Public Health Tracking Networks | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Work with CDC and other data partners to strengthen existing and develop new NCDMs. This work will occur in Content Work Groups, in collaboration with our data stewards, and in the CDC fall workshops. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete
|  | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Participate in National Tracking workgroups: i) SND ii) PMO iii) CWG . CWG participation during Y3 includes: Climate, Community Design, Sub-County data work, and CO-chair analyes subteam developing new drinking water NCDMs. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete
|  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Maintain sufficient local Tracking Program staff and expertise by evaluating, identifying and supporting training opportunities for Tracking staff and partners. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
|  | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | CO Tracking staff will use outreach and required management spreadsheets to document activities likely to lead to public health actions. We will use CDC template to share both completed public health actions and activities that may lead to public health actions. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Complete | To date Tracking has submitted 6 PHAs
|  | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Report annual evaluation results to CDC | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q2-Q3 | Complete
|  | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | Maintain portal aligned with CDC requirements and schedule annual portal review with CDC partners to ensure periodic evaluation | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Complete
|  | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements |  | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
|  | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | Work with Tracking web team to collect and submit analytics for Colorado Tracking portal | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q2 | Complete | Submitted analytics to CDC in September | The Colorado Tracking portal at the time did not have access to analytics that were seperate from the Departments, making it very difficult to collect all requested anaytics.
|  | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Maintain previous SAS code and XML software to gather and format our data into CDC-required format | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete
|  | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Participate in required Data Calls with CDC and state partners | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete
|  | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Engage partners at the Colorado Hospital Assocation to develop data use agreement for use and reporting of sub-county hospitalization and emergency department visits. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | In Progress | Colorado Tracking used resources provided by the national tracking program to create a two-page summary document to be shared with the Colorado Hospital Assocation. A meeting with the Colorado Hospital Association has been scheduled for March 2020 to discuss our proposal for obtaining their approval to submit sub-county NCDM data to CDC. UPDATE: This meeting was delayed by the COVID19 pandemic response. |  | Use tracking program resources to negotiate with National Hospital Assocation to negotiate use of discharge data sets for sub-county public health surveillance.
|  | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Identify and explore new or novel data sources for other environmental public health surveillance (e.g., social media, electronic health records, EMS). | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Colorado tracking established a Data Use Agreement between our parent division within the health deparment and the Health Facilities and Emergency Medical Services Division to allow access to a weekly data feed for emergency medical services calls related to asthma. This data set will be used in a prospective asthma surveillance model. Colorado Tracking has also continued to develop subject matter expertise in working with the Colorado version of the All-Payer Claims Database, working on projects to improve data quality and optimize database design. Colorado Tracking has also begun working on a data use agreement with the Statewide Syndromic Surveillance program, operated by Tri-County Health Deparment, to obtain syndromic surveillance data for asthma-related emergency department visits. We have also begun working to amend our intra-agency agreement with Colorado's Medicaid program to allow direct access to Medicaid claims data for conducting environmental public health surveillance. | This effort was directly impacted b the COVID19 response. I think we need to role this over into the new workplan. We haven't made an attempt to reschedule this meeting since the pandemic began. I'm not sure when the best time would be to try to resume this effort. The effort also depended in part on Kirk Bol participating, who has also been heavily invovled in the COVID19 resonse, so we will need to make sure we coordinate with him again when we want to pick this back up.
|  | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Import and pilot 2-3 key CO Tracking Datasets within the CDPHE Open Data Portal. Evaluate if there is an increased usage and visibility of the datasets from the Open Data environment | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3 | Complete | Added the pilot blood lead level vulnerability data to the CDPHE Open Data Portal
|  | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Work with Office of Communications to assist in the department-wide website migration. This includes the Colorado Tracking portal content. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2 | Complete | Migration from Drupal 7 to Drupal 8 has been completed. Navigation of the site has been imporved. | The new layout has created some challenges with Tableau dashboards and sizing.
| Building Environmental Public Health Capacity at the Local Level | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Create an environmental public health mini-grants project .CO Tracking will release a Request for Applications (RFA) to local and tribal health departments; we ask applicants to propose a small-scale environmental project in their jurisdiction, that will either use Tracking data to inform the project or gather new data that theTracking program can add to the portal. Based upon our budget, we will plan to fund four local or tribal health departments. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress | Colorado Tracking has funded 5 local public health agenices to complete an environmental health project. Four of the five projects are water testing projects. Three of them are testing private well water and providing health education to high risk areas that have been identified in their jurisdications. One of the water projects is testing water in the home in mobile home parks, they are also providing the testing and health education. The last project is an air quality project. This jursidiction has places Purple Air monitors around schools.
| PFAS | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create a statewide inventory map of potential PFAS exposure sites (airports, fire stations, potentially COGCC-record fire locations | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2 | Complete | Worked with hazardous materials, water quality, env epi and the executive directors office to identify data sets, data gaps and platform to develop and share are drinknig water source system and community prioritization web mapping application. | Not a lot of exact data on PFAS use. Need to use several data sets as a proxy. Could use better inventory.
|  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create a map of areas of concern, i.e. water sample sites with high PFAS results (precise location obscured, added buffer zones) | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2 | In Progress | The combination of the PFAS inventory tool with HE/EJ community information is beginning to provide this information. | Still in development
|  | Science and Content 2 (SC2) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Create public water system sample result map (from historic samples (2013-2014) and new samples coming from state-funded PWS testing) | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q2-Q4 | Complete | The PFAS team created a data dashboard from the results of the 2020 PFAS Sampling project for fire districts, surface water samples, and public water systems. Internal maps were created for programmatic use.The public-facing data dashboard only mapped surface water sample sites due to concerns for security, privacy, and lack of comprehensive public water system boundaries, but allowed for data to be filtered by principle county served and searched by name. | Combining previous water system sampling results with the 2020 Sampling Project's results was not feasible given the data infrastructure. Mapping drinknig water sample results was not feasible given concerns for security of the system entry point location and a lack of comprehensive water system service boundaries in the state.
|  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Utilize the statewide inventory map, areas of concern map, and HEEJ data to recommend targeted sampling | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress
|  | Science and Content 1 (SC1) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Conduct surveillance of biomonitoring data from CDPHE labs | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress
|  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Track public water system enrollment for the PFAS Sampling Project | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2 | Complete | Created and maintained a live, public-facing dashboard that displays public water system eligibility, enrollment status, and a map of project coverage by county. This has been utilized internally to track enrollment progress and develop a sampling strategey. In addition, the dashboard was used by public water systems, the media, and the general public. | The enrollment process was not automated, requiring significant staff time to compile enrollment data and update the dashboard.
|  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Inform the WQCD Response as to the Prioritization of PFAS Sample Locations using GIS/spatial data summarization including EPA PFAS Data Point Locations, Physical Setting Vulnerability Scores per SWAA Boundary, and HE/EJ inclusion population data per census tract inside SWAA | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2 | Complete | Completed the assigned GIS Data Analysis and Presentation of Data to the WQCD | n/a | n/a
| COVID | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Participate in Epidemiology Operations branch of CDPHE's COVID-19 response by providing technical assistance to local health department staff regarding epidemiologic case investigation and long-term care facility outbreak response; maintaining data integrity for COVID cases in the Colorado NEDS database (CEDRS); analyze and synthesize data across counties to identify clusters obscured by county-level data; assisting with local public health departments' case investigation and contact tracing efforts; triaging calls in the CDPHE epi call center | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q3-Q4 | Complete |  | The COVID deployments resulted in significant reductions in staff time available to work on remaining Tracking projects.
|  | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Served as Lab/Epi liaison, facilitating communication between laboratory, epidemiology, and outbreak investigation staff. Create R/SQL script to monitor testing status of high priority COVID19 specimens. Fulfilled ongoing COVID19 case data request to University of Colorado's academic modeling team. Assessed geocoding accuracy of COVID19 case and testing data. Created an internal dashboard to visualize and assess completeness of race/ethnicity data. Provided imputed estimates of race/ethnicity distribution of COVID19 infection, hospitalization, ICU, mortality and testing rates. Explored mapping and data visualization options for COVID19 indicators, and consulted on developement of statewide COVID-19 dashboard. Created weekly case and testing spatial density maps for COVID19 response team. Conducted spatial and temporal analysis of COVID19 outcomes at the county and census tract level. Analyzed association between census tract-level social determinants of health, comorbidity rates, & air pollution exposures with COVID19 outcomes. Provided briefings on geographic disparities of COVID19 infection, hospitalziation, ICU, mortality, and testing rates to COVID19 state epidemiologist, COVID19 response staff, and state health equity office. Participated in daily and weekly COVID-19 surveillance meetings. | SC- Standardized & accessible env. & health surveillance data | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q3-Q4 | Complete | Project continued into Y4
|  | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Investigate the effects of short- and long-term exposure to air pollution (PM2.5, ozone, and NO2) on cases, hospitalizations, and fatalities associated with COVID-19. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q3-Q4 | Complete | Project continued into Y4
Note on E165: Berg, Kevin: Maybe we can work together to flesh this one out more, or maybe just shorten to to create "communications plan for asthma surveillance project deliverables" and put in "Communications" section
Note on E166: Berg, Kevin: Should these (in purple) be in the 'Communications" section?