## Instructions
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Annual Performance Report (APR) - Section I
Budget Period: August 1, 2020 - July 31, 2021(Budget Year 4)
Reporting Period: February 1, 2020 - January 31, 2021.
Instructions Please use this workbook to document progress for your Budget Year 4 Work Plan as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section I of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)." The Work Plan tab includes the Year 4 plan you submitted in your 2020 APR. Columns I-L, with the orange Continuation Report (Section I) banner, are where you should enter information about your progress. For each activity, select the Current Status from the dropdown menu (not started, complete, in progress, or behind schedule) and provide relevant information under Successes, Challenges, and CDC Support Needed.
Technical Support If you need technical support when using this template, email your project officer.

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
Florida EPHT Project Narrative Budget Year 4
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan." Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
SCIENCE AND CONTENT | Project 1- Update NCDMs on state portal
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Nationally Consistent Data Measures (indicators) on the State EPHT Portal have been updated to the most recent data available. As in the past, the data was queried from data stewards and stored in a SQL Server database. After transformation, the data is served to the EPHT web portal and made available with tables, maps, and charts. Messaging and metadata have been updated as needed. Childhood lead poisoning data, hospitalizations, and ED Visits have been updated to include 2019 data for NCDMs. | We continually refine the messaging/metadata about the NCDMs. We have a footnote regarding the ICD9/ICD10 transition, and added a new footnote during Year 04 about the need to use caution when interpreting rates, especially for sub-county geograpies. | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 4
|  |  | 3 | 5 | 7 | 4 | 19
Project 2-Update jurisdictional priority measures on state portal
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Florida EPHT Program has continued to include some measures on the EPHT portal that are not NCDMs but are state priorities. This includes occupational health measures, built environment measures, life expectancy, and dog bites. Unlike NCDMs, these state priority measures are not updated every year, but rather every 2-3 years. The built environment (community access) measures were updated in late 2019. The latest Occcupational Health indicators for 2016 were added during Year 04. | Some of these optional measures are included in our community profile reports. These reports have been available at the county and zip code level since 2013. Florida has continued to refine the zip code functionality for these reports. Life Expectancy data was added during this reporting period (5-year estimates). The community access measures include estimates of the percent of population that lives within a half mile of fast food, healthy food sources, parks, and trails. It also includes some busy roadway measures to estimate the population exposed to near-roadway air pollution.
TECHNOLOGY AND INFORMATICS
Project 3-Work with content workgroup to adopt newly proposed NCDMs
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Florida EPHT Program has joined several of the new Content Workgroups, and is starting to participate in data development discussion. In the past, Florida EPHT worked with the Council of State and Territorial Epidemiologists (CSTE) on a sub-county life expectancy mapping project. This census tract level analyses has revealed interesting relationships between mortality data and economic hardship. The mapping used ArcGIS Online to provide interactive displays to stakeholders like county health departments and community groups, and is now a part of the state portal. | The PI for Florida EPHT (Chris DuClos) has worked to provide adequate representation on the Content Workgroup Teams. Florida currently has representatives on the Community Design Team, HABs Team, Hospitalization Team, COVID and Extreme Weather Team, Health Equity Team, Drinking Water Team, Sub-county Geography Team, Radon Community of Interest, as well as SND and PMO Teams.
COMMUNICATIONS
Project 4- Maintain public EPHT portal that complies with CDC requirements
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Florida EPHT web portal is available at www.floridatracking.com. Portal evaluation was completed with Project Officer in summer 2020. In Year 04, we have worked to meet all CDC requirements, and improved the reporting of our Google Web Analytics. Metadata and messaging are being continually refined and improved based on user feedback and data updates (such as the ICD9/ICD10 transition). | Florida will work with CDC on portal reviews during Year 05, as needed. Portal redesign (for user selection interface) is ongoing, and will continue in Year 05.
Project 5- Develop tools and processes to improve data quality
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Florida has continued to develop robust transformation routines to convert raw data to NCDMs and evaluate data quality and utility. Florida’s SQL Server database was recently upgraded to a newer version of SQL, which opens up some additional transformation routines (e.g. for drinking water data). In Year 04, the database manager for EPHT has continued to work on tools and methods to make data more useful, accessible, and timely through improvements to stored procedures, views, and other database objects. | The EPHT Database Manager continues to refine the SQL routines that are used to serve our data to the web. In the past year, we have made improvements to the way that transfers are handled, and we have looked at the impact of de-duplication routines on prevalence estimates. Florida has added additional parameters to customizable links to get to a more targeted dataset. Search routines were re-evaluated and improved on the web portal. Census tract geographies were added for select indicators when possible to enhance the granularity of the data. Community profile reports were improved with ZIP code level rates for select hospitalization and ED measures.
PROGRAM SERVICES
Project 6- Maintain the technology infrastructure for submitting NCDMs during data calls
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Florida EPHT staff members have continued to follow the how-to-guides to construct data sets according to XML schema needed by CDC, and then submit data via Secure File Upload. These data processing and upload routines have been refined over the last few years of scheduled data calls, and the technology to submit Tracking NCDMs to CDC is updated regularly (e.g. newer versions of XML schema). In Year 04, Florida EPHT has continued to provide data to the National EPHT portal, while also working with CDC contractors to improve process efficiency and the accuracy of NCDM documentation. | The EPHT Database Manager (John Folsom) has continued to provide feedback on How-To-Guides to CDC and contractors. Data are processed and evaluated for QA post submission and post CDC release to the public.
Project 7- Establish electronic access to data sources
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| In Year 04, Florida EPHT has continued to work with data owners and subject matter experts to obtain electronic access to data sources and to document process improvements needed to increase availability and accessibility of data through integrated seamless transfers. The EPHT database manager has already documented process improvement through metadata in SQL Server, and has updated such documentation in Year 04. Florida will continue to work to create repeatable and reliable routines for addressing sub-county data analysis needs, and work with data owners on challenges documented in the gap analysis. | The hospitalization and ED database in Florida can be directly accessed by EPHT staff, in the creation of NCDMs and other data measures (e.g. injuries for dog bites).
Project 8- Increase data management efficiency
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| In Year 04, data transformations have been conducted and documented using either SSIS script packages or SAS code. Existing routines have been documented with Application Status Reports by EPHT staff, and these routines include reusable electronic scripts to increase data management efficiency, repeatability, and accuracy. Florida has continued to work on enhanced documentation of standard operating procedures, to include scripts that more efficiently allow for data transformations and APIs that allow for data access. More robust data management routines and APIs will simplify the use and conversion of raw data and increase efficiency of data access by end users. | The Florida EPHT Database Manager will present on these database enhancements if requested by the SND Workgroup. Troubleshooting of routines occurs when necessary. Code refactoring for efficiency is an ongoing and iterative process.
Project 9- Develop and implement annual communications plan
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Florida EPHT has continued to engage key Tracking audiences, including data stewards, state and local health department staff, policymakers, TAG members, and relevant community organizations. In terms of strategy, Florida has updated the state Communications and Outreach plan, which has existed for many years. This plan now includes SMART objectives to better measure the impact of these events and activities. Florida has continued to work with Communications staff to target key Tracking audiences, such as policymakers and our Technical Advisory Group. Florida’s outreach plan evolves every year to add events, change focus of social media, and develop new videos. | The annual communications plan was submitted during October 2020, and will be updated as needed during Year 05. The pandemic affected our ability to go to in-person events, so we have shifted to more virtual content. Chris DuClos presented on a virtual conference during 2020, and Diane Neidhart (Communications Specialist) is coordinating virtual presentations for Children's Week at the state capitol.
Project 10- Provide regular updates about tracking activities to partner via email distribution
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| In Year 04, Florida has continued to write a quarterly E-newsletter and distribute it to stakeholders. Florida has continued to allow website visitors to opt-in for the newsletter if they want to receive it. Florida distributes Tracking E-news quarterly. The goal is better communications between EPHT program and stakeholders (about available resources like data and outreach products). | E-news emails have been tracked with Active Campaign, which tells us how many people have received the email, opened it, and clicked on embedded links. Topics for E-news have included data update announcements, sharing newly developed communications materials, and highlighting upcoming TAG and community events.
Project 11- Utilize social media at least quarterly for EPHT outreach
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Florida has continued to work with state agency communications staff to have items posted to social media, using Department level accounts. The goal is increased impact of social media reach (e.g. more views of YouTube videos from EPHT and more website traffic to EPHT portal). Florida EPHT has worked on inforgraphics and other materials that can be featured on Facebook, Instagram, and Pinterest. | EPHT has maintained an excellent working relationship with the Department's lead graphic designer to better coordinate the creation of outreach materials that also meet the Department's standards. This allows county health departments to implement the materials without having to obtain additional routing approval. There was turnover in our social media coordinator position, and EPHT is still working to understand the expectations of the new individual responsible for posting agency updates.
Project 12- Provide EPHT presentations to internal and external audiences
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| In Year 04, Florida has continued to look for opportunities to present Tracking Program information, including health trainings, virtual fairs, university lectures, and other events, to include at least one external audience every year. Florida is scheduled to present to external audiences, including students in the public health field, county health departments, and GIS practitioners. The goal is better awareness of EPHT principles and adoption of EPHT strategies for addressing environmental health problems (and also to obtain buy-in from external stakeholders). | The pandemic made it much harder to reach audiences with EPHT presentations. However, Chris DuClos did present on mapping chronic disease rates during the NACDD virtual conference in mid-2020. Jessi Joiner met with a public health student from the University of Florida as part of a class assignment interview discussing job roles in environmental public health. Jessi Joiner presented to students at the University of Miami on GIS Day, Novemeber 18, 2020.
Project 13-Develop and implement partnership plan
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| During Year 04, Florida EPHT updated and maintained our list of partners. These partnerships are critical to the success of the EPHT Program in Florida. Our list of partners includes: Florida Asthma Program (CDC funded), Florida Birth Defects Registry (partially CDC funded), Florida Cancer Data System (partial), CO Poisoning Program, Radon Program, University of Miami, Florida State University, University of South Florida, Bureau of Epidemiology, Bureau of Vital Statistics, Bureau of Chronic Disease, American Lung Association, American Cancer Society, Florida Public Health Association, Florida Rural Health Association, and Florida Environmental Health Association. | Most of these partners attend our TAG Meetings. For example, in January 2021, the TAG member from the Florida cancer registry attended our webinar and provided valuable feedback on the visualization of our sub-county data displays.
Project 14-Maintain a Technical Advisory Group to inform Tracking Program decisions
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Florida has had an active TAG for many years, and will continue to meet with them and inform them about data, analysis, messaging, metadata, etc. at least once per year. In the past, TAG meetings have been held at least once a year. The goal of this activity is to maintain a TAG that provides broad-based input on EPHT program activities, using a variety of perspectives. | Florida held a TAG meeting during Year 04, in January 2021.
Project 15- Establish and maintain collaborative relationship with at least one university
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Florida has continued to work with universities that have an interest in environmental health by collaborating with guest lectures, student mentoring, presentations, and peer reviewed journal articles. More specifically, Florida has worked with the University of Miami, Florida State University, and the University of South Florida. The goal is to establish a greater awareness of EPHT data and methods in the academic community, leading to greater use of EPHT resources by students and researchers. | Meetings were held with university partners during Year 04.
Project 16- Support training of public health workforce on basic Tracking principles
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Introductory EPHT training courses are available on our state portal at www.fltracking.com/healthtracking/learning.htm. In Year 04, Florida has continued to work with stakeholder organizations to provide training classes at workshops and annual meetings (e.g. Florida Public Health Association). Florida also mentored graduate students with an interest in Environmental Health. Florida has provided presentations for the Florida Public Health Association, Florida Environmental Health Association, and the Florida Rural Health Association. | The goal of this activity is to hold training classes and/or webinars to educate stakeholders on the Tracking Program, which will lead to greater awareness of the principles of EPHT. This was made more difficult during the pandemic, with several statewide conferences cancelled or postponed. The Program Manager (Jessica Joiner) continues to be very active in the Florida Environmental Health Association.
Project 17-Document and submit Public Health Actions quarterly
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Florida has continued to work with local and state partners to document public health actions that were enabled by EPHT data and tools, and report to CDC at least twice a year or quarterly if possible. Florida has submitted PHAs through the Public Health Actions Report (PHAR) to CDC for many years. The goal of these PHAR Reports is the documentation of interventions and success stores that can be used by CDC to show the value of Tracking. Greater feedback from CDC on the quality of PHAs is much appreciated.
Project 18- Assist the CDC Tracking Program in conducting performance evaluation
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| In Year 04, Florida continued to refine our existing annual evaluation plan based on the CDC framework and input from state and local partners. Florida has continued to work with CDC to clarify accomplishments and quantify impacts of program efforts. Our state evaluation plan has been updated annually for the last several years. Updating and implementing this evaluation plan has led to more effective use of resources and quantification of program impacts. | During Year 04, the project officer for Florida EPHT conducted a portal evaluation at floridatracking.com, and improvements were made to the data and user interface as a result of this feedback.
Project 19-Assist the State Health Department with GIS Services for COVID-19
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| In Year 04, Florida EPHT staff volunteered to work on the COVID19 GIS mapping dashboard and helped handle the huge volume of emails being received from the public. This project allowed for better information dissemination to concerned Florida residents. During this pandemic, Florida EPHT staff worked to answer questions from Florida residents and visitors about COVID19 and mapping trends. | Jessica Joiner and Chris DuClos were the primary EPHT staff members to work on the dashboard.

## Work Plan
EH17-1702 Budget Period: |  |  | August 1, 2020 - July 31, 2021
Date Submitted:
No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activity description. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project. | Continuation Report (Section I)
Project Title | Activity Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline | Status | Successes | Challenges | CDC Program Support Needed
Update and maintain NCDMs on state portal |  | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Participate in workgroup discussion and reach out to data owners to assess strengths and limitations of data to be included on state portal. ICD9 to ICD10 transition required input from several partners. COPD data for 2018 currently under further review with CDC assistance. |  |  | Q1-Q4 | In Progress | Messaging for the ICD9 to ICD10 transition is now included on the state portal | Asthma and COPD numbers/rates changed significantly from 2014 to 2016. COPD saw an unexplained drop for 2018 and 2019. | The PI for Florida EPHT (Chris DuClos) has been corresponding with the data and science teams at CDC about the unusual drop in COPD counts/rates for the year 2018, which also shows up in 2019.
|  | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Work with Lead Poisoning prevention program has resulted in 2013-2018 lead data being available on the state portal. Work with Bureau of EH Water staff on geographic boundaries for public water systems continues. |  |  | Q1-Q4 | In Progress | Productive meetings were held with Florida CLPPP (Lead) program and Florida DEP Drinking Water program staff | Lead data has finally caught up, as state surveillance partners finished their QI efforts; Public water system Boundary mapping is still ongoing, added Centroid Points this year | Have states (other than California) been successful in getting drinking water stewards to update their service delivery areas? Examples of large systems with multiple drinking water plants would be helpful.
|  | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Ensure that all NCDMs remain updated on the EPHT portal, submit required data sets to CDC twice a year, and allow for NCDM download |  |  | Q2-Q4 | In Progress | All NCDMs have been updated, including lead poisoning | Childhood lead poisoning measures went through extensive QI review | Portal review feedback from CDC will be helpful to ensure that all NCDMs are properly displayed, with relevant metadata
|  | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Florida EPHT developed new language about the ICD9 to ICD10 transition for NCDMs. Florida has also developed life expectancy messaging and updated community access measures, which are displayed in EH profile reports. Limitations of population denominators for rate calculations were added to chart and table footers. |  |  | Q3-Q4 | Complete | UMASS Population Data added to public portal; Documentation connected to metadata records | UMASS data contains some outlier estimates at both the census tract and ZIP Code level. | None at this time
Update jurisdictional priority measures on state portal |  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs, or other agreed-upon standards. Florida EPHT has developed built environment measures and community health profiles to address state and community level priorities (e.g. Healthy Weight). |  |  | Q1-Q4 | Complete | Life Expectancy data (5-year estimates) have been added to the state EPHT portal, and community access meausres reflect 2019 estimates | The user interface to access Life Expectancy data (and other measures) is not ideal. Implementing sub-county denominators is now complete for ZIP Codes. | Florida is one of the states that contracted with UMASS to produce sub-county population estimates. It would be helpful to see how these estimates compare to those available to CDC from other sources.
|  | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Work with Bureau of Environmental Health to improve messaging of safe fish consumption and low mercury levels. Improve presentation of fish advisory materials on EH webpage. Publish and distribute updated Healthy Fish cookbook on state EPHT portal. Work on infographics for Harmful Algal Blooms, Beat the Heat, and Blue Green Algae in English, Spanish, and Haitian Creole. |  |  | Q1-Q2 | Complete | Beat the Heat, Red Tide, and Blue Green Algae Infographics are in development. Beat the Heat is almost ready - undergoing translation at this time | Because the EPHT program no longer has our own social media presence, we have to rely on the larger DOH accounts to publicize resources like the new cookbook | None at this time
Work with content workgroup to adopt newly proposed NCDMs |  | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Serve on state and national workgroups to discuss utility of existing NCDMs, determine the format of new NCDMs, and discuss with Content WG how to best display and present data. |  |  | Q1-Q4 | Complete | Florida staff are currently serving on 12 EPHT workgroups with CDC staff and other grantees | Keeping up with all of the Workgroup calls can sometimes be challenging; | None at this time
|  | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Work with Radon and Indoor Air Program to address deficiencies in current risk maps for Radon potential (exposures). Collaborate with Florida Geological Survey on creating better risk map surface. Integrate weather (temperature/heat index) data into public portal. |  |  | Q1-Q4 | In Progress | Productive meetings were held with the TAG group and the Florida BRACE Program at FSU, to discuss climate data. | The volume of data for these indicators has proved a bit challenging to manage/query. The number of indicatos may be reduced by better customization features. | None at this time
Complete routine analyses of Tracking data to look for patterns |  | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | EPHT Epidemiologists have developed an analysis plan that includes an evaluation of completeness and data quality. Use of the analysis plan leads to reports for all stakeholders. |  |  | Q1-Q4 | Complete | Florida EPHT have worked with multiple university partners on Epidemiological analyses | When multiple IRB approvals are required, the timing of projects can sometimes be an issue | Please provide a central place where EPHT grantees can see all of the journal articles published by CDC and other states, esp. those articles that featured EPHT data
|  | Science and Content 2 (SC2) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Work with Bureau of Epidemiology to understand the spatial distribution and exposure risk factors for Carbon Monoxide Poisoning after extended power outages due to hurricane damage. Collaborate with Epi staff and EH scientists to improve the public health messaging around the use of portable electric generators (a major CO Poisoning hazard). Work with local health departments to determine accessibility of community mental health resources after disasters (CASPER). Dissiminate CASPER findings through a peer-reviewed journal (Journal of Public Health Management and Practice), which was accepted for publication in early 2021. |  |  | Q2-Q4 | Complete | CASPER findings were accepted for publication through a peer-reviewed journal (Journal of Public Health Management and Practice), in early 2021. Focus on hurricane response and recovery efforts. | There is no statewide law mandating that CO alarms be purchased or used with portable generators; There is also no statewide law stating that generators have to be at least 20 feet from any structure. Mental health questions were not easy to administer during the CASPER process. | None at this time
|  | Science and Content 2 (SC2) | SC1.D Disseminate additional indicators & measures to address grantee priorities | EPHT collaborated with the FDOH Division of Public Health Statistics and Performance Management to create the Chronic Disease Risk Factor mapping application, a resource illustrating county and sub-county variability of chronic conditions and related factors that may increase the risk of severe illness from COVID-19. |  |  | Q1-Q2 | Complete | Chronic Disease Risk Factor mapping application was a success and has been requested to update the existing data measures for continued use. A GIS Snapshot article has been submitted to CDC's Preventing Chronic Disease journal detailing the creation and use of the mapping application. KY EPHT has reached out for collaboration on their own measures for a related mapping application. | Data availability and staff responsibilities have slowed down the planned data update. | None at this time
|  | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | Gap analysis is being conducted as part of an evaluation of current portal strategies and technologies. The Florida EPHT Web Application Developer completes Application Status Reports every year to document/improve current technology and to suggest new approaches for issues like searching, keyword management, web analytics, and code troubleshooting. |  |  | Q1-Q4 | In Progress | Performance gaps were identified and corrected by IT staff. Additional refinements to stored procedures have been documented by EPHT database manager. | Our chart interfaces probably need a refresh. We need to do a better job of anticipating user needs as they explore the public portal. | Understanding the database logic used by CDC could be helpful for our state Database Manager (John Folsom).
Maintain public EPHT portal that complies with CDC requirements |  | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements | Portal has been available since 2009. Major redesign completed in 2016. Almost no down time in 2017-2020 (servers are still reliable). |  |  | Q1-Q4 | Complete | Portal performance has been improved by modifying default selections to only the latest year (as opposed to all years of data) | The user interface (selection tree) needs to be modified to provide a smoother experience for portal visitors; Making these changes while keeping up with data updates has been a real challenge | None at this time
Develop tools and processes to improve data quality |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Florida EPHT Database Manager has created stored procedures, transformation routines, and other SQL Server objects to improve the data flow and robust storage of EPHT data. |  |  | Q1-Q4 | In Progress | Population (denominator) data/estimates from the University of Massachusetts implemented at the tract level. ZIP Code rolling out as well. | Changing the UMASS code from STATA software into SQL Server code required the help of some database staff from Vital Stats | Is there an update on the University of Minnesota population estimates? Florida EPHT is curious how they look in comparison to UMASS, for our state
|  | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | The Florida EPHT Database Manager and Web Application Developer attend IT workgroup meetings for agency standards, change management, and server updates. |  |  | Q1-Q4 | Complete | Five new builds of our EPHT portal were rolled out during this grant year | IT staff turnover (e.g. for server maintenance) is always an issue, but we have worked around it | None at this time
Maintain the technology infrastructure for submitting NCDMs during data calls |  | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Two Florida EPHT staff members always maintain SAMS credentials for Secure File Uploads. Florida routinely evaluates metadata creation and validation requirements. Florida EPHT continues to use XML Spy software for data validation efforts. |  |  | Q1-Q4 | Complete | Data submissions continue to be completed on time by Florida EPHT database manager | As data stewards improve data quality, we sometimes need to resubmit data for multiple years; Radon data may be next for this type of refresh/resubmission | Are there any plans to ask for tract-level Vital Statistics data from EPHT grantees? Are there any plans to allow states to submit subcounty ZIP Code data (e.g. for Hosp/ED)? Florida does not have address level data in order to provide census tracts for Hosp/ED
Establish electronic access to data sources |  | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | The Florida EPHT Database Manager documents process improvement through metadata in SQL Server. The result should be repeatable and reliable routines for addressing sub-county data analysis needs. |  |  | Q1-Q3 | Complete | Florida Vital Statistics records are available at the tract level; this has been an existing policy for many years | Address level data is not available for Hospitalization and ED data, by State Rule. Therefore, the data can't be geocoded to the census tract level for these data sets. | Is there a list of how many states have census tract level Hosp/ED data? How many of these states participated in the sub-county data call with CDC?
Increase data management efficiency |  | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Data transformations will be conducted and documented using either SSIS script packages or SAS code, many of which were developed by the content workgroup teams, Programming for use of API can be implemented with the assistance of our web application developer. |  |  | Q1-Q4 | Complete | Data transformation packages are documented at a high level of detail within SQL Server | Finding the time to access data from the Tracking API has been difficult | None at this time
Develop and implement annual communications plan |  | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Florida EPHT participates in Tracking Awareness Week and has collaborated with their regional PMO group to plan and create outreach materials for quarterly topics. Also participated in Children's Week at the State Capitol. |  |  | Q1-Q4 | Complete | Children's Week was a success, with thousands of people in attendance | Tabling was done with three people, which was very useful for helping kids with games and handing out materials. | None at this time
|  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | The Florida Communications and Outreach Plan includes dissemination strategies for messages and products. Hardcopy and electronic materials are distributed (e.g. Infographics) at appropriate venues, such as Children's Week, professional conferences, and community events. |  |  | Q1-Q4 | In Progress | Hardcopy outreach materials have been shipped to multiple County Health Departments and other stakeholders | Printing budget for this year was still underestimated, and required a minor redirection of funds | Is there a central library of infographics and other hardcopy materials produced by the national and state EPHT programs? Sounds like a good student project!
|  | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity | Florida is working on extreme heat messaging with other states. We’re hoping to get KY, LA, and FL DOH social media accounts to tag each other and post messaging around the same time to create a greater reach on social media. |  |  | Q1-Q4 | Complete | Heat messaging will be sent to social media manager before the summer season | Printing budget for this year was still underestimated, and required a minor redirection of funds | None at this time
|  | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | This is one of the Advanced Activities, and Florida has not yet completed it. However, the planning for this activity will continue at our TAG Meeting in 2021. |  |  | Q1-Q4 | In Progress | Feedback was received from state TAG partners and local stakeholders about the need for sub-county messaging | TAG Webinar and in-person meeting was held January 26, 2021. Turnover of staff in Health Communications Specialist position has caused delays in the project. | Are there good examples of sub-county data messaging and dissemination? How do public health agencies inform communities about trends in data like Life Expectancy?
Provide regular updates about tracking activities to partners via email |  | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | The Florida EPHT Health Communications Specialist sends out quarterly E-newsletter to state stakeholders. |  |  | Q1-Q4 | In Progress | Diane Niedhart has been doing an excellent job of creating and disseminating our quarterly newsletters to hundreds of recipients. The number of opens have increased, and the number of bounced emails have been reduced by verifying email addresses. | Turnover of staff in Health Communications position has results in some delays on content updates. | None at this time
Utilize social media at least quarterly for EHPT outreach |  | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Florida EPHT works with our DOH Office of Communications to post quarterly messages through the agency's social media accounts on FB, Twitter, and Pinterest. These messages are tailored to observance months (e.g. Asthma Awareness Month). |  |  | Q1-Q4 | Complete | Florida EPHT has sent multiple posts to the DOH Communications office, social media manager | Our EPHT posts compete with multiple public health observances, so they don't always get posted | How many followers do the national EPHT accounts have on social media?
Provide EPHT presentations to internal and external audiences |  | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | Florida EPHT routinely exhibits at state events such as the Florida Asthma Coalition and presents at national meetings such as NEHA/CSTE. Florida also conducts webinars routinely, such as the one given to University of South Florida students in October 2019. Jessi Joiner presented on the FDOH COVID19 Dashboard at the 2020 GIS Symposium for the University of Miami on November 18. |  |  | Q1-Q4 | Complete | The Florida EPHT Principal Investigator gave an HIA presentation to the national NEHA webinar audience | TAG Webinar originally scheduled for 10/10/18 had to be postponed due to Hurricane Michael; Rescheduled for May 2019. TAG Meeting held 1/28/21 with about 30 partners in attendance. | None at this time
|  | Communications 2 (C2) | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner | Florida has worked with the Florida Rural Health Association to highlight EPHT data and its relevance to the rural communities. Chris DuClos submitted abstract for NEHA EPHT Tools of the Trade. Jessi Joiner submitted an abstract on a national EPHT pilot project for the CSTE Environmental Health track. Jessi also presented to the FSU public health student association. |  |  | Q2-Q3 | Complete | Presentation was attended by dozens, with a portal demo given on new features and data. | Travel support has been an issue for people to attend statewide meetings. Travel bans were enacted after the hurricanes, and they have yet to be fully lifted. Coronvirus has presented new travel challenges and resulted in the cancellation of in-state and national conferences where EPHT usually presents. | None at this time
|  | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | This is one of the Advanced Activities, and Florida has not yet completed it. However, one of our projects was featured in local newspapers and TV (life expectancy). |  |  | Q1-Q4 | In Progress | Life expectancy projects have captured significant media attention | All media contacts are centrally managed by our agency's Office of Communications. Chris DuClos has talked to media persons about climate and health. | None at this time
Develop and implement partnership plan |  | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Florida EPHT is working to update our collaboration plan to include new/innovative external partners, such as the Florida Department of Transportation |  |  | Q3-Q4 | In Progress | New partnerships developed with Department of Transportation, and non-motorized traffic monitoring (walkability) | Diane Neidhart is working to foster new partnerships, but it is difficult during the pandemic. | None at this time
Maintain a Technical Advisory Group to inform Tracking Program decisions |  | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Florida EPHT has maintained the state Technical Advisory Group for many years. The latest TAG meeting was held January 28, 2021. |  |  | Q1-Q4 | Complete | State TAG have over 50 members, from local and state agencies/nonprofits. | January 2021 TAG Meeting featured data indicator interests/gaps, new communications products, and population denominator limitations and feedback. | None at this time
Establish and maintain collaborative relationship with at least one university |  | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Florida EPHT has relationships with Florida State University (GIS and geocoding), the University of Miami (Developmental Disability linkage) and the University of South Florida (Birth Defects). |  |  | Q1-Q4 | Complete | University partnerships are thriving, with multiple projects in walkability, economic hardship index, life expectancy, birth defects, etc. | The budget and timing of projects can sometimes be a challenge, and working around student schedules can be an issue | Is there a list of all university projects completed by other grantees?
Support training of public health workforce on basic Tracking principles |  | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Florida provides training at statewide meetings, including the Florida Rural Health Association conference and the Florida Environmental Health Association statewide workshop. |  |  | Q1-Q4 | Complete | Florida presents at statewide conferences, including the Florida Rural Health Association and Florida Environmental Health Association | Travel support has been an issue for people to attend statewide meetings. Travel bans were enacted after the hurricanes and yet to be fully rescinded. Coronavirus restrictions resulted in many in-person events being canceled or postponed. | None at this time
|  | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Florida distributes training resources online, including introductions to basic Tracking principles. The 3 modules of training previously on the state portal at https://www.floridatracking.com/healthtracking/learning.htm had to be discontinued as support for FLASH technology was dropped |  |  | Q3-Q4 | Complete | EPHT Training courses are available on the state portal at https://www.floridatracking.com/healthtracking/learning.htm | The older format of these training videos does not work well with Google Chrome. IE, Edge, and Firefox appear to work fine. Source files were obtained to try and update the formats. | None at this time
|  | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Florida is in the process of updating our training plan to identify and prioritize the needs of Tracking stakeholders in order to provide more resources and training |  |  | Q1-Q4 | In Progress | EPHT Technical (IT) meeting is held every Thursday to cover the needs for data updates and portal management | We are maintaining a web-based data query system with hundreds of data points (from multiple agencies) with only 2 IT staff members | Can CDC share an example of a document that shows a grantee's ranked needs?
Document and submit Public Health Actions quarterly |  | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Florida completes the Public Health Action Report template each quarter and submits to our project officer. |  |  | Q1-Q4 | Complete | PHAs have been submitted quarterly to our project officer. The number submitted is usually 2-5. | Getting PHAs approved by CDC is challenging. Since EPHT is primarily a data dissemination program, finding the people who are using our data can sometimes be a challenge. | Please forward the full list of accepted PHAs again
Assist the CDC Tracking Program in conducting performance evaluation |  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Florida has maintained a CDC-funded EPHT Program since 2003. Florida currently funds 8 FTE positions with EPHT funding. |  |  | Q1-Q4 | Complete | EPHT Program is still funded, and housed in the Division of Community Health Promotion | Our state budget awarded from CDC has dropped a bit the last few years. | Does CDC know if full funding can be restored?
|  | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Florida completed evaluation metrics as part of the PMT spreadsheet. |  |  | Q2-Q3 | Complete | Evaluation plan updated | The new Excel template will take some time to get used to, as part of the APR Continuation | None at this time
|  | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | Florida completes the Program Evaluation Module as needed and is in compliance with all portal requirements. |  |  | Q1-Q4 | Complete | Portal review completed by Bob Kennedy in 2021. Florida updated some data sets and metadata and should now adhere to all of the portal standards. | The user interface (selection tree) needs to be modified to provide a smoother experience for portal visitors; Making these changes while keeping up with data updates has been a real challenge | None at this time
|  | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | Florida uses Google Analytics to collect statistics on our state portal. Florida is aware of the web analytics requirements and has produced reports to meet CDC standards. |  |  | Q1-Q4 | Complete | Google Analytics are exported weekly and combined into spreadsheet several times a year. | Web analytics were sent up to CDC in 2020 | None at this time

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year