## Instructions
  Instructions
  Purpose of the Template
  Please use this workbook to document your Budget Year 5 Work Plan and Project Narrative as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section II of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)."
  This workbook includes tabs containing the finalized EH17-1702 Logic Model (blue tab), EH1702 Strategies & Activities (yellow tab) for reference, Project Narrative (purple tab) to provide greater detail regarding your planned projects, and the standardized Work Plan template (green tab). The only tabs which you should fill out are the Project Narrative tab and the Work Plan tab.
Filling out the Project Narrative tab:
  Required Reporting: Use the Project Narrative tab to provide details on how each project outlined in your work plan correspond to the specific strategies, activities, and tasks listed. In the Project Summary section, please provide an overview of the project; be sure to adhere to the 200 word limit for this section. There are no limits on the number of projects proposed. Please keep in mind that some of these projects may be an extension of the project proposed and approved in Budget Year 1 or 2 (i.e. initial EH17-1702 application). The planned projects must support the intent of the original EH17-1702 Notice of Funding Opportunity (NOFO).
  Optional Reporting: Use the right-hand side of each project area (Activity Description) to provide additional details which may not be captured in the work plan or in the project summary section. There is no word limit for this section. You may note comments pertaining to budgetary issues that might hamper the success or completion of the project as originally proposed and approved in Budget Year 1.
Filling out the Work Plan tab:
1. Project Title Create a short title for your project, no more than ten words. Examples include “Asthma Prevention”, “Improving Outdoor Air Quality,” "Improving Portal Infrastructure," "Expanding University Partnerships," etc. You may repeat the same project title in subsequent rows depending on the number of supporting strategies and activities for that project, or combine rows in that column to include the same title. You will provide a detailed description of each project on the Project Narrative tab.
2. Strategy Select a strategy from the drop-down list. Each project should fall into one primary strategy. While you can select supporting strategies and activities related to that primary strategy (ex. A Communications strategy/activity supporting the primary Science strategy/activity for that project), the first strategy you select will be the main focus of your project.
3. Activity Select an activity from the drop-down list. The activity should relate to the strategy you previously selected for that project. Each project should list at least two activities to be implemented in the budget year.
4. Activity Description In five sentences or less, describe the activity you are implementing in Column E.
5. Output Select a prospective output from the drop-down list. You may select one output per activity, or one overall output for the project. If you select multiple outputs for the project, you may find not all activities will correspond with an output.
6. Short-Term Outcome Select a prospective short-term outcome from the dropdown list. You may select one outcome per activity, or one outcome overall for the project.
7. Timeline Select when the specific activity will be accomplished from the drop-down list. Options include Quarter 1 (Q1) through Quarter 4 (Q4), meaning the activity will be accompished at the end of the budget year, or a specific time period (ex. Q1, Q2) .
Technical Support
If you need technical support when using this template, email your project officer.
            EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
      EH17-1702 Annual Performance Report (APR) - Section II only
      Budget Period: August 1, 2021 - July 31, 2022 (Budget Year 5)
      Reporting Period: August 1, 2021 - July 31, 2022

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
Iowa Department of Public Health Project Narrative Budget Year 5
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan" (green tab). Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
SCIENCE AND CONTENT | Project 1- Portal Data and Measure Maintenance
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| This project is an ongoing annual set of activities directed at the maintenance and update of existing data and measures as additional years of data are published on the Iowa Tracking Portal. Specific activities within this project target Science and Content, and Communications strategies and outcomes. Grantee has an established portal update schedule for the publication of new and updated content. The availability of a new and updated content is then promoted through multiple channels. |  | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 5
|  |  | 11 | 4 | 2 | 3 | 20
Project 2- Annual Data Load
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is an ongoing annual set of activities directed at the maintenance and update of existing data and measures as additional years of data are collected and released by the data owner/steward. Specific activities within this project target Science and Content strategies and outcomes. Grantee has an established data load schedule for the major datasets based on anticipated release schedules. As new years of data are received the data are appended to prior year’s data and descriptive summaries are generated to assist with validation and quality assurance. Following validation the published data visualizations are updated to include the new year of data at the next quarterly portal update.
TECHNOLOGY AND INFORMATICS
Project 3- Data Call Participation
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is an ongoing annual set of activities directed at the ongoing submission of Tracking data flows from the grantee. Specific activities within this project target Science and Content, and Technology and Informatics strategies and outcomes. Grantee will maintain active accounts and expertise in the systems and tools needed to submit data to CDC, and will complete fall and spring data submissions during the scheduled time frames.
COMMUNICATIONS
Project 4- Portal Technical Maintenance
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is an ongoing annual set of activities directed at maintaining the compliant operation of the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Communications, and Program Services strategies and outcomes. Grantee maintains an Iowa Tracking Portal compliant with the "Tracking Grantee Portal Requirements and Recommendations". Maintenance activities include the collection and monitoring of website function and use metrics, a rotating review of content and messaging, and collaboration with the University of Iowa to develop additional messaging components.
Project 5- Portal Promotion
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project includes new and recurring annual activities directed at the promotion of the Tracking Network. Specific activities within the project target the Communications and Program Services strategies and outcomes. Activities will include participation in national and regional coordinated campaigns, and participation as an exhibitor at state conferences.
PROGRAM SERVICES
Project 6- Partner and Network Engagement
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project includes new and recurring annual activities directed at sustaining the Tracking Network in Iowa through engagement with partners, communications, and professional development; and align Tracking needs and priorities with organizational strategic and capacity planning. Specific activities within this project target Science and Content, Technology and Informatics, Communications, and Program Services strategies and outcomes. Grantee will update and implement partnership and communications plans to promote and expand Tracking in Iowa. Beyond the administrative tasks related to partnership and communications; efforts under this project also serve to meet participation with National EPHT workgroups and the continued evaluation of the Iowa Tracking portal; and ensure representation by Tracking in regular meetings with Department Leadership, Information Management, and Data Management is the primary mechanism to accomplish integration with the Department Strategic Planning Process.
Project 7- Training and Capacity Building
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project includes new and recurring annual activities directed at the development and conduct of training opportunities. Specific activities within the project target the Communications and Program Services strategies and outcomes. Activities will include the delivery of both in-person and online training to support use of the Tracking Portal.
Project 8- Monitor Performance of Program Activities
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project includes new and ongoing annual activities directed at the monitoring and evaluation of the program through administrative reporting to CDC. Specific activities within this project target the Program Services strategies and outcomes. The use of CDC provided forms and templates will be used to report Public Health Actions, evaluation metrics, and portal statistics.
Project 9- Substance Use Morbidity Measures
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project was first identified in a previous work plan but was deprioritized by the initiating program as other Substance Use data and measures were developed, but remains a target for inclusion on the portal. This project is directed at the development and incorporation of state specific substance use morbidity measures for display on the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee will collaborate with the substance abuse program to define state specific measures and extract and transform the exisiting Hospital and ED discharge data for use on the Iowa Tracking Portal, and the establishment of standard descriptive summaries for use in validating the data. Messaging and content for the substance use morbidity measures will be developed and promoted through multiple channels.
Project 10- Prescription Monitoring Measures
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is an expansion of the successful publication of Opioid and other controlled substance prescription measures. This project is directed at the development and incorporation of additional state specific prescription monitoring measures for display on the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee will collaborate with the substance abuse program to define state specific measures and extract and transform the exisiting prescription monitoring program data for use on the Iowa Tracking Portal, and the establishment of standard descriptive summaries for use in validating the data. Messaging and content for the substance use morbidity measures will be developed and promoted through multiple channels.
Project 11- Extreme Cold Morbidity Measures
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is a continuation of a project first identified in Year 3, the project continues to be developed as part of a CWG team. This project is directed at the development and incorporation of the optional NCDM extreme cold measures for display on the Iowa Tracking Portal. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee will utilize the optional NCDM documentation for extreme cold measures to extract and transform the exisiting Hospital and ED discharge data for use on the Iowa Tracking Portal, and the establishment of standard descriptive summaries for use in validating the data. Messaging and content for the extreme cold measures will be developed and promoted through multiple channels.
Project 12- Immunization Profile
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is a continuation of a project first identified in Year 3, and postponed from the Year 4 work plan due to the COVID-19 Pandemic Response. This project is directed at the development of immunization profile reports for display on the Iowa Tracking portal. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. Grantee will collaborate with the immunization program to develop a composite data connection to support a county based snapshot of multiple measures, and the development of a standard letter size Immunization profile visual for use on the Iowa portal. Messaging and content for the new Immunization profile will be developed and promoted through multiple channels.
Project 13- Public Water WIIN Data
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project was first identified in the Year 4 work plan, but was postponed due to the COVID-19 Pandemic Response. This project is directed at the incorporation of data collected in Iowa as part of the Water Infrastructure Improvements for the Nation Act. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. Grantee will collaborate with Iowa DNR share data, develop data visualizations, and messaging.
Project 14- Implement Geocoding Processes
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is the evolution of the previous geocoding standards projects, which adopted the EPHT geocoding standards, but was unable to establish a geocoding process due to staff turn over in information management and the COVID-19 Pandemic response. This project is directed at the establishment of a geocoding process for Tracking data that includes address information within the Iowa Department of Public Health. Specific activities within this project target the Science and Content, and Technology and Informatics strategies and outcomes. Grantee will coordinate with the data management and information management programs to a geocoding process for department data sets that already include address information. Emphasis will be on developing a geodatabase infrastructure that would support efforts to geocode data.
Project 15- Sub-County Asthma Evaluation
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project was first identified in the Year 4 work plan, but was delayed pending the establishment of a geocoding process. This project is directed at the development of a routine analysis to discovery spatial and demographic patterns in Asthma Hospitalizations data for dissemination to local health departments. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. The implementation of the geocoding process will allow the grantee to pursue more advanced analysis of existing data sets. The analysis of Asthma Hospitalizations at a census tract level will be a pilot that can later be applied to other health outcomes. Emphasis will be on the creation of a report that incorporates this analysis together with interpretive messaging for local health departments to use as part of the Coummunity Health Needs Assessment process. Use of the report will be tracked and documented.
Project 16- Sub-County Private Well Evaluation
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project was first identified in the Year 4 work plan, but was postponed due to program staff vacancies and the COVID-19 Pandemic response. This project is directed at the development of a routine analysis to discovery spatial and demographic patterns in Private Well Water Testing data for dissemination to local health departments. Specific activities withing this project target the Science and Content, Technology and Informatics, and Communications strategies and outcomes. Private Well data already included the sub-county Township identifier, by adding this Township identifier as a display layer grantee will beable to conduct more advanced analysis at the Township level. Emphasis will be on the creation of a report that incorporates this analysis together with interpretive messaging for local health departments to use as part of the Coummunity Health Needs Assessment process. Use of the report will be tracked and documented.
Project 17- Seasonal Influenza Surveillance Report
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This project is the continuation of a project that was identified and added to the Year 4 work plan after the initial submission. This project is directed at the tracking and evaluation of impact associated with the data visualizations published to increase efficiency and timliness of data analysis and reporting for seasonal influenza. Visualizations include of updates to the Seasonal Influenza Surveillance report used internally and new visualizations targeted at the general public. Specific activities withing this project target the Technology and Informatics, Program Services, and Communications strategies and outcomes. Emphasis will be on documentation of impact from the completed project.
Project 18- Violent Death Reporting System Measures
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This is a new project identified for the Year 5 work plan directed at the development of state specific measures for display on the Iowa Tracking Portal from the Violent Death Reporting System. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee will collaborate with the injury prevention program to define state speific measure, integrate the Violent Death Reporting System (VDRS) data into the IDPH Tracking infrastructure, and extract and transform that data for use on the Iowa Tracking Portal. Messaging and content for the VDRS measures will be developed and promoted through multiple channels.
Project 19- Sexually Transmitted Infections Measures
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This is a new project identified for the Year 5 work plan directed at the development of additional state specific measures for display on the Iowa Tracking Portal from the Iowa Disease Surveillance System and STI Program data. Specific activities within this project target Technology and Informatics, Science and Content, and Communications strategies and outcomes. Grantee will collaborate with the STI program to define state speific measures, integrate program data into the IDPH Tracking infrastructure, and extract and transform that data for use on the Iowa Tracking Portal. Messaging and content for the STI measures will be developed and promoted through multiple channels. This project will expand on a previous project that developed the existing measures for Gonorrhea and Chlamydia on the Tracking Portal.
Project 20- Hospital Discharge Dataset Accessibility Quality Improvement
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
This is a new project identified for the Year 5 work plan directed at improving the accessibility of the Iowa Hospital Association Inpatient and Outpatient Discharge data housed within the IDPH. Specific activities within this project target Technology and Informatics strategies and outcomes. The Discharge data has been idetified as a target for a Quality Improvement project by the department focused on accessiblity of the data for use beyond the Iowa Public Health Tracking Portal. The emphasis will be on developing an efficient process for IDPH programs and external partners to access the discharge data. Recent organization changes and staff turnover has resulted in some institutional knowledge loss, and the identification of this Quality Improvement project.

## Work Plan
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Work Plan Template
EH17-1702 Budget Period: |  |  |  | August 1, 2021 - July 31, 2022
Date Submitted to CDC: |  |  |  | 2021-03-26
REFERENCE NOTES | No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activty description. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project.
| Project Title | Activity Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline
| Portal Data and Measure Maintenance | Winter Portal Update | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will publish new and updated data visualizations and content. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q2-Q4
|  | Winter Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published updates via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q2-Q4
|  | Winter Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published updates via Social Media channels. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q2-Q4
|  | Spring Portal Update | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will publish new and updated data visualizations and content. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4
|  | Spring Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published updates via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4
|  | Spring Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published updates via Social Media channels. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4
|  | Summer Portal Update | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will publish new and updated data visualizations and content. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2
|  | Summer Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published updates via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2
|  | Summer Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published updates via Social Media channels. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2
|  | Fall Portal Update | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will publish new and updated data visualizations and content. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3
|  | Fall Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published updates via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q3
|  | Fall Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published updates via Social Media channels. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q3
| Annual Data Load | Air Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the EPA Air Now data repository. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Air Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Climate Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Iowa State University Climate Science Program. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Climate Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Private Water Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the Private Well Tracking System data connection. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Private Water Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Public Water Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Iowa DNR. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Public Water Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Discharge Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Iowa Hospital Association. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Discharge Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | BD Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Iowa Registry of Congenital and Inherited Disorders. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
|  | BD Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
|  | Cancer Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the SEER program. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
|  | Cancer Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
|  | Lead Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the HHLPSS data connection. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Lead Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | ACS Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the American Communities Survay Data Download site. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Population Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the NCHS Bridged-race Population Estimates website. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Vital Records Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the Vital Records Program data connection. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Vital Records Data Validation | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Grantee will conduct descriptive analysis of the new year of data to support data validation and health equity evaluation. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | IDSS Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the Iowa Disease Surveillance System data connection. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
|  | IRIS Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will extract and load the most recent year of data from the Immunization Registry Information System data connection. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | PMP Data Load | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will procure and load the most recent year of data from the Board of Pharmacy. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
| Data Call Participation | Fall Required Flows | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will submit new years of data available for required data flows during the Fall Data Call. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2
|  | Fall Optional Flows | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will submit new years of data available for optional data flows during the Fall Data Call. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2
|  | Spring Required Flows | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will submit new years of data available for required data flows during the Spring Data Call. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3
|  | Spring Optional Flows | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Grantee will submit new years of data available for optional data flows during the Spring Data Call. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3
|  | Data Submission Accounts | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Grantee will maintain active accounts for SAMS and CDC Join. | TI- Comprehensive surveillance system w. tools, guides & best practices | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
| Portal Technical Maintenance | Portal Maintenance | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements | Grantee will use Siteimprove quality assurance reports to monitor the function and operation of the Iowa Tracking Portal. Weekly reports will be tracked and monitored to ensure consistent operation. | PS- Systematic approach to assessing program activities & overall performance | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Portal Review | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | Grantee will facilitate and assist CDC when conducting annual portal reviews. | PS- Systematic approach to assessing program activities & overall performance | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Webstats Submission | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | Grantee will collect and submit portal statistics using the reporting template provided by CDC. | PS- Systematic approach to assessing program activities & overall performance | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
| Portal Promotion | TAW Participation | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Grantee will participate in Tracking Awareness Week planning activities as part of the PMO group work. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | TAW Social Media | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate Tracking Awareness Week materials through Social Media. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Midwest PMO Participation | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity | Grantee will participate in efforts by the Midwest PMO group to develop coordinated outreach materials. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | PMO Winter Activity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate coordinated materials through Social Media. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2
|  | PMO Spring Activity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate coordinated materials through Social Media. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2
|  | PMO Summer Activity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate coordinated materials through Social Media. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q3
|  | PMO Fall Activity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will disseminate coordinated materials through Social Media. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Gov Conference Networking | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Grantee will network at the Iowa Governor's conference to engage potential partners. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q3
|  | Gov Conference Materials | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will distribute tracking communication products at Iowa Governor's conference. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q3
| Partner and Network Engagement | CWG Participation | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Grantee will participate on the Content Work Group bimonthly calls, and specific CWG teams as appropriate. Proposals for CWG activities will be developed, submitted, reviewed, and ranked when solicited. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | PI Forum Participation | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will participate on the PI Forum bimonthly calls. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | SND Participation | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will participate on the Standards and Network Development Group calls, and specific SND teams as appropriate. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | PMO Participation | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will participate on the Program Marketing and Outreach Group calls, and specific PMO teams as appropriate. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | Data Request Tracking | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will track and respond to requests for data not readily accessible on the tracking portal. | SC-Generated & disseminated env. Public health evidence | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  | Data Request Evaluation | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will evaluate requests for data not readily accessible on the tracking portal to identify and prioritize public health concerns and priorities. | SC-Generated & disseminated env. Public health evidence | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  | Partnership Plan | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Grantee will review and update the Partnership Plan. | PS- Systematic approach to assessing program activities & overall performance | Comm- Engaged partners & users | Q1-Q2
|  | External Partner Engagement | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Grantee will collaborate with the Data Management program to identify and engage external partners involved with the state specific content under development. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | TAG Engagement | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Grantee will engage the Tracking Advisory Group of existing partners in ongoing review and expansion of Iowa Tracking Portal. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | TAG Priority Review | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will engage the Tracking Advisory Group of existing partners to identify and prioritize public health concerns and priorities. | SC- Standardized & accessible env. & health surveillance data | Comm- Engaged partners & users | Q1-Q4
|  | University Collaboration | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Grantee wil maintain the existing relationship with the University of Iowa in support of the Iowa Tracking portal. Collaborative efforts are spread through the proposed projects. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | Media Collaboration | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | Grantee will coordinate with the department Public Information Officer to promote Tracking and the Tracking Portal through earned media. Media contacts with the Iowa Department of Public Health are established and maintained through the department Public Information Officer. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | National Presentation | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | Grantee will seek opportunities to present at national or regional conferences. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | National Co-Presentation | Communications 2 (C2) | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner | Grantee will seek opportunities to co-present with other grantees at national or regional conferences. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | Communications Plan | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Grantee will review and update the Communications Plan. | PS- Systematic approach to assessing program activities & overall performance | Comm- Engaged partners & users | Q1-Q2
|  | Tracking Priority Review | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will engage existing and new partners to maintain and enhance the influence of Tracking in Iowa through the proposed projects. | Comm- Partnerships w/ env. health stakeholders | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Staff Development | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Grantee will use departmental staff evaluation tools to identify staff capacity, resource, and training needs/opportunities. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Data Management Meetings | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will attend monthly meetings with Data Management to ensure alignment of objectives with public health concerns and priorities. | SC- Standardized & accessible env. & health surveillance data | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  | Executive Meetings | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will attend quarterly meetings with Department Leadership to ensure alignment of objectives with public health concerns and priorities. | SC- Standardized & accessible env. & health surveillance data | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  | IM Meetings | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | Grantee will coordinate with Information Management to Evaluate gaps or barriers to effective use of data. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
| Training and Capacity Building | Visualize This Training Scheduling | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Grantee will collaborate with the University of Iowa to schedule and conduct Data Visualization training sessions. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Visualize This Listserve | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of scheduled trainings via listserv. | Comm- Targeted comm. products & messages | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Visualize This Materials | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will distribute tracking communication products at Data Visualization training. | Comm- Targeted comm. products & messages | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q2
|  | Tackling Data Scheduling | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Grantee will collaborate with the University of Iowa to schedule and conduct Tackling Data training sessions. This is based on continued interest and demand from partners. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q2
|  | Tackling Data Listserv | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of scheduled trainings via listserv. | Comm- Targeted comm. products & messages | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q2
|  | Tackling Data Materials | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will distribute tracking communication products at Tackling Data training. | Comm- Targeted comm. products & messages | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q2
|  | Health Equity Training Development | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Grantee will collaborate with the U of I to develop a new training course that emphasizes how the portal can be used to meet Health Equity objectives. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Health Equity Training Scheduling | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Grantee will collaborate with the University of Iowa to schedule and conduct The new Health Equity training sessions. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Health Equity Training Listserve | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of scheduled trainings via listserv. | Comm- Targeted comm. products & messages | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Health Equity Training Materials | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will distribute tracking communication products at Health Equity training. | Comm- Targeted comm. products & messages | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Data COP Curriculum Development | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Grantee will coordinate with the Data and Informatics Community of Practice to include Tracking principles in the curriculum for training. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q2
|  | IDPH Data Day Materials | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will distribute tracking communication products at IDPH Data Day. | Comm- Targeted comm. products & messages | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q2
|  | Training Video Development | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Grantee will collaborate with the University of Iowa to develop video tutorials targeted at both the use of the Iowa Tracking Portal and the data and measures published. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Training Video Publishing | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Grantee will publish video tutorials on the department YouTube channel and link or embed on Iowa Tracking portal. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Training Video Promotion | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will include new tutorial videos in quarterly announcement of published updates via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
| Monitor Performance of Program Activities | Evaluation Plan | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Grantee will collect and submit Performance Metrics using the reporting template provided by CDC. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q3
|  | Winter PHAR | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will submit public health actions based on project results using the PHAR in the first quarter. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences. | Q1-Q2
|  | Spring PHAR | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will submit public health actions based on project results using the PHAR in the second quarter. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences. | Q1-Q2
|  | Summer PHAR | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will submit public health actions based on project results using the PHAR in the third quarter. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences. | Q2-Q3
|  | Fall PHAR | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will submit public health actions based on project results using the PHAR in the fourth quarter. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences. | Q3-Q4
|  | IM Meetings | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Grantee will attend monthly meetings with Information Management to ensure alignment of objectives. | TI- Comprehensive surveillance system w. tools, guides & best practices | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  | Executive Meetings | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Grantee will attend quarterly meetings with Department Leadershipto ensure alignment of objectives. | TI- Comprehensive surveillance system w. tools, guides & best practices | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
| Substance Use Morbidity Measures | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform Hospital and ED discharge data to generate Substance Use Morbidity measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Substance Use Morbidity measures from the Hospital and ED Discharge Data. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of Substance Use Morbidity measures. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of Substance Use Morbidity measures. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of Substance Use Morbidity measures. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the Substance Use Morbidity measures. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published Substance Use Morbidity measures via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published Substance Use Morbidity measures via Social Media channels. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
| Prescription Monitoring Measures | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform Prescription Monitoring Program Data data to generate Prescription Monitoring measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
|  | Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Prescription Monitoring measures from the Prescription Monitoring Program Data. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
|  | Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of Prescription Monitoring measures. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
|  | Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of Prescription Monitoring measures. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3
|  | Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of Prescription Monitoring measures. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3
|  | Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the Prescription Monitoring measures. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3
|  | Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published Prescription Monitoring measures via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q3
|  | Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published Prescription Monitoring measures via Social Media channels. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q3
| Extreme Cold Morbidity Measures | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform Hospital and ED discharge data to generate Extreme Cold Measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Extreme Cold Measures from the Hospital and ED Discharge Data. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of Extreme Cold Measures. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q2
|  | Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of Extreme Cold Optional NCDM. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2
|  | Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of Extreme Cold Optional NCDM. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2
|  | Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the Extreme Cold Optional NCDM documentation. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2
|  | Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published Extreme Cold Optional NCDM via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2
|  | Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published Extreme Cold Optional NCDM via Social Media channels. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2
| Immunization Profile | Measure Identification | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Grantee will collaborate with the immunization program to identify the measures to be included in a County level profile of immunization measures to assist in the Community Health Needs Assessment and Health Improvement Planning process. | SC-Generated & disseminated env. Public health evidence | SC- Health & Environmental data are accessed and used by internal/external audiences | Q1-Q3
|  | Profile Development | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will collaborate with the immunization program to design a County level profile of immunization measures to assist in the Community Health Needs Assessment and Health Improvement Planning process. | Comm- Targeted comm. products & messages | Comm- Engaged partners and users | Q1-Q3
|  | Data ETL | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of Immunization data for use in the Immunization profile. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible and higher quality display of data on public portal | Q1-Q3
|  | Content Development | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop an immunization profile report to assist in the Community Health Needs Assessment and Health Improvement Planning process. | Comm- Targeted comm. products & messages | SC- Health & Environmental data are accessed and used by internal/external audiences | Q1-Q3
|  | Profile Publishing | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will make the county level immunization profile available to local public health agencies. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Tracking Network and environmental health issues | Q1-Q3
|  | PHA Development | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will track use of the disseminated profile and work with users to demonstrate impact through Public Health Actions. | SC- Development of targeted jurisdiction specific program activities based on generated evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
| Public Water WIIN Data | Data Evaluation | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Grantee will coordinate with the Iowa DNR to evaluate the WIIN data to identify and derive measures and content for addition to the portal. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Data Integration | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Grantee will establish a data sharing agreement and coordinate with Information Management to integrate the WIIN data. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Data ETL | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform WIIN data to generate measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations based on WIIN data and measures. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
| Implement Geocoding Processes | Tool Evaluation | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will collaborate with Information Management to ensure the Melissa Address Lookup and Geocoding tool is meeting the needs and expectations of the EPHT standards. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Geodatabase Development | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will collaborate with Information Management to develop a geodatabase from the outputs of all address level geocoding conducted on department data sets to facilitate future geocoding efforts. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Geocoding Process | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will collaborate with Information Management to identify tools and processes to implement address level geocoding for appropriate data sets consistent with the adopted Geocoding Standards. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
| Sub-County Asthma Evaluation | Asthma Geocoding | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Grantee will geocode Asthma Hosp Discharge data to the census tract level. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Environmental data are accessed and used by internal/external audiences | Q1-Q4
|  | Sub-county Asthma Analysis | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Grantee will develop a script to analyze sub-county data to identify spatial and demographic patterns of asthma. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Environmental data are accessed and used by internal/external audiences | Q1-Q4
|  | Sub-County Asthma Visualization | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop a visualization of the sub-county data that highlights patterns and inequities identified. | SC- Development of targeted jurisdiction specific program activities based on generated evidence | SC- Health & Environmental data are accessed and used by internal/external audiences | Q1-Q4
|  | Sub-County Asthma Report | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will integrate the visualization into a report template to assist in the Community Health Needs Assessment and Health Improvement Planning process. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Tracking Network and environmental health issues | Q1-Q4
|  | Sub-County Asthma Evaluation | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will track use of the disseminated report and work with users to demonstrate impact through Public Health Actions. | SC- Development of targeted jurisdiction specific program activities based on generated evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
| Sub-County Private Well Evaluation | Sub-County Private Water Township Join | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will procure and integrate a shapefile and geodatabase that represents the Township level of sub-county data. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Environmental data are accessed and used by internal/external audiences | Q1-Q4
|  | Private Water Township Analysis | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Grantee will develop a script to analyze sub-county data to identify spatial and demographic patterns of private well testing. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Environmental data are accessed and used by internal/external audiences | Q1-Q4
|  | Private Water Township Visualization | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop a visualization of the sub-county data that highlights patterns and inequities identified. | SC- Development of targeted jurisdiction specific program activities based on generated evidence | SC- Health & Environmental data are accessed and used by internal/external audiences | Q1-Q4
|  | Private Water Township Report | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Grantee will integrate the visualization into a report template to assist in the Community Health Needs Assessment and Health Improvement Planning process. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Tracking Network and environmental health issues | Q1-Q4
|  | Private Water Township Evaluation | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will track use of the disseminated report and work with users to demonstrate impact through Public Health Actions. | SC- Development of targeted jurisdiction specific program activities based on generated evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
| Seasonal Influenza Surveillance Report | Internal Data Evaluation | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Grantee will coordinate with the Center for Acute Disease Epidemiology to track and evaluate the use of the internal reports to demonstrate impact. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q2
|  | PHA Development | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Grantee will document and report impact. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q2
| Violent Death Reporting System Measures | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform the Violent Death Reporting System (VDRS) data to generate measures and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of VDRS measures from the VDRS Data. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of VDRS measures. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of VDRS measures. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of VDRS measures. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the VDRS measures. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published VDRS measures via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published VDRS measures via Social Media channels. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
| Sexually Transmitted Infection Measures | Data Query | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Grantee will develop the process to load and transform Iowa Disease Surveillance System data to generate measures for additional Sexually Transmitted Infections (STI) and make it available on the Iowa Tracking Portal. The data load process uses stored procedures to ensure that useful data is available soon after release from data owner/steward. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data ETL | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will coordinate with Information Management to establish scripts to automate the extraction and transformation of the new STI measures. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data Descriptives | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop descriptive analyses to support data validation and health equity evaluation of STI measures. | SC- Standardized & accessible env. & health surveillance data | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Data Visualizations | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Grantee will develop and publish data visualizations of STI measures. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Content Bite | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Grantee will develop a targeted infographic data bite to promote the use of STI measures. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Plain Language Content | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will develop and publish messaging and content to accompany the data visualizations based on the STI measures. | Comm- Targeted comm. products & messages | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Listserve Publicity | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Grantee will distribute announcement of published STI measures via listserv. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | Social Media Publicity | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will promote the published STI measures via Social Media channels. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
| Hospital Discharge Dataset Accessibility Quality Improvement | Needs Evaluation | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | Grantee will participate in a formal Quality Improvement project to increase accessibility of the Hospital Discharge Data set. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Resource Alignment | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Grantee will engage IM staff an resource to align efforts to increase accessibility of the Hospital Discharge Data set with department technical infrastructure. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Process Development | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Grantee will develop new processes and tools to increase access to the Hospital Discharge Data set. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Process Implementation | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Grantee will implement new processes and tools to increase access to the Hospital Discharge Data set. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year