## Instructions
  Instructions
  Purpose of the Template
  Please use this workbook to document your Budget Year 5 Work Plan and Project Narrative as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section II of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)."
  This workbook includes tabs containing the finalized EH17-1702 Logic Model (blue tab), EH1702 Strategies & Activities (yellow tab) for reference, Project Narrative (purple tab) to provide greater detail regarding your planned projects, and the standardized Work Plan template (green tab). The only tabs which you should fill out are the Project Narrative tab and the Work Plan tab.
Filling out the Project Narrative tab:
  Required Reporting: Use the Project Narrative tab to provide details on how each project outlined in your work plan correspond to the specific strategies, activities, and tasks listed. In the Project Summary section, please provide an overview of the project; be sure to adhere to the 200 word limit for this section. There are no limits on the number of projects proposed. Please keep in mind that some of these projects may be an extension of the project proposed and approved in Budget Year 1 or 2 (i.e. initial EH17-1702 application). The planned projects must support the intent of the original EH17-1702 Notice of Funding Opportunity (NOFO).
  Optional Reporting: Use the right-hand side of each project area (Activity Description) to provide additional details which may not be captured in the work plan or in the project summary section. There is no word limit for this section. You may note comments pertaining to budgetary issues that might hamper the success or completion of the project as originally proposed and approved in Budget Year 1.
Filling out the Work Plan tab:
1. Project Title Create a short title for your project, no more than ten words. Examples include “Asthma Prevention”, “Improving Outdoor Air Quality,” "Improving Portal Infrastructure," "Expanding University Partnerships," etc. You may repeat the same project title in subsequent rows depending on the number of supporting strategies and activities for that project, or combine rows in that column to include the same title. You will provide a detailed description of each project on the Project Narrative tab.
2. Strategy Select a strategy from the drop-down list. Each project should fall into one primary strategy. While you can select supporting strategies and activities related to that primary strategy (ex. A Communications strategy/activity supporting the primary Science strategy/activity for that project), the first strategy you select will be the main focus of your project.
3. Activity Select an activity from the drop-down list. The activity should relate to the strategy you previously selected for that project. Each project should list at least two activities to be implemented in the budget year.
4. Activity Description In five sentences or less, describe the activity you are implementing in Column E.
5. Output Select a prospective output from the drop-down list. You may select one output per activity, or one overall output for the project. If you select multiple outputs for the project, you may find not all activities will correspond with an output.
6. Short-Term Outcome Select a prospective short-term outcome from the dropdown list. You may select one outcome per activity, or one outcome overall for the project.
7. Timeline Select when the specific activity will be accomplished from the drop-down list. Options include Quarter 1 (Q1) through Quarter 4 (Q4), meaning the activity will be accompished at the end of the budget year, or a specific time period (ex. Q1, Q2) .
Technical Support
If you need technical support when using this template, email your project officer.
            EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
      EH17-1702 Annual Performance Report (APR) - Section II only
      Budget Period: August 1, 2021 - July 31, 2022 (Budget Year 5)
      Reporting Period: August 1, 2021 - July 31, 2022

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Work Plan
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Work Plan Template
EH17-1702 Budget Period: |  |  |  | August 1, 2021 - July 31, 2022
Date Submitted to CDC: |  |  |  | 2021-03-31
REFERENCE NOTES | No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activty description. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project.
| Project Title | Activity Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline
| 1. Evaluate, Improve, and Update Existing Data on State, National Portals | Routine Data Quality Checks | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | a. Conduct routine data quality checks for all Tracking data sets | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Routine Portal Updates |  | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | b. Conduct routine portal updates of content with new years of data - including all content areas where updates were delayed due to COVID-19 response |  |  | Q1-Q4
|  | Maintain Required NCDM |  | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | c. Maintain all required NCDM on the Maine Tracking Network |  |  | Q1-Q4
|  | Maintain Optional NCDM |  | SC1.D Disseminate additional indicators & measures to address grantee priorities | d. Maintain all optional NCDM and state-specific measures and indicators on the Maine Tracking Network |  |  | Q1-Q4
| 2. Add New Data to the State Portal | Integrate Weather Data | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | a. Integrate weather data into Heat Illness and Cold Illness content areas | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q2
|  | New Years of Private Well Water Data |  |  | b. (CARRIED OVER) Add new years of well water test data to portal for existing water quality measures (if not completed in Y4) |  |  | Q1-Q3
|  | New Years of Radon in Air Data |  |  | c. Obtain, clean, and integrate new years of Radon air data into the Radon content area |  |  | Q1-Q4
|  | Explore Rabies Data |  |  | d. (CARRIED OVER) Continue exploring Rabies data for eventual addition to the portal |  |  | Q1-Q3
|  | Explore Lead Paint Abatement Data |  |  | e. (CARRIED OVER) Explore data on lead paint abatements for potential addition to the Lead Poisoning content area |  |  | Q1-Q4
|  | Explore Need for Other Data |  | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | f. Explore need for other data, including real-time data, with our Technical Advisory Group, data stewards, and partners |  |  | Q1-Q4
|  | Staff CWGs |  | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | g. Continue to assign staff to Content Work Groups |  |  | Q1-Q4
| 3. Expand and Enhance Sub-County Data on the State Portal | Sub-County Mapping in Tableau | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | a. Explore options for transitioning subcounty High-Risk Area maps (Lead Poisoning) and point maps (Lead Poisoning, Private Well Water) from Integeo to Tableau | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | Explore Sub-County Methods |  |  | b. Continue to explore subcounty methods and establish mutually compatible town- and census tract-based geographies |  |  | Q1-Q4
|  | Display Difference from State Average |  |  | c. Explore options in Tableau for displaying sub-county maps of statistical difference from the state average |  |  | Q1-Q4
|  | PFAS Mapping |  |  | d. Develop secure maps of PFAS in well water and soil for use by Maine CDC's Environmental Toxicology Program and Maine's Department of Environmental Protection in their ongoing response to emerging PFAS contamination issues | SC-Generated & disseminated env. Public health evidence |  | Q1-Q4
|  | South Portland Sub-County Data |  |  | e. Support Maine Health Data Organization (MHDO) efforts to geocode hospital discharge data, in support of Project 6, Activity e. and in support of overall NEPHT efforts to summarize NCDM data to the Census Tract level |  |  | Q1-Q4
| 4. Assure and Improve Data Quality, Usefulness, Availability, and Timeliness | MHDO Data Management | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | a. Conduct regular cleaning and management of hospital administrative data from the Maine Health Data Organization (MHDO) | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3
|  | DSAs and MOUs |  | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | b. Review and update Data Sharing Agreements and Memoranda of Understanding as needed |  |  | Q1-Q4
|  | Use Quarterly MHDO Data |  | SC1.F Address gaps & limitations in data | c. Continue to use quarterly MHDO data to reconcile the previous year of admission date data |  |  | Q1-Q4
|  | Apply and Develop QA/QC | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | d. Continue to apply and develop QA/QC processes, and maintain protocols and documentation for processing data and calculating measures | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Gap Analysis |  | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | e. Conduct a Gap Analysis |  |  | Q1-Q4
| 5. Participate in Data Calls | Data Calls | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | a. Submit all required NCDMs to CDC during fall and spring annual data calls | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q3
|  | SAMS Access | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during data calls | b. Ensure epi staff have SAMS access and are trained in submission of NCDMs | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q3
|  | Maintain NCDM Submission Tech & Infrastructure |  |  | c. Maintain technology and infrastructure for submitting NCDMs |  |  | Q1-Q4
| 6. Use Tracking Data for Public Health Actions and Practice | Update Data Annually for Use | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | a. Publish updated annual displays of lead poisoning, CO poisoning, private well water testing and quality, tickborne diseases, heat-related illness, cold-related illness, and radon for partners and data users | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | Provide Data to CHNA |  | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | b. Provide Tracking data to Maine’s Shared Community Health Needs Assessment (CHNA) as requested |  |  | Q3-Q4
|  | Maine CDC Reaccreditation |  |  | c. Staff Maine CDC Public Health Reaccreditation team |  |  | Q1-Q4
|  | Summarize Syndromic Surveillance Data for Asthma |  |  | d. Explore syndromic surveillance data for asthma ED visits, to evaluate utility as a complemetary variable for the Asthma content area |  |  | Q2-Q4
|  | South Portland Sub-County Study |  |  | e. (CARRIED OVER) Explore subcounty hospital discharge data for residents of the Portland and South Portland areas to assess whether regional petroleum container "tank farms" are responsible for any clusters of asthma or other respiratory diseases - in cooperation with Maine DEP and Maine Health Data Organization. |  |  | Q1-Q4
|  | CO Poisoning Medical Record Review |  | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | f. (CARRIED OVER) Complete a review of CO poisoning medical records to assess case reporting completeness and to obtain complete data for detector effectiveness study (if not completed in Y4) |  |  | Q1-Q2
|  | CO Poisoning Surveillance Evaluation |  |  | g. (CARRIED OVER) Evaluate Maine EPHT's case-based CO Poisoning Surveillance System (COPSS) |  |  | Q1-Q4
|  | CO Detector Effectiveness Manuscript |  |  | h. (CARRIED OVER) Complete analysis and submit for publication a manuscript describing the effectiveness of CO detectors at preventing morbidity |  |  | Q1-Q4
|  | Respond to Data Requests |  | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | i. Respond to ad hoc data requests from partners, users, legislative audiences, and stakeholders, for the purposes of public health practice or action as needed |  |  | Q1-Q4
|  | Use Tracking Data for PHAs |  |  | j. Use Tracking data to develop and evaluate public health actions for lead, CO poisoning, private well water testing, radon, heat- and cold-related illness, and/or any other content, as needed |  |  | Q1-Q4
| 7. Maintain, Implement, and Submit Program Plans, Reports, and Reviews | Communications Plan | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | a. Complete and submit an annual Communication Plan | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Tracking Network & env. health issues | Q1-Q2
|  | Partnership Plan | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | b. Complete and submit an annual Partnership Plan | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q2
|  | Annual Progress Report | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | c. Document yearly accomplishments and progress in our Annual Progress Report | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q2-Q3
|  | Site Visit |  |  | d. Assist CDC in scheduling and carrying out a site visit of our Program Officer and other appropriate NEPHT Program staff to Maine, if needed | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q3
|  | Public Health Action Reports | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | e. Complete and submit quarterly Public Health Action Reports |  |  | Q1-Q4
|  | Evaluation and Data Management Plans |  | PS2.B Develop & implement annual evaluation plan | f. Update Evaluation and Data Management Plans as needed |  |  | Q1-Q2
|  | Annual Portal Review |  | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | g. Assist CDC with annual portal reviews as requested |  |  | Q1-Q4
|  | Monthly Web Stats |  | PS2.D Collect & submit standardized web statistics on public Tracking website twice a year | h. Compile monthly web statistics for the Maine Tracking Network and submit to CDC twice per year or as requested |  |  | Q1-Q4
| 8. Promote the Maine Tracking Network and the National Tracking Program | Tracking Awareness Week | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | a. Participate in and promote Tracking Awareness Week | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Tracking Network & env. health issues | Q3-Q4
|  | User Newsletter |  | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | b. Continue publishing an e-newsletter for Maine EPHT portal users and stakeholders |  |  | Q1-Q4
|  | News Updates |  |  | c. Schedule and publish news updates, features, and announcements based on portal updates or expansions using appropriate media channels |  |  | Q1-Q4
|  | Promote Content on Social Media |  |  | d. Create and disseminate social media posts to promote the Maine Tracking Network and Tracking data, for example when new data is added or content areas are updated |  |  | Q1-Q4
|  | Staff Exhibit Booths |  | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | e. Staff exhibit booths at annual meetings of the Maine Public Health Association and the Maine Municipal Association, and the Maine Sportsman's Show, if possible given COVID-19 restrictions |  |  | Q1-Q3
|  | On-Demand Webinars and Portal Demos |  |  | f. Create and lead webinars, in-person demos, or reviews of portal data for LPPF partners, the LPPF advisory board, and any other users or stakeholders upon request |  |  | Q1-Q4
|  | Update Messaging Portal |  | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | g. Update the Maine Tracking Network messaging portal with news items, data descriptions, and metadata whenever data on the portal are added or updated |  |  | Q1-Q4
|  | Success Stories |  |  | h. Identify potential EPHT success stories; publish at least one on the Maine Tracking Network messaging portal |  |  | Q1-Q4
|  | Gather Data Use Stories |  | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | i. Continue to use tools for soliciting user information, such as a user survey or solicitation for Tracking data use ‘stories’ |  |  | Q1-Q4
|  | Staff PMO | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | j. Staff national and regional PMO groups | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
| 9. Conduct Trainings | Promote Trainings | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | a. Promote Maine and National trainings via the Maine Tracking Network messaging portal | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Conduct Trainings on New Tools/NRT Displays |  | PS1.D Develop & implement program-specific training opportunities | b. Conduct or make available trainings on new mapping tools and/or new real-time data displays as needed |  |  | Q1-Q4
|  | Conduct Trainings for LPPF |  |  | c. Conduct or make available trainings on updated lead data and mapping for LPPF partners |  |  | Q1-Q4
|  | Develop New Trainings |  |  | d. Develop web-based training modules for new content as needed |  |  | Q1-Q4
| 10. Conduct Health and Risk Communications Activities | Social Media for Awareness Weeks | Communications 1 (C1) | C1.D Utilize social media at least quarterly | a. Promote prevention messages on social media during awareness weeks and months, such as Lyme Disease, Lead Poisoning, Radon, Drinking Water, etc. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Tracking Network & env. health issues | Q1-Q4
|  | Social Media for Health Advisories |  |  | b. Create, post, and selectively boost social media posts about routine seasonal or weather event-specific health advisories related to CO poisoning risks, extreme heat, and extreme cold |  |  | Q1-Q4
|  | Distribute Family Fish Guide |  | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | c. Distribute family fish guide to obstetrics provider offices |  |  | Q1-Q4
|  | Maintain Fish Web Content |  |  | d. Maintain healthy fish consumption web content |  |  | Q1-Q4
|  | Press Releases/ HANs for Health Advisories |  |  | e. Issue seasonal or event-specific press releases and/or Health Alert Network messaging for CO poisoning prevention, heat illness prevention, or cold illness prevention |  |  | Q1-Q4
|  | Data Storytelling |  |  | f. (CARRIED OVER) Develop and publish a data storytelling product informed by our needs assessment and featuring curated Tracking content with interpretive text to allow people to quickly understand important trends, patterns, or associations. These will be targeted at state and local decision-makers, with the goal of educating and inspiring public health action. |  |  | Q1-Q4
|  | Custom Communications Project |  |  | g. (CARRIED OVER): Develop and present one new custom communications product informed by our needs assessment on Tracking data or risk communication |  |  | Q1-Q4
|  | County EH Snapshots |  |  | h. (CARRIED OVER) Complete and disseminate environmental health snapshots for each county |  |  | Q1-Q4
|  | Regional PMO | Communications 2 (C2) | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner | i. Work with other New England grantees via the Regional PMO to coordinate efforts and jointly promote portal content | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
| 11. Maintain and Enhance the Maine Tracking Network | Maintain and Enhance Portals | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements | a. Maintain and enhance existing public and secure portals | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Poral 2.0 Redesign |  |  | b. Continue to explore new best-practice options for organizing and structuring the Maine Tracking Network data portal, including the integration of new types of data display, including data stories, quick-view dashboards, and 'deep dives' for detailed exploration or data download. This design framework will be utilized in Project 11.c. below, as we explore Tableau and experiment with rebuilding existing content areas in the Tableau environment. |  |  | Q1-Q3
|  | Portal 2.0 Tableau Exploration |  |  | c. Based on findings from Project 11.b. above, continue to explore options for recreating existing displays and creating new displays in Tableau, including a complete redesign/rebuild of the Lead content area in our Tableau test environment |  |  | Q1-Q2
|  | Portal 2.0 Upgrade Drupal Environment |  |  | d. In coordination with Projects 11.b and 11.c above, complete an upgrade and expansion of Drupal environment to integrate with Tableau data displays |  |  | Q1-Q4
|  | Maintain and Enhance Databases |  |  | e. Maintain and enhance all existing databases |  |  | Q1-Q4
|  | Use Existing and Develop New Tools |  | TI1.B Develop tools and processes to improve data qualities | f. Use existing tools and develop and implement new tools to improve data quality, usefulness, and availability |  |  | Q1-Q4
|  | Staff SND | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | g. Staff national SND group | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
| 12. Maintain and Enhance Program Capacity and Partnerships | Provide Technical Assistance | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | a. Provide technical assistance by request to internal and external Tracking partners, stakeholders, and public health system partners | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | TAG |  | C2.B Maintain TAG to inform Tracking Program decisions | b. Convene Technical Advisory Group at least 2 times per year |  |  | Q1-Q4
|  | Guest Lectures |  | C2.C Establish, Maintain relationship & collaborate with at least 1 university | c. Present guest lectures incorporating Tracking principles and/or data at Maine colleges and/or universities, or talks to community partners, stakeholders, or other groups upon request |  |  | Q1-Q4
|  | Provide Expertise to Media |  | C2.D Establish & Maintain relationship with local media | d. Provide subject matter expertise to the media on issues related to Tracking |  |  | Q1-Q4
|  | Include Links to Data |  |  | e. Include data and links to data portal in news releases and health advisories |  |  | Q1-Q4
|  | Northeast Epidemiology Conference |  | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner | f. Attend and present at any Tracking-specific sessions of the annual Northeast Epidemiology Conference, if the conference and such sessions are held. |  |  | Q1-Q2
|  | Maintain Staffing | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | g. Maintain sufficient staffing to accomplish program goals | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | Maintain Contracts |  |  | h. Maintain a contract for epidemiological and health communications services |  |  | Q1-Q4
|  | Training |  | PS1.B ID & prioritize technical & capacity needs among staff for training needs | i. Identify and procure relevant training for staff |  |  | Q1-Q4
|  | Maintain Enterprise Software and OIT Staff Relationships | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | j. Maintain enterprise-level software (IBM Cognos BI or other supported portal platform software), embedded OIT staff, and regular communications with OIT managers | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | Comply with OIT Requirements |  |  | k. Continue to review and comply with all OIT requirements and standards for a web-based portal |  |  | Q1-Q4
|  | COVID-19 Response | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | l. Support ME-CDC's COVID-19 Response (NOTE: this activity will be not be funded with Tracking funds, but will be covered by dedicated COVID-19 response funds at the Maine CDC level. We include it here for completeness, since much of our COVID-19 response work is relevant to our Tracking capacity and tools.) | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q3-Q4

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
Maine Project Narrative Budget Year 5
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan" (green tab). Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
SCIENCE AND CONTENT | 1. Evaluate, Improve, and Update Existing Data on State and National Portals
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Maine EPHT will continue our ongoing efforts to evaluate and improve all existing data on the Maine Tracking Network and the National Tracking Network, and will work to establish a schedule whereby we update all existing measures every year with a new year of data, assuming these data are available. Data evaluation and improvement will consist of our routine data quality checks, which we enhance and update on an ongoing basis. These include increased involvement of data stewards with data quality checks and portal reviews; replicate analyses of a subset of measures by a second epidemiologist; better comparison of NCDM to existing sources of similar data; and improved notification of users on the rare occasions when data errors are discovered. With these efforts, Maine EPHT will ensure that we are maintaining and enhancing all required NCDM, optional NCDM, and state-specific measures on the Maine Tracking Network, and that data being sent to CDC for display on the national portal are error-free and up-to-date. |  | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 5
|  |  | 6 | 1 | 3 | 2 | 12
2. Add New Data to the State Portal
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Maine EPHT has a successful record of implementing new NCDM and developing new state-specific measures for the state portal. To facilitate the addition of new data, Maine EPHT will continue to staff and actively participate in CWGs, including Hospitalizations, Cold-Related Illness, Drinking Water, Radon, Harmful Algal Blooms, Differential Privacy, Geospatial, and Data Modernization workgroups, adding newly developed measures where they align with program priorities. In Year 5, we plan to: a) integrate weather data into displays of heat-related and cold-related illnesses, in coordination with Maine CDC’s BRACE Climate and Health program; b) complete an update of the private well water content area with new years of testing data, if not complete in Year 4; c) obtain, clean, and integrate new years of radon air data into existing portal displays; d) continue exploring data for a new rabies content area; and e) explore data on lead paint abatements for potential addition to the Lead Poisoning content area.
TECHNOLOGY AND INFORMATICS
3. Expand and Enhance Sub-County Data on the State Portal
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Maine EPHT will continue to expand and enhance our sub-county data offerings on the Maine Tracking Network. Maine EPHT staff will continue to a) explore options for moving all subcounty High-Risk Area maps (Lead Poisoning) and point maps (Lead Poisoning, Private Well Water) from our enhanced mapping tool (Integeo Map Intelligence) into our next-generation portal platform software, Tableau; b) continue to explore subcounty methods and establish mutually compatible town- and census tract-based geographies; c) explore options in Tableau for the display of sub-county maps to show statistical difference from the state average; d) develop secure point and small-area maps of PFAS in well water and soil for use in an ongoing response to contamination; and e) support efforts by the Maine Health Data Organization (MHDO) to geocode hospital discharge data, in support of Project 6, Activity e, and in Maine EPHT's overall efforts to summarize and present NCDM data at the Census Tract level.
COMMUNICATIONS
4. Assure and Improve Data Quality, Usefulness, Availability, and Timeliness
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Maine EPHT has developed numerous procedures to assure and improve data quality, usefulness, availability, and timeliness. The most important is a) the review, cleaning, and managing of hospital discharge data from the Maine Health Data Organization (MHDO). Maine EPHT staff provide MHDO a first-pass quality control review of their annual data; previously, these reviews have identified significant issues, which have led to revisions and re-releases of data. Maine EPHT will continue to provide this external review of MHDO data in Year 5. In addition, Maine EPHT program staff will: b) review and update as needed all memoranda of understanding (MOUs) and data sharing agreements (DSAs) enacted with data stewards; c) continue to use quarterly MHDO data to reconcile the previous year of admission date data; d) continue existing and ongoing procedures and practices to review and document data quality, and develop new methods and protocols as needed; and e) complete an assessment of informatics needs and associated gap analysis to address barriers to the effective use of data for public health decision-making.
5. Participate in Data Calls
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
As in previous years, Maine EPHT will continue to maintain existing data flows to CDC, submitting all required metadata and NCDM in the fall and spring data calls. Staff will follow both CDC guidelines and our own written protocols developed under prior awards to ensure timely, efficient, consistent, and scientifically sound NCDM. We will ensure that all epidemiology staff have SAMS access and are trained in submission of NCDM, and we will maintain all necessary technology and infrastructure for submitting NCDM to CDC.
PROGRAM SERVICES
6. Use Tracking Data for Public Health Actions and Practice
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Maine EPHT maintains a strong focus on staging and analyzing data to generate information for other programs and to support public health actions and decision-making. As in previous years, program activities will be focused on developing data that can be used to take public health actions, as well as on facilitating those actions. Program activities fall broadly into the following categories: 1) conducting routine descriptive analyses of Tracking data to facilitate their use for public health action; 2) using Tracking data to identify and prioritize public health concerns and priorities for the State of Maine; 3) conducting analyses of Tracking data to discover patterns of disease, exposures, and hazards; and 4) providing, applying, and interpreting Tracking data to facilitate, develop, and evaluate public health actions. See more detail on each of these activities in the Activity Description section. | Maine EPHT will a) continue to tailor displays of data on childhood lead poisoning, CO poisoning, private well water testing and quality, tickborne diseases, radon test data and testing practices, and now updated heat-related and cold-related illness, to the specifications of related programs that use these data for taking action. When requested, Maine EPHT will b) provide lead poisoning, lead screening, and private well water testing data, and any other Tracking data as requested, to Maine’s Shared Community Health Needs Assessment, which will use them to identify, track, and evaluate efforts to reduce environmental public health challenges. In addition, Maine EPHT program management staff will c) continue to sit on several of Maine CDC’s Public Health Reaccreditation Teams (as they are re-started when agency COVID-19 response allows), providing a Tracking perspective and putting Tracking data towards the effort of identifying and documenting Maine CDC’s activities to conduct and disseminate assessments of population health status and public health issues facing the community. Maine EPHT will d) explore syndromic surveillance data to determine whether a near-real time display of syndrome data for Asthma ED Visits would complement existing Asthma data on the portal; and e) explore subcounty hospital discharge data for residents of the Portland and South Portland areas to assess whether regional petroleum container "tank farms" are responsible for any clusters of asthma or other respiratory diseases - in cooperation with Maine DEP and Maine Health Data Organization. Maine EPHT will f) complete a review of CO poisoning medical records to assess case reporting completeness and to obtain complete data for detector effectiveness study; g) complete an evaluation of Maine's case-based Carbon Monoxide Poisoning Surveillance System; and h) complete an analysis and submit a manuscript for publication describing the effectiveness of CO detectors at preventing CO poisoning morbidity. Finally, Maine EPHT will i) respond to any ad hoc requests for special data analyses, displays, or no-publicly available data from partners, portal users, legislative staff, and any other stakeholders, for public health practice or the development or implementation of a public health action, as needed; and j) use Tracking data to develop and evaluate public health actions for lead poisoning, CO poisoning, private well water testing, heat- and cold-related illness, and any other content for which a need for public health action arises.
7. Maintain, Implement, and Submit Program Plans, Reports, and Reviews
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Maine EPHT will complete, submit, maintain, and implement all program plans, reports, and reviews required by CDC. These will include a) an annual Communications Plan, to be updated and submitted each fall, which will include a risk communication plan and specific, measurable, achievable, realistic, and time-bound (SMART) objectives; b) a Partnership Plan to identify and engage new and innovative external partners; c) an Annual Performance Report to document program successes and progress towards goals; d) assistance to the CDC Tracking Program if it plans for a site visit during Year 5; e) quarterly Public Health Action Reports describing public health actions made possible by Tracking data and/or staff capacity; f) updates to the Evaluation and Data Management Plans as needed; g assistance to the CDC Tracking Program in conducting annual portal reviews as requested; and h) a report of standardized website statistics to describe the patterns of use of the Maine Tracking Network.
8. Promote the Maine Tracking Network and the National Tracking Program
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Maine EPHT will continue to commit significant time and resources in Year 5 to program marketing and outreach, with the goal of promoting the Maine Tracking Network and the National Tracking Program. These efforts will broadly include: marketing of the Tracking and the Maine Tracking Network and Program via Tracking Awareness Week, newsletters, news updates, and social media; staffing of exhibit booths at relevant conferences and trade shows; presenting portal demonstrations to key stakeholder audiences; maintaining and enhancing the Maine Tracking Network messaging portal; and staffing and participating in regional and national PMO workgroups. | Specific activities associated with this project will include: a) participation in and promotion of Tracking Awareness Week; b) continued publication of an e-newsletter for Maine EPHT data users and stakeholders; c) scheduling and publishing of news updates, features, and announcements about portal updates and expansions in appropriate media channels – either our own e-newsletter, Maine CDC’s communication channels, or both; d) creating and disseminating social media posts to promote the Tracking portal and Tracking data; e) staffing exhibit booths at the annual conferences of the Maine Public Health Association and the Maine Municipal Association, and at the Maine Sportsman’s Show, if possible given COVID-19 restrictions; f) creating and leading webinars, in-person demos, or reviews of portal data for Lead Poisoning Prevention Fund (LPPF) partners, the LPPF advisory board, and any other users or stakeholders upon request; g) updating the Maine Tracking Network messaging portal with news items, data descriptions, and metadata whenever data on the portal are added or updated; h) identifying and publishing at least one Tracking success story on the Maine Tracking Network messaging portal; i) continuing to use one or more tools to solicit user feedback and information; and j) staffing and participating in regional and national Program Marketing and Outreach (PMO) workgroups.
9. Conduct Trainings
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
As part of its commitment to increasing its organizational capacity to support the Tracking Network, Maine EPHT will continue to conduct trainings on the Maine Tracking Network, and on Tracking principles, for state and local public health professionals and Tracking partners. All available Maine and National trainings will be promoted and made accessible on the Maine Tracking Network messaging portal, including the Tracking 101 and Tracking in Action learning modules, to facilitate training and education. In addition, Maine EPHT will conduct regular trainings for Maine CDC’s funded lead poisoning prevention partners, and will work with data stewards and users to identify any needs for additional trainings, especially following the development of any new content, functionality, or tools.
10. Conduct Health and Risk Communications Activities
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Maine EPHT will continue to implement health and risk communication strategies laid out in the Communications Plan. These activities will use mass and small media to reach target audiences with messages related to CO poisoning, heat- and cold-related illnesses, and safe fish consumption choices. Maine EPHT will utilize social media at least quarterly, and existing risk communications messages and products will be disseminated to target audiences (see more detail on each of these tasks in the Activity Description section). Additionally, Maine EPHT will continue development of at least two custom products to communicate Tracking data and information, informed by our needs assessment, including a data storytelling project, featuring selected data and measures in a curated display, with interpretive text, to allow people to quickly understand important trends, patterns, and associations related to a topic available on the Maine Tracking Network – likely one of our flagship content areas: tickborne diseases, lead poisoning, private well water, or the new radon content area. Finally, Maine EPHT will continue to work with our regional PMO group to coordinate on communications efforts and promote portal content with regional significance. | Social medial will be utilized at least quarterly to a) promote awareness weeks and months for lead poisoning prevention, Lyme disease, radon, drinking water, etc.; and b) create, post, and selectively boost social media posts about routine seasonal or weather event-specific health advisories related to CO poisoning risks, extreme heat, and extreme cold. Existing risk communications messages and products will be disseminated as follows: For safe fish consumption, c) family fish guides will be distributed to obstetrics practices, and d) web content will be maintained. For CO poisoning prevention, heat illness prevention, and cold illness prevention, e) we will issue seasonal press releases alerting Mainers to weather conditions and behaviors that put them at risk of poisonings or illnesses related to extreme temperatures. More generally, we will f) develop a data storytelling product, featuring curated Tracking content with interpretive text to allow people to quickly understand important trends, patterns, or associations and informed by a needs assessment conducted in Year 4; g) develop and present a custom communication product based on the findings of a needs assessment conducted in Year 4; h) create and disseminate county-level environmental health snapshots; and i) work with other New England EPHT grantees via the regional PMO group to coordinate efforts, share materials, and jointly promote portal content where applicable.
11. Maintain and Enhance the Maine Tracking Network
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
The Maine Tracking Network uses a combination of IBM Cognos Business Intelligence as the web-based data reporting system, Drupal Content Management System as a front-end messaging platform, and Integeo Map Intelligence for secure advanced mapping applications. Since 2011, Maine EPHT has also maintained a secure, role-based portal where unsuppressed data are available for authorized users. In Year 5, our focus will be on a 'Portal 2.0' effort to re-envision our portal structure and to transition from our Cognos platform to a more powerful and flexible Tableau environment. Notable efforts will include the following: an exploration of best practice options for organizing and structuring the Maine Tracking Network data portal, including addition of new data display types such as data stories and dashboards; and an upgrade and expansion of our Drupal messaging portal to integrate cleanly with Tableau displays. Finally, we will continue to: maintain and enhance all existing databases and systems used to house hospital discharge data and intermediate data tables for portal display; use existing tools and processes to improve data quality, usefulness, and availability; develop new tools and processes; and continue to staff and actively participate in the Standards and Network Development (SND) workgroup.
12. Maintain and Enhance Program Capacity and Partnerships
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| One of Maine EPHT’s particular strengths is the diverse and skilled team of internal staff and external partners and stakeholders that we have assembled over the 19 years of our program. We plan to maintain and enhance this programmatic strength in Year 5 through targeted outreach and partnership building, and dedicated staff training and capacity building. These efforts will fall broadly into four areas: 1) strengthening existing partnerships and creating new partnerships through meetings, presentations, provision of technical assistance, and interactions with our TAG, academic partners, data users and stewards, and other stakeholders; 2) establishing and maintaining a relationship with local media; 3) maintaining and enhancing our program capacity through staff and contract management and provision of ongoing training and support; 4) working with our Office of Information Technology to ensure program activities align with organizational objectives; and 5) leveraging the capacity of the Maine EPHT team to continue to support Maine CDC's unprecedented COVID-19 response effort. Further detail on the activities associated with these areas is given in the Activity Description section. | Maine EPHT will create new and strengthen existing partnerships through the following activities: a) provision of technical assistance by request to internal and external Tracking partners, stakeholders, and public health system partners; b) regular meetings with our Technical Advisory Group, and the addition of members in key areas as needed; and c) presentation of guest lectures at Maine colleges and universities and to other groups as requested, which will include descriptions of Tracking principles and products. Maine EPHT will establish and maintain a relationship with the local media through d) the provision of subject matter expertise to the media; and e) the inclusion of data and links to the data portal in all media communications. Maine EPHT will engage regional partners by f) attending and presenting at any Tracking-specific sessions at the Northeast Epidemiology Conference in Fall 2020, assuming the conference and such sessions are held. Maine EPHT will maintain and enhance program capacity by g) maintaining sufficient staffing to accomplish program goals; h) maintaining a contract for epidemiological and health communications services; and i) identifying and providing relevant training for staff. Maine EPHT will work with our Office of Information Technology (OIT) to ensure alignment of program activities and organizational goals by j) continued collaboration with OIT around the use and maintenance of enterprise-level software, the embedding of OIT staff within our program, and regular communication between program management staff and OIT managers; and k) compliance with all OIT requirements and standards for our web-based portal. Finally, Maine EPHT will provide its staff as needed to Maine CDC for technical and tracking-relevant aspects of agency response to the COVID-19 pandemic, including core epidemiology functions, case investigations, contact tracing, data visualization efforts, and evaluation of health outcome and healthcare utilization models for advanced planning.

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year