## Instructions
  Instructions
  Purpose of the Template
  Please use this workbook to document your Budget Year 2 Work Plan Report Out and Project Narrative as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section I of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)."
  This workbook includes tabs containing the finalized EH17-1702 Logic Model (blue tab), EH1702 Strategies & Activities (yellow tab) for reference, Project Narrative (purple tab) to provide greater detail regarding your completed projects, and the standardized Work Plan template (green tab).
  If you have additional projects you have developed during this past reporting period in addition to previously submitted projects, please provide information on new projects in the Project Narrative tab and Work Plan tab.
Filling out the Project Narrative tab:
  Required Reporting: Utilizing your previously submitted Project Narrative information, provide details on how each completed project that was outlined in your work plan corresponded to the specific strategies, activities, and tasks listed. In the Project Summary section, please provide an overview of the completed project; be sure to adhere to the 200 word limit for this section.
  Optional Reporting: Use the right-hand side of each project area (Activity Description) to provide additional details which may not be captured in the work plan or in the project summary section. There is no word limit for this section. You may note comments pertaining to budgetary issues that might have hampered the success or completion of the project as proposed and approved in Budget Year 2, as well as significant successes or challenges related the project.
Filling out the Work Plan tab:
1. Status: Utilizing your previously submitted proposed work plan for Year 2, select the status of each task and project from the drop down list.
2. Successes: Briefly describe notable progress on completing project related tasks.
3. Challenges: Describe any challenges that may have affected the ability to achieve goals related to the task and project.
4. CDC Program Support: Describe how CDC could help overcome challenges to completing tasks and projects.
Technical Support
If you need technical support when using this template, email your project officer.
            EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
      EH17-1702 Annual Performance Report (APR) - Section I only
      Budget Period: August 1, 2018 - July 31, 2019 (Budget Year 2)
      Reporting Period: February 1, 2018 - January 31, 2019
      Arizona Department of Health Services (PI: Matthew Roach)

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
[Recipient] Project Narrative Budget Year 2
Type your project narrative below. Please limit your narrative to 200 words per project. Each project falls into one primary strategy. Each project has at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. Your strategy/strategies as well as your supporting activities were noted on the "Work Plan" (green tab). Activities in RFA-CDC-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited to reporting on projects previously proposed. If you have added additional projects during this project period, simply fill out a new project box to the end of your worksheet and report.
SCIENCE AND CONTENT | Conduct Program Marketing and Outreach
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Grantee will update and implement annual communication plan for year 2. Communication activites implemented for year 2 will include regular updates to stakeholders and the general public on on Tracking activites including new data uploads and other new features on the Tracking portal. this will be done through call out boxes on the website, newsletter updates, and social media posts. Grantee will also participate in program wide communcation activities including Tracking Awareness week 2019. Grantee will continue to promote and market the Tracking Network (local & national) to appropriate audiences. These presentations will include content on data avaliable on both networks, how to use the portals and potential uses for the data. Existing Tracking communication messages and products will be disseminated to appropriate audiences. These communication products may include factsheets, infographics, and other products that could be developed from needs assessments. Efforts wil be led by our EPHT health education team (lead: health educator, risk communication specialist, pio/health educator, and IT web designer). The group will communicate by in-person meetings at least weekly, telephone, and email. Overall team meetings with other EPHT teams including science and content, and technology and informatics, and program services will occur at least monthly to ensure a shared vision. | Activity 1) Update communication plan according to CDC guidelines. Activity 2) Grantee will participate in Tracking Awareness Week by posting social media posts Activity 3) Post announcements on Tracking website to call attention to new data, new features, and new communication products on Arizona's tracking portal. Distribute newsletters communicating new data and applications to relevant audiences. Activity 4) Grantee will post social media to Facebook and Twitter regarding grantee NCDM portal updates, PHAs, Tracking Awareness Week, and other multi collaborative grantee communication activities. Activity 5) Present on Tracking portal both local and national to relevant stackholders. Distribute existing and new communication materials in year 2. Activity 6) Grantee will post website updates regarding new and optional NCDM added to the website. Specifically, the relation between environment and health for the NCDM as well as supporting resource websites (internal and external to the agency). Activity 7) Hand out Tracking materials at presentations and other outreach events Activity 8)The Grantee will participate with PMO West in Lead Poisoning Awareness Week and other topics brought up by the group. The Program will post social media, blogs, and email newsletter to listserv. Activity 8) Conduct needs assessment with appropriate party and develop new communication tools for them. Activity 9) Science & Content team will provide Tracking required/optional/non-NCDM written updates on portal and trend information to AZ PMO team for outreach efforts. Activity 10) AZ PMO, Science & Content, and Program Services will meet with technology & informatics team to address feedback and improve portal with recommendations by users of the data. Activity 11) PMO will do outreach to university students and health department staff about EPHT trainings and internship opportunities. | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 2
|  |  | 2 | 1 | 2 | 2 | 7
Initiate, Maintain, and Expand Partnerships
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Grantee will update and implement partnership plan to develop and maintain relationship with previous and new partners. In year 2, Grantee will continue to communicate with ADHS tribal liason to ensure Tribal connections are maintained and enhanced. We will continue to maintain and expand our internal partners including : Childhood Lead Poisoning Prevention Program, Enviromental Toxicology, Climate and Health Program, Office of Cancer Registry, Birth Defects Program, Safe WATCH, Biomonitoring Program, Public Health Emergency Prepardeness Program, and Arizona Radiation Regulatory Agency. We will also expand our extrnal partnerships with traditonal partners like county health departments (e.g.) Maricopa County Public Health Department, universities (Arizona State University and University of Arizona), and Arizona Department of Enviromental Quality as well as non-traditional partners like Arizona Department of Transportation, and tribal governments. The grantee will send out press releases to media and provide responses and interviews to reporters regarding data, PHAs, and other partner activities. The grantee will also partner on national conferences and webinars with PMO West or EPHT content workgroups. Efforts wil be led by our EPHT health education team (lead: health educator, risk communication specialist, pio/health educator, and IT web designer). The group will communicate by in-person meetings at least weekly, telephone, and email. Overall team meetings with other EPHT teams including science and content, and technology and informatics, and program services will occur at least monthly to ensure a shared vision. | Activity 1) Update partnership plan for year 2. Continue to meet and collaborate with internal partners to guide Tracking program activities. Activity 2) Hold bi-annual TAG meetings Activity 3) Lecture and host intern from local Universities. Continue to maintain relationship with University of Arizona College of Public Health Program and Arizona State University. Activity 4) Send out press release through agency media channels (print news, tv, and radio) regarding PHAs and NCDM updates to portal and trends found in data and respond to media requests by providing subject matter expert interview. Activity 5) Co-present at national meeting such as Council of State and Territorial Epidemiologists or CSTE webinar regarding Tracking related project with PMO West or EPHT Content Workgroups. Activity 6) AZ PMO will work with Science & Content team to gather feedback from AZ stakeholders on potential new NCDM for adding to state portal and tweaks to existing NCDM. Activity 7) AZ Technology and Informatics will enlist PMO help for guidance on additional features to add to the secure and public portal based on stakeholder feedback of portal. Activity 8) AZ PMO will work with Science & Content team to create trainings and content for public health & non-public health stakeholders regarding how to use AZ portal to support their work.
TECHNOLOGY AND INFORMATICS
Identify and Integrate Public Health and Environmental Data
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The grantee will continue to evaluate each dataset as per CDC recommendations through the CDC Metadata Creation Tool for NCDM. NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC Secure Access Management System (SAMS). Optional NCDM will be collected, formatted, and submitted as per CDC guidance document. NCDM will be uploaded into grantee Tracking Portal. The program will identify additional indicators by engaging local partners through workshops on Tracking Data. Science and Content Workgroup Staff will participate in grantee CWG. Arizona Content and Science Workgroup staff will participate in grantee meetings. CWG staff will engage stakeholders using CDC EPHT SharePoint site discussion boards. The Program has partnered with MCDPH and the ADEQ through a sub-contract in order to gather perspectives for novel data element additions to Tracking. Analysis will reduce data gap by creating datasets at sub-county scale (primary care area or other small geographical area). If feasible, data will be added to state portal. Delegation of work will be led by the Science and Content Capacity Team (PI, Epidemiologist, Risk Communication Specialist, Agency Liaison/Policy Advisor, GIS Developer, GIS Supervisor, IT Manager). | Activity 1) Grantee will continue to identify and evaluate NCDM data and projects done in collaboration with CWG. Activity 2) Grantee will continue to prepare NCDM for CDC data submissions and upload NCDM to the grantee Tracking Portal as per CDC requirements. Activity 3) Grantee will continue to maintain NCDMs as per CDC guidance and disseminate via grantee network. Activity 4) Grantee will continue to engage local partners via workshops and participate in grantee CWG in order to identify additional indicators. Activity 5) Grantee will continue collaboration with partners to improve existing and adopt new NCDM developed by CWG. Activity 6) Grantee will continue to collaborate with MCDPH and ADEQ to address gaps and limitations in data. Activity 7) Technology and Informatics team will ensure that programmers and software are available that science and content team can use to create existing & new NCDM in XML for submission. Activity 8)AZ PMO will create website plain messaging language to accompany new NCDM datasets on state portal and meet with AZ Science and Content Team to ensure accuracy of website information. Activity 9) CDC Preventive Medicine Fellow will assist with engaging AZ tribes in order to establish tribal needs, data sharing and opportunities for assisting with environmental epidemiology issues.
COMMUNICATIONS
Analyze and Apply Data to Translate Science into Action
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program’s Epidemiologist with support from the PI will conduct routine descriptive analysis of required and optional NCDM to evaluate quality and completeness of data using SAS and the CDC DIVE validation tool. Routine analysis will also be done on CWG indicators under development. The Epidemiologist will use Tracking data to identify vulnerable populations using numbers, rates, and percentages to identify elevated risk areas. Counties identified in the highest segmented category when compared to state and national comparisons will be shared at the planned workshop, email, and planned workgroup meetings with stakeholders. From this information, health education material will be developed to aid in prevention efforts for priority areas. The Program has partnered with MCDPH through a sub-contract. Scope of work includes conducting routine analysis using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards at sub-county scale. Timely reporting of their findings to ADHS will help coordination efforts for further investigation with other state and local partners as well as new insights/solutions. Delegation of work will be led by the Science and Content Capacity Team (PI, Epidemiologist, Risk Communication Specialist, Agency Liaison/Policy Advisor, GIS Developer, GIS Supervisor, IT Manager). | Activity 1) Grantee will continue to conduct routine descriptive analysis of NCDM to evaluate data quality and completeness. Activity 2) Grantee will continue to use Tracking Data to identify and prioritize jurisdiction public health concerns and priorities. Activity 3) Grantee will continue to conduct routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards. Activity 4) Grantee will continue to apply and interpret Tracking Data to inform the development and evaluation of public health actions. Activity 5) Science & Content will work with PMO, Program Services, and Technology and Informatics to develop new portal tools to answer analysis questions by EPHT users for PHAs. Activity 6) PMO will do a news release and social media regarding EPHT data trends found. Science and Content team will ensure accurate messages. Also, for PHAs. Activity 7) Science & Content will work with PMO, Program Services, and Technology and Informatics to develop new portal tools to answer analysis questions by EPHT users for PHAs. Epidemiologists at MCDPH will also help analyze Tracking Data NCDM and report back monthly of findings through email, teleconference, or in person meetings. The Epidemiologist and county health departments under the secure portal will use ESRI Insights, a browser-based analytic tool for spatial and non-spatial data. The Epidemiologist and PI will also use SAS for data analyses and informing the development and evaluation of public health actions. Tracking data will be used to notify stakeholders regarding changes in environmental and health outcome NCDM at workshops, workgroup meetings, teleconferences, and email.
Increase Organizational Capacity to Support the Tracking Network
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program will lead, support, and maintain existing Environmental Public Health Tracking Program within state jurisdiction by staffing appropriately to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the state and secure portal, data analysis support, and data updates. The Program will continue to hold Technical Advisory Group Meetings at least once a year. Additionally, Program Working Groups will meet at least once a month to discuss technical capacity and needs. The Program will facilitate three workshops with county health departments for describing Tracking principles. In Years 2-5 The Program will work with Arizona State University School of Geographical Sciences and Urban Planning and other local universities to develop web-based or in-person training program-specific training modules regarding use case. The program will develop a sub-contract with a university stakeholder to formalize the partnership using an interagency service agreement. Internships would be offered working in either program aspects of epidemiology, communications or GIS. ADHS has a formal internship process established with required documentation for insurance purposes. Local universities are familiar with the ADHS internship coordinator. | Activity 1) EPHT Program staff will meet with and teach other internal and external partners about EPHT NCDM collection and formatting guidance with programs such as ADEQ, CLPPP, Climate and Health, biomonitoring, toxicology, birth defects, SafeWATCH in order to gather data on existing and new NCDM. Activity 2) Technology and Informatics Teams and Science and Content team will develop scripts and SOPs (e.g. SAS Programs) to help partner programs which support AZ EPHT to help expedite data call uploads (e.g. WQL,CLP2,CLP4,BD, PWS). Activity 3) Science and Content Team (epidemiologist and PI) will establish relationship with university for assisting on collaborative public health project using EPHT data and teaching university students about EPHT. Activity 4) Staffing appropriately to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the state/secure portal, data analysis support, and data updates. Activity 5) Hold Technical Advisory Group Meetings at least once a year. Additionally, Program Working Groups will meet at least once a month to discuss technical capacity and needs. Activity 6) Hold EPHT workshops throughout state with county health department for describing Tracking principles in person, teleconference, or webinar. Activity 7) Develop web-based or in-person training program-specific training modules for EPHT with local universities (ASU,UA) and host EPHT interns.
PROGRAM SERVICES
Monitor the Impact and Performance of Program Activities
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program will submit public health actions twice per year to the project officer through email. PHAs will also be described in an evaluation report & the APR. The PI will assume responsibility for the document and will be supported by the CDC preventive medicine fellow. The Program will develop and implement an annual evaluation plan, based on the CDC recommendations. The evaluation plan will be coordinated through the Program Service Workgroup led by the Policy Advisor/Liaison and supported by the Principal Investigator and CDC Preventive Medicine Fellow. The evaluation plan will also include success stories to document program successes which can be shared on the National Portal. The Science and Content Workgroup, Communications Workgroup and Technology and Informatics Workgroup assigned staff from AZ will participate in workgroups based on area of expertise using teleconferences, webinars, and providing reviews during in-person grantee meetings. The IT Web Designer will provide website statistics and clicks for various subpages of the Tracking Program to identify the most used through Google Analytics which is standard practice for the agency’s websites. Website statistics will be submitted to the project officer by email twice per year and documented in the evaluation plan/ annual progress report. | Activity 1) AZ Science and Content team will use tracking data to help jurisdictions and partners identify public health concerns and use data to monitor intervention effectiveness using time series data. Data can contribute to local and state health assessment plans and improvement plans. Activity 2) Technology and Informatics Team will work with IT leadership to ensure data metrics help align with needs for state health improvement plan and county health improvement plan metrics that may use tracking data to help monitor effectiveness. Activity 3) AZ PMO will post updates and announcements about grantee tracking activities to Tracking listserv and on social media about the impact of program activities on public health in AZ. Activity 4) CDC Preventive Medicine Fellow assists Science and Content Team on identifying PHA opportunities and writing up quarterly PHAs to CDC. Activity 5) CDC Preventive Medicine Fellow will lead program services team in developing annual evaluation plan and capturing evaluation results and performance report for evaluation reporting. Activity 6) AZ Science and Content, Technology and Informatics, Program Marketnig and Outreach, and Program Services teams formed in year 1 will meet by webinar, in person, or teleconference to assist in portal review and updates. Activity 7) AZ PMO Team led by health educator will ask technology and informatics team to use Google Analytics to capture web statistics to submit to CDC and help inform program evaluation.
Maintain and enhance information technology infrastructure
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Arizona EPHT Portal follows guidance from CDC Tracking Grantee Portal Standards and Recommendations (version 1.) Grantee portal is being updated to meet all standards and recommendations through using ESRI GIS products. In year 2, the grantee will move its platform to Amazon Web Services (AWS) cloud to increase reliability and conform to state standards. Grantee will migrate data structure to SQL and launch a secure portal with user-based access. Public facing portal will be redesigned to provide additional functionality, new required and optional NCDM, and reporting options.Options will be based on science and content team feedback. Delegation of work will be led by the EPHT Technology and Informatics Team (IT Liaison, GIS Supervisor, GIS Developer, and Web Media Specialist). The GIS Developer will handle a majority of efforts at 1 FTE and rely on the GIS Supervisor and IT Liaison for following state standards and procurement of hardware and software. The GIS Developer will communicate at least weekly by email, phone, and in person meetings with PI to ensure science and content updates are incorporated. The TI team will meet monthly for team meetings with PI and Science and Content Team staff for exchanging updates. | Activity 1) Grantee portal will continue to be maintained and updated with new NCDM indicators, and grantee will launch secure portal and support multiple dataset analysis.Activity 2) New reporting tools will be created to dynamically display relevant information. Charts and graphs will be designed to reflect changes in ICD10. Activity 3) Load testing will be performed prior to launch of redesigned portal. Statistics of use patterns will be analyzed to determine improvement areas. Activity 4) The PI and the GIS Developer have access to the CDC EPHT SharePoint Site for downloading newest version of the data validation program (DIVE) and indicator templates, CDC’s Secure Access Management System (SAMS) for secure file transfer and metadata creation tool (MCT) and capability to convert SAS datasets to XML. Activity 5) Platform will move to AWS cloud in accordance with statewide initiatives. Activity 6) Sub County data will continue to be added to allow for community based analysis. The state will work with local partners to provide secure determine needs and provide meaningful enhancements to data visualization and analysis capabilities. Activity 7) SAS and SQL and Python scripting will be used to automate the process of validating and updating data. Activity 8) Technology and Informatics team will ensure secure and public portal are available for science and content team to conduct routine descriptive epidemiology of NCDM/Non-NCDM to discover patterns of disease, exposure, and hazards in a timely manner Activity 9) .Technology and Informatics team will participate in TAG to hear feedback and disseminate technology updates to AZ TAG. Activity 10) Technology and Informatics team will ensure users have access to public and private portal and that internal program staff have access to IT resources for performing NCDM updates/queries.
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)

## Work Plan
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Work Plan Template
EH17-1702 Budget Period: |  |  | February 1, 2018 - January 31, 2019
Date Submitted to CDC: |  |  | 2019-04-10
REFERENCE NOTES | No more than 10 words per project title. Describe full project in Project Narrative tab. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One task per row; no more than 5 sentences per task. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project. | Continuation Report (Section I)
| Project Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline | Status | Successes | Challenges | CDC Program Support Needed
| Conduct Program Marketing and Outreach | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Update communication plan according to CDC guidelines. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2 | Complete |  | Discovered that many metrics included in year 1 communication plan were unclear or found that we were unable to measure in the way expected.
|  | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Grantee will participate in Tracking Awareness Week by posting social media posts | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4 | Complete
|  | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Post annoucements on Tracking website to call attention to new data, new features, and new communication products on Arizona's tracking portal. Distribute newsletters communicating new data and applications to relevant audiences. | Comm- Targeted comm. products & messages | Comm- Engaged partners & users | Q2-Q3 | Complete |  | Identified a need for a system to track changes to the Data Explorer (including changes to features, additionals of data sets, addition of data years, addition of data at different geographies) so that we can update on only the newest changes
|  | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will post social media to Facebook and Twitter regarding grantee NCDM portal updates, PHAs, Tracking Awareness Week, and other multi collaborative grantee communication activities. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete |  | Posts did not result in an increase in average daily unique page views to the EPHT website or data explorer
|  | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | Present on Tracking portal both local and national to relevant stackholders. Distribute existing and new communication materials in year 2. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete | Engaged with 29 unique audiences through presentations and exhibiting. Daily unique page views increased from an overall average of 5.5 per day to 8.2 following a presentation (including the day of the presentation and 2 days after) | Measuring the impact of presentations and engagements in a way other than hits to the website | Continued support in developing and disseminating evaluation methods
|  | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will post website updates regarding new and optional NCDM added to the website. Specifically, the relation between environmen and health for the NCDM as well as supporting resource websites (internal and external to the agency). | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete
|  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Hand out Tracking materials at presentations and other outreach events | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete
|  | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity | The Grantee will participate with PMO West in Lead Poisoning Awareness Week and other topics brought up by the group. The Program will post social media, blogs, and email newsletter to listserv. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q2-Q3 | Complete
|  | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Conduct needs assemessment with appropriate party and develop new communication tools for them. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4 | In Progress | Rural county environmental health directors identified a need for communication products related to septic systems; a brochure is under development | Response rate for tribal partners was very low. Need to try a different strategy to conduct a needs assesment with this audience.
|  | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Science & Content team will provide Tracking required/optional/non-NCDM written updates on portal and trend information to AZ PMO team for outreach efforts. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete
|  | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | AZ PMO, Science & Content, and Program Services will meet with technology & informatics team to address feedback and improve portal with recommendations by users of the data. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete
|  | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | PMO will do outreach to university students and health department staff about EPHT trainings and internship opportunities. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete | Recruited 1 intern from the University of AZ that is working on EPHT projects; presented at 3 university courses/seminars
| Initiate, Maintain, and Expand Partnerships | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Update partnership plan for year 2 . Continue to meet and collaborate with internal partners to guide Tracking program activities. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete
|  | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Hold bi-annual TAG meetings | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete | In person TAG meetings held on June 18 and November 9, 2018; presented to 17 new attendees in November and recuited 10 to workgroups. TAG distribution list now contains 57 contacts. | Met some challenge in defining, building, and recruiting for workgroups, as well as maintaining action items of workgroups between larger TAG meetings.
|  | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Lecture and host intern from local Universities. Continue to maintain relationship with University of Arizona College of Public Health Program and Arizona State University. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete | Developed a contract with University of Arizona for EPHT analysis work and collaboration on integrating vector borne disease data into the AZ Data Explorer
|  | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | Send out press release through agency media channels (print news, tv, and radio) regarding PHAs and NCDM updates to portal and trends found in data and respond to media requests by providing subject matter expert interview. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete |  | PIO position became vacant during year 1 after first press release distributed
|  | Communications 2 (C2) | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner | Co-present at national meeting such as Council of State and Territorial Epidemiologists or CSTE webinar regarding Tracking related project with PMO West or EPHT Content Workgroups | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete | 1)December 2018 ISDS/CSTE Webinar on cold illness with NYC EPHT epidemiologist Katie Lane 2) March 2018 AZ/CA heat syndromic surveillance webinar with California BRACE Program.
|  | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | AZ PMO will work with Science & Content team to gather feedback from AZ stakeholders on potential new NCDM for adding to state portal and tweaks to existing NCDM. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | Received feedback from TAG during Nov 9 meeting on datasets that should be explored; sucessfully identified a novel data source for cost information (SHELDUS) and contracted with the University of Arizona to explore data sources and display options for vector borne diseases | Prioritizing requests for new data and managing the process, including identification of data sources, working with partners, managing data sharing agreements if necessary, deciding upon indicators and measures, and producing metadata. | Potentially a master list of novel data sources (non NCDM data) that grantee states include on state Data Explorers. This might allow an easy reference to identify a state that has sucessfully published novel data sources or non-NCDM's requested by local stakeholders.
|  | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | AZ Technology and Informatics will enlist PMO help for guidance on additional features to add to the secure and public portal based on stakeholder feedback of portal. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Feedback on Data Explorer acquired through the TAG as well as an internal ADHS Data Visualization Club, which was a useful form for feedback
|  | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | AZ PMO will work with Science & Content team to create trainings and content for public health & non-public health stakeholders regarding how to use AZ portal to support their work. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete | Developed a how-to-guide video on using the Data Explorer for the general public that is now available online based on requests from stakeholders and the TAG.
| Identify and Integrate Public Health and Environmental Data | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Evaluate each dataset using criteria (CDC EPHTN Tracking Network Profile Version 1.2 for metadata standards) in metadata reports through the CDC Metadata Creation Tool for NCDM. We will participate in projects regarding CWG. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete
|  | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC. In conjunction, NCDM will be uploaded into grantee Tracking Portal supported by ESRI GIS software and SAS for data analysis. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | The CDC QA process noted statistically significant decreases in some indicators from our Hospital Discharge Database, which prompted further research and the discovery that several hospitals from a northern AZ county were removed from HDD during the submission years due to poor data quality. This prompted improvements in our internal process for understanding and validating yearly HDD datasets.
|  | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Required and optional NCDM will be collected, formatted, and submitted using the guide “Standards for Nationally Consistent Data and Measures within the CDC’s National Environmental Public Health Tracking Network Version 4.0.” Data will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC Secure Access Management System (SAMS). | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete
|  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | The program will identify additional indicators by engaging local partners through 3 workshops on Tracking Data. Science and Content Workgroup Staff will participate in grantee Content Working Groups. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete
|  | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Arizona Content and Science Workgroup staff will participate in grantee teleconference, webinars, and in-person grantee meetings. Content Workgroup staff will engage stakeholders using CDC EPHT SharePoint site discussion boards. A budget was requested to send 3 staff to the 2 required grantee meetings described in Year 1. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete
|  | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | The Program will partner with Maricopa County Department of Public Health (MCDPH) and the Arizona Department of Environmental Quality (ADEQ) through a sub-contract in order to gather their perspectives for novel data element additions to Tracking. Epidemiologists at MCDPH will analyze air and water quality data from ADEQ as well as health outcome NCDM from ADHS to determine if sufficient and relevant. Analysis will reduce data gap by creating datasets at sub-county scale (primary care area or other small geographical area). If feasible, data will be added to state portal. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4 | Complete | Collaborated with ADEQ to have them add population served per water system as a variable collected in yearly data sets; integrated one novel data set (SHELDUS); expanded the availability of sub-county data
|  | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Technology and Informatics team will ensure that programmers and software are available that science and content team can use to create existing & new NCDM in XML for submission. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete
|  | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | AZ PMO will create website plain messaging langugage to accompany new NCDM datasets on state portal and meet with AZ Science and Content Team to ensure accuracy of website information. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete | Plain language messaging about NCDM's added to the website for the following content areas: population characteristics, air pollution, climate, cold illness, sunlight and UV, community design, and public water system water quality
|  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | CDC Preventive Medicine Fellow will assist with engaging AZ tribes in order to establish tribal needs, data sharing and opportunities for assisting with environmental epidemiology issues. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | In Progress | Developed Tribal Communication plan and meet with Tribal Liaison; have presented at tribal colultation meetings, to tribal partner organizations, and tribal epidemiology centers; planning a regional tribal EPHT meeting for June 2019
| Analyze and Apply Data to Translate Science Into Action | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | The Program’s Epidemiologist with support from the PI will conduct routine descriptive analysis of NCDM to evaluate quality and completeness of data using SAS and epidemiological analysis as well as use the CDC DIVE validation tool. The statistic will also use data as talking points for 3 planned workshops with local partners. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | Complete
|  | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | The Epidemiologist will use Tracking data to identify vulnerable populations using numbers, rates, and percentages to identify elevated risk areas. Counties identified in the highest segmented category when compared to within state and national comparisons will be shared at the planned workshop, email, and planned workgroup meetings with stakeholders such as local health departments, tribes, and university researchers. From this information, health education material will be developed to aid in prevention efforts for priority areas. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress |  | Heath communication material related to identified vulnerabilities has not yet been developed.
|  | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | The Program will partner with (MCDPH) through a sub-contract. Scope of work will include conducting routine analysis using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards at sub-county scale. Timely reporting of their findings to ADHS will help coordination efforts for further investigation with other state and local partners as well as new insights/solutions. Epidemiologists at MCDPH will analyze Tracking Data NCDM and report back monthly of findings through email, teleconference, or in person meetings. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress |  | Epidemiologist time was largely devoted to preparing and validating data sets as far back as possible to bring the AZ Data Explorer up to speed with other grantees. Need more time to develop protocols and codes for routine analysis. | Support from Journal Club in developing processes for conducting routine analysis
|  | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | The Epidemiologist and county health departments under the secure portal will use ESRI Insights, a browser-based analytic tool for spatial and non-spatial data. The Epidemiologist and PI will also use SAS for data analyses and informing the development and evaluation of public health actions. Tracking data will be used to notify stakeholders regarding changes in environmental and health outcome NCDM at workshops, workgroup meetings, teleconferences, and email. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress | PHA's submitted and accepted but not formally evaluated
|  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Science & Content will work with PMO, Program Services, and Technology and Informatics to develop new portal tools to answer analysis questions by EPHT users for PHAs. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete
|  | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | PMO will do a news release and social media regarding EPHT data trends found. Science and Content team will ensure accurate messages. Also, for PHAs. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete |  | PIO position became vacant during year 1 after first press release distributed
|  | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Science & Content will work with PMO, Program Services, and Technology and Informatics to develop new portal tools to answer analysis questions by EPHT users for PHAs. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Complete | IT and GIS team develop innovative tools that benefit many groups within the health deparment outside of EPHT
| Maintain and Enhance Information Technology Infrastructure | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements | Grantee portal will continue to be maintained and updated with new NCDM indicators, and grantee will launch secure portal and support multiple dataset analysis. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | In Progress |  | Work needed to determine users and specifications of the secure portal will require significant input from the Research and Indicators Work Group of the TAG
|  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | New reporting tools will be created to dynamically display relevant information. Charts and graphs will be designed to reflect changes in ICD10. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete
|  | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | Load testing will be performed prior to launch of redesigned portal. Statistics of use patterns will be analyzed to determine improvement areas. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Major improvemenst to load time from >20 seconds to <2 seconds
|  | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | The PI and the GIS Developer have access to the CDC EPHT SharePoint Site for downloading newest version of the data validation program (DIVE) and indicator templates, CDC’s Secure Access Management System (SAMS) for secure file transfer and metadata creation tool (MCT) and capability to convert SAS datasets to XML. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete
|  | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Platform will move to Amazon Web Services (AWS) cloud in accordance with statewide initiatives | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Increased uptime and reliability of site availability. | Overall cost savings for the agency, but the program takes on more cost for hosting and disseminating data.
|  | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Sub County data will continue to be added to allow for community based analysis. The state will work with local partners to provide secure determine needs and provide meaningful enhancements to data visualization and analysis capabilities. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Sub-county data was added for 7 datasets to the public portal | Need to work with data stewards define advanced options (i.e. age, sex, and race/ethnicity groups, as well as time frames of data that can be displayed at sub-county geographies). That process will take longer. | Help need to assure data stewards that there has been an "expert determination" that there is "no reasonable way to re-identify individuals at the data scale released"
|  | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | SAS and SQL and Python scripting will be used to automate the process of validating and updating data. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete
|  | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Technology and Informatics team will ensure secure and public portal are available for science and content team to conduct routine descriptive epidemiology of NCDM/Non-NCDM to discover paterns of disease, exposure, and hazards in a timely manner. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | In Progress | Public data explorer is up and is available for routine analysis. | Secure data explorer is under evaluation. The TAG put in a request for a secure data explorer.
|  | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Technology and Informatics team will participate in TAG to hear feedback and disseminate technology updates to AZ TAG. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete
|  | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Technology and Informatics team will ensure users have access to public and private portal and that internal program staff have access to IT resources for performing NCDM updates/queries. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | In Progress | Public-facing secure portal not yet developed or launched
| Increase Organizational Capacity to Support the Tracking Network | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Staffing appropriately to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the state/secure portal, data analysis support, and data updates. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete
|  | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Hold Technical Advisory Group Meetings at least once a year. Additionally, Program Working Groups will meet at least once a month to discuss technical capacity and needs. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete | Held 2 in-person TAG meetings during the reporting period, recruitng new partners and getting more volunteers for workgroups at each meeting
|  | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Hold EPHT workshops throughout state with county health department for describing Tracking principles in person, teleconference, or webinar. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | Complete | Presented to counties during the Epidemiology and Surveillance Capacity Meeting
|  | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Develop web-based or in-person training program-specific training modules for EPHT with local universities (ASU,UA) and host EPHT interns. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4 | In Progress | Hosted 1 intern from University of Arizona and incorporated EPHT into spatial epidemiology course at the University of Arizona College of Public Health through class lecture and projects using Tracking data.
|  | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | EPHT Program staff will meet with and teach other internal and external partners about EPHT NCDM collection and formatting guidance with programs such as ADEQ, CLPPP, Climate and Health, biomonitoring, toxicology, birth defects, SafeWATCH in order to gather data on existing and new NCDM. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | Complete | Connected with new programs at ADEQ (air quality division) and within ADHS (office of continuous improvement and pre-hospital information & EMS registry system) | Some data sets would require a secure portal to be in place before we discussed data sharing.
|  | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Technology and Informatics Teams and Science and Content team will develop scripts and SOPs (e.g. SAS Programs) to help partner programs which support AZ EPHT to help expedite data call uploads (e.g. WQL,CLP2,CLP4,BD, PWS). | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete
|  | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Science and Content Team (epidemiologist and PI) will establish relationship with university for assisting on collaborative public health project using EPHT data and teaching university students about EPHT. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4 | Complete | Entered into a contract with University of Arizona College of Public Health to formalize and support these activities
| Monitor the Impact and Performance of Program Activities | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | CDC Preventive Medicine Fellow assists Science and Content Team on identifying PHA opportunities and writing up quarterly PHAs to CDC. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Complete | 3 public health actions were submitted during quarters 3 and 4 of year 1 | Difficult to measure impacts of actions as that often takes time. As a young program, many actions that we are doing now we hope will become PHA's, but we will not know the true impacts for some time.
|  | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | CDC Preventive Medicine Fellow will lead program services team in developing annual evaluation plan and capturing evaluation results and performance report for evaluation reporting. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | In Progress | An evaluation plan was developed and data collection is ongoing.
|  | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | AZ Science and Content, Technology and Informatics, Program Marketing and Outreach, and Program Services teams formed in year 1 will meet by webinar, in person, or teleconference to assist in portal review and updates. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Complete
|  | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | AZ PMO Team led by health educator will ask technology and informatics team to use Google Analytics to capture web statistics to submit to CDC and help inform program evaluation. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4 | Complete
|  | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | AZ Science and Content team will use tracking data to help jurisdictions and partners identify public health concerns and use data to monitor intervention effectiveness using time series data. Data can contribute to local and state health assessment plans and improvement plans. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4 | Complete
|  | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Technology and Informatics Team will work with IT leadership to ensure data metrics help align with needs for state health improvement plan and county health improvement plan metrics that may use tracking data to help monitor effectiveness. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4 | Complete | Actively working with office of continuous improvement to identify metrics required for state health assessment and state health improvement plan | Some metrics need to be developed and require coordination with outside partners (i.e. need to develop an air quality metric that requires working with AZ Dept of Environmental Quality)
|  | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | AZ PMO will post updates and announcements about grantee tracking activiites to Tracking listserv and on social media about the impact of program activities on public health in AZ. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4 | Complete

## DONT DELETE Ranges for Workplan
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year