## Instructions
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Annual Performance Report (APR) - Section I
Budget Period: August 1, 2020 - July 31, 2021(Budget Year 4)
Reporting Period: February 1, 2020 - January 31, 2021.
Instructions Please use this workbook to document progress for your Budget Year 4 Work Plan as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section I of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)." The Work Plan tab includes the Year 4 plan you submitted in your 2020 APR. Columns I-L, with the orange Continuation Report (Section I) banner, are where you should enter information about your progress. For each activity, select the Current Status from the dropdown menu (not started, complete, in progress, or behind schedule) and provide relevant information under Successes, Challenges, and CDC Support Needed.
Technical Support If you need technical support when using this template, email your project officer.

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
Arizona Environmental Public Health Tracking Program Project Narrative Budget Year 4
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan." Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
SCIENCE AND CONTENT | Conduct Program Marketing and Outreach
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Grantee will update and implement annual communication plan. Communication activites implemented will include regular updates to internal staff, stakeholders,university partners, TAG members and the general public on Tracking activites including new data uploads and other new features on the Data Explorer. This will be done through call out boxes on the website, newsletter updates, and social media posts. Grantee will also participate in program wide communcation activities including Tracking Awareness Week 2020. Grantee will continue to promote and market the Tracking Network (local & national) to new audiences to include health science librarians , ADHS legislative liasion, and city level officials. These presentations will include content on data avaliable on both networks, how to use the Data Explorer, and potential uses for the data. Additional Tracking communication messages will be developed and disseminated to inform Tracking users and agency social media followers about program activities and new resources. These communication products will include audience profiles for Tracking users and factsheets on health outcomes prioritized by TAG and needs assessments. Efforts will be led by our EPHT health education team (lead: Health Educator, Risk Communication Specialist, and IT Web Designer). In addition, a comunication team will work monthly to discuss social media content, webstat reviews, and planning out other communication activites outlined in the communication plan. The group will communicate by in-person meetings at least bi-weekly, telephone, and email. Overall team meetings with other EPHT teams including Science and Content, Technology and Informatics, and Program Services will occur at least monthly to ensure a shared vision. | Activity 1) Review previous year's communication plan and re-evaluate metrics. Update communication plan according to CDC guidance. Communication team (health educator, evaluator, and epidemiologist) will meet monthly to execute communication plan activites. (New epidemiologist Carmen will fulfill CDC medicine fellow Sally Ann's evaluator role and back-up epidemiologist in this new workplan.) Activity 2) Participate in Tracking Awareness Week (2020) by posting social media posts and a blog post. Activity 3) Post announcements on Tracking Website and Data Explorer to call attention to new data, new features, and new communication products. Several new communication products include audience profiles for tracking users and expanding our How-to-Use video tutrorial series will be posted during year 4. Distribute quarterly newsletters communicating new data and applications to relevant audiences. Activity 4) Grantee will post social media to Facebook and Twitter regarding grantee portal updates, PHAs, Tracking Awareness Week, and other multi-collaborative grantee communication activities. In addition, grantee will collaborate with internal ADHS staff memembers from Cancer Registry and Birth Defects Prevention to do (social media, newsletter, etc.) outreach during respective awareness weeks. Activity 5) Present on Tracking Program to local and nationally relevant stakeholders (CSTE, NEHA, ASTHO, etc.) and local university students through webinar, conference, or classroom settings. Target local county health departments to collaborate on projects. Send email to all county environmental health departments to provide trainings on Tracking. Distribute existing and new communictions materials during year 4. Activity 6) Grantee will post website updates regarding new and and optional NCDM added to the Data Explorer. Content will highlight the relationship between the environment and health as well as supporting resources websites (internal and external to the agency). Activity 7) Hand out tracking materials (AZ Tracking general info infographic, quick reports infographic) at presentations and other outreach events to include local health department trainings, university presentations, and community outreach events. Activity 8) The grantee will participate in the PMO West-led quarerly communication campaign, Tracking Awareness Week, and other topics brought up by the group. The program will post social media posts and email newsletters to the listserv. Activity 9) Conduct a needs assessment of environmental health needs at the city level and discuss environmental gaps and how the Tracking team can assisst local city governments. Produce 2 custom communication products such as infographics based on needs. Activity 10) Science & Content team will provide Tracking required/optional/non-NCDM written updates on the Data Explorer and information to AZ PMO team for outreach efforts. Activity 11) AZ PMO, Science & Content, and Program Services will meet with Technology & Informatics team to address feedback and improve Data Explorer with recommendations by users of the data. Teams will utilize university classes, TAG feedback, and feedback form on Data Explorer for evaluation. Activity 12) PMO will do outreach to university students, new internal health department staff, and other areas of the health department (not contacted yet) about EPHT trainings and internship opportunities. | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 4
|  |  | 2 | 2 | 2 | 2 | 8
Initiate, Maintain, and Expand Partnerships
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Grantee will update and implement partnership plan to develop and maintain relationships with previous and new partners. Grantee will continue to communicate with ADHS tribal liason to ensure Tribal connections are maintained and enhanced. We will continue to maintain and expand our internal partners including: Childhood Lead Poisoning Prevention Program, Enviromental Toxicology, Climate and Health Program, Office of Cancer Registry, Birth Defects Program, Safe WATCH, Biomonitoring Program, Public Health Emergency Prepardeness Program, and Arizona Radiation Regulatory Agency. We will also expand our external partnerships with traditonal partners like county health departments (e.g. Maricopa County Public Health Department), universities (Arizona State University, University of Arizona, Northern Arizona University), and Arizona Department of Enviromental Quality as well as non-traditional partners like Arizona Department of Transportation, non-profit organizations, healthcare organizations, and tribal governments. The grantee will send out press releases and EPHT training materials (e.g. how-to-video) to media and provide responses and interviews to reporters regarding data, PHAs, and other partner activities. The grantee will also partner on national conferences and webinars with PMO West or EPHT content workgroups. Efforts will be led by our EPHT health education team (lead: Health Educator, Risk Communication Specialist, and IT Web Designer). The group will communicate by in-person meetings at least bi-weekly, telephone, and email. Overall team meetings with other EPHT teams including Science and Content, Technology and Informatics, and Program Services will occur at least monthly to ensure a shared vision. | Activity 1) Update partnership plan. Evaluate TAG members to assess partnership status and needs. Identify new/innovative external partners and conduct outreach to propose trainings and resources available. Activity 2) Hold at least 2 TAG meetings per year, at least 1 of which will be an in-person meeting. Convene TAG EPHT meeting group to provide quarterly updates to TAG memebers and share how feedback and issues were addressed from past meetings. Activity 3) Lecture at local universities and host at least one intern. Continue to maintain relationship with University of Arizona College of Public Health Program, Arizona State University, and Northern Arizona University. Expand relationships to community colleges and work to inform university health science librarians about Tracking program. Activity 4) Send out press release through agency media channels (print news, tv, and radio) regarding Data Explorer updates, PHA's, or trends found in data. Respond to any media requests by providing subject matter expert interview. Outreach to media partners with use of EPHT Data Explorer training materials (web-based or in person). Activity 5) Co-present at a national or regional meeting or webinar (e.g. CSTE, AMS, NEHA, APHA) regarding Tracking related project with PMO West or EPHT Content Workgroups. Activity 6) Grantee will gather feedback from AZ stakeholders (e.g. users, TAG) on potential new NCDM or non-NCDM. Feedback can be provided via CWGs and locally new data sets and indicators will be explored based on feedback. Grantee will participate in CWGs and help complete CWG activities such as scoping reports, white papers, and piloting of indicators. Activity 7) AZ Technology and Informatics will enlist Tracking team help for guidance on additional features to add to the Data Explorer based on stakeholder feedback of Data Explorer. Activity 8) AZ PMO will work with Science & Content team to create trainings and content for public health & non-public health stakeholders regarding how to use AZ Data Explorer to support their work.
TECHNOLOGY AND INFORMATICS
Identify and Integrate Public Health and Environmetnal Data
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The grantee will continue to evaluate each dataset as per CDC recommendations through the CDC Metadata Creation Tool for NCDM. NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC Secure Access Management System (SAMS). Optional NCDM will be collected, formatted, and submitted as per CDC guidance document. NCDM will be uploaded into grantee Data Explorer. The program will identify additional indicators by engaging local partners through TAG meetings, presentations, and outreach. Science and Content Workgroup Staff will participate in grantee CWG. Arizona Science and Content Workgroup staff will participate in grantee meetings. The Program has partnered with MCDPH and ADEQ through a sub-contract in order to gather perspectives in display of air and water quality data and for novel data element additions to Tracking. Analysis will reduce data gaps by creating datasets at sub-county scale (primary care area or other small geographical area). Delegation of work will be led by the Science and Content Capacity Team (PI, Epidemiologists, Risk Communication Specialist, Agency Liaison/Policy Advisor, GIS Developer, GIS Supervisor, IT Manager). | Activity 1) Evaluate each dataset using criteria (CDC EPHTN Tracking Network Profile Version 1.2 for metadata standards) in metadata reports through the CDC Metadata Creation Tool for NCDM. We will participate in projects regarding CWG and evaluate CWG work such as sub-county cancer data. Science and Content team will coordinate with other data stakeholders within the department such as birth defects, cancer, and ADEQ for input. Activity 2) NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC. In conjunction, NCDM will be uploaded into grantee Tracking Data Explorer supported by ESRI GIS software and SAS for data analysis. The program will maintain two epidemiologists for back-up purposes for completing data in a timely manner. Activity 3) Required and optional NCDM will be collected, formatted, and submitted using the guide “Standards for Nationally Consistent Data and Measures within the CDC’s National Environmental Public Health Tracking Network Version 4.0.” Data will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC Secure Access Management System (SAMS). Activity 4) The program will identify indicators needed by local stakeholders by engaging with local partners through TAG meetings and presentations with partners and universities. New indicators will be added to the Data Explorer and communicated to stakeholder groups through newsletters, TAG meetings, and presentations. Activity 5) Arizona Science and Content Workgroup staff will participate in grantee teleconference, webinars, and in-person grantee meetings to provide input on improvement and development of NCDMs. Staff will participate in CWGs and work on piloting indicators, scoping reports, etc. Activity 6) The Program will partner with the Arizona Department of Environmental Quality (ADEQ) through a sub-contract in order to gather their perspectives the display of air and water quality data from ADEQ (such as representativeness, data granularity, time scale, and accuracy). The program will also work with the TAG to identify limitations and solutions for data in environmental or public health data sets (e.g. sub-county). Activity 7) Technology and Informatics team will ensure that programmers and software are available that Science and Content team can use to create existing & new NCDM in XML for submission. Program will ensure at least .5 FTE staff dedicated for IT and ensure that SAS is purchased or forms completed to get from CDC on timely basis to do work. Activity 8) AZ PMO will create website plain messaging language to accompany new NCDM datasets on state portal and meet with AZ Science and Content Team to ensure accuracy of website information.
COMMUNICATIONS
Analyze and Apply Data to Translate Science into Action
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Epidemiologists with support from the PI will conduct routine analysis and data-cleaning of required and optional NCDM to evaluate quality and completeness of data using SAS and the CDC DIVE validation tool. Pilot analyses will also be done on CWG indicators under development. The Epidemiologists will develop SAS programs and protocols to routinely use Tracking data to identify vulnerable populations using numbers, rates, and percentages to identify elevated risk areas. Results will be shared with stakeholders via email, media, and meetings. From this information, health education material will be developed to aid in prevention efforts for priority areas. The Program has partnered with MCDPH through a sub-contract to gain a program epidemiologist. Data on heat illness in children will also be used in an advanced time-series analysis to inform the development of recommendations for schools on how to mitigate the effects of extreme heat among students. Routine discriptive analysis will be used on NCDM data for surveillance reports, such as heat-related illness and cold-related illness. Delegation of work will be led by the Science and Content Capacity Team (PI, Epidemiologist, Risk Communication Specialist, Agency Liaison/Policy Advisor, GIS Developer, GIS Supervisor). | Activity 1) Epidemiologists with support from the PI will conduct routine descriptive analysis of NCDM using SAS and epidemiological analysis. Surveillance reports will be generated and posted on the AZ EPHT website, such as for heat-related illness and cold-related illness. Key talking points from descriptive analysis will be developed for planned workshops (1) EPHT in Tribal Lands, (2) State Heat Meeting, and (3) TAG in-person meeting. Activity 2) Epidemiologists will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-NCDM data in the Data Explorer. For example, report on trends in numbers, crude rates, age-adjusted rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. Activity 3) The Program will partner with (MCDPH) through a sub-contract to gain a program epidemiologist. Scope of work will include developing SAS programs and protocols for conducting routine analysis using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards at the county and sub-county scale. Timely reporting of the epidemiologist's findings will help the program's coordination efforts for further investigation with other state and local partners as well as new insights/solutions. The program's epidemiologist will analyze Tracking Data NCDM and report back quarterly of findings through email, teleconference, or in person meetings. Activity 4) Use Tracking Data to support and inform other internal programs and plans such as Climate and Health, CLPPP, Birth Defects, and ADEQ. For example, summarize annual air quality data in the state for State Health Assessment Report and help CLPPP evaluate their Childhood Blood Lead Risk Map and utilization. Activity 5) Tracking data on heat-illness in children will be used to inform the development of recommendations for schools on how to mitigate the effects on students. Impacts of the recommendations will be tracked through evaluation efforts that include a state-wide survey on implementation of school heat policy guidelines in first year. The program will respond to inquiries from partners for new public health action data needed as requested. Activity 6) Science & Content will work with PMO, Program Services, and Technology and Informatics to develop new tools for the Data Explorer that enhance data display and utility. Activity 7) PMO team will do a news release and social media regarding EPHT data. Science and Content team will ensure accurate messages. Activity 8) Science & Content will work with PMO, Program Services, and Technology and Informatics to develop tools to track program activities and analyses that support external partners and health outcomes of the jurisdiction. PI or evaluator will submit PHA's and track PHA outcomes with partners as they are finished over long periods of time to gather necessary information.
Increase Organizational Capacity to Support the Tracking Network
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program will lead, support, and maintain existing Environmental Public Health Tracking Program within state jurisdiction by staffing appropriately to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the Data Explorer, data analysis support, and data updates. The Program will continue to hold Technical Advisory Group Meetings at least once a year and will encourage Working Groups to meet regularly to address priority projects (e.g. development of a secure Data Explorer, development of community profile reports). The Program will facilitate presentations and webinars with stakeholders that describe how to use the Data Explorer and how to find locally-relevant data. The Program will work with University of Arizona and other local universities to develop web-based or in-person training program-specific training modules regarding use case. Internships will be offered working in either program aspects of epidemiology, communications, or GIS. ADHS has a formal internship process established with required documentation for insurance purposes. Local universities are familiar with the ADHS internship coordinator. | Activity 1) Grantee will maintain appropriate staffing to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the AZ Data Explorer, data analysis support, and data updates. Activity 2) Hold Technical Advisory Group Meetings at least twice a year. Additionally, tracking program staff will meet at least once a month to discuss technical capacity and needs. Activity 3) Develop materials and trainings on how to use the Data Explorer. Continue partnerships with University of Arizona to support integration of EPHT into the public health course curriculum. Activity 4) Deliver web-based or in-person EPHT trainings for public health staff (such as ADHS "How to trainings") and students. Activity 5) EPHT Program staff will meet with and teach other internal and external partners about EPHT NCDM collection and formatting guidance with programs such as ADEQ, CLPPP, Climate and Health, biomonitoring, toxicology, birth defects, SafeWATCH in order to gather data on existing and new NCDM. Activity 6) Technology and Informatics Teams and Science and Content team will develop scripts and SOPs (e.g. SAS Programs) to help partner programs which support AZ EPHT to help expedite data call uploads (e.g. WQL,CLP2,CLP4,BD, PWS). Activity 7) Science and Content Team (epidemiologists and PI) will establish relationship with university for assisting on collaborative public health project using EPHT data and teaching university students about EPHT.
PROGRAM SERVICES
Monitor the Impact and Performance of Program Activities
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program will submit public health actions twice per year to the project officer through email. PHAs will also be described in an evaluation report & the APR. The PI will assume responsibility for the document. The Program will develop and implement annual evaluation plans, based on the CDC recommendations. The evaluation plan will be coordinated through the Program Service Workgroup led by the Evaluator and supported by the Principal Investigator. The evaluation plan will also include success stories to document program successes which can be shared on the National Portal. The Science and Content Workgroup, Communications Workgroup, and Technology and Informatics Workgroup assigned staff from AZ will participate in workgroups based on area of expertise using teleconferences, webinars, and providing reviews during in-person grantee meetings. The IT Web Designer will provide website statistics and clicks for various subpages of the Tracking Program to identify the most used through Google Analytics which is standard practice for the agency’s websites. Website statistics will be submitted to the project officer by email twice per year and documented in the evaluation plan/ annual progress report. | Activity 1) AZ Science and Content and Program Services teams will develop an evaluation plan for Year 4 to engage tribal involvement within the TAG and EPHT Program. Results and feedback from Year 3's tribal engagement plan will be used to prepare an action plan to engage members of this stakeholder group. Activity 2) Epidemiologist and evaluator will develop an evaluation plan to evaluate the impact of 2 previously submitted PHAs (1) Heat Awareness Campaign and (2) Childhood Blood Lead Risk Map. Based upon findings, team will work with PI to recommend improvements that will include a timeline for changes for these two activities. Activity 3) AZ Science and Content, Technology and Informatics, Program Marketing and Outreach, and Program Services teams will meet routinely to discuss updates to the Data Explorer and website content. Activity 4) AZ PMO Team led by health educator will ask technology and informatics team to use Google Analytics to capture web statistics to submit to CDC and help inform program evaluation. Activity 5) AZ Technology and Informatics, Science and Content, Program Marketing and Outreach, and Porgram Services teams will utilize cloud-based services to track performance measures and grant activities, specifically PHAs, indicators, presentaitons/trainings, technical assistance requests, evaluation plans/timelines, etc. Activity 6) The Epidemiologist will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-NCDM data in the Data Explorer. For example, report on trends in numbers, crude rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. Activity 7) AZ PMO will post updates and announcements about grantee tracking activites to Tracking listserv and on social media about the impact of program activities on public health in AZ.
Maintain and enhance information technology infrastructure
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Arizona EPHT Data Explorer follows guidance from CDC Tracking Grantee Portal Standards and Recommendations. The Data Explorer will continue to be improved by adding additional features and data visuzaliation options based on user feedback and requests. At the request of the TAG, development of a secure Data Explorer will be further explored with the Data and Research Indicators workgroup of the TAG. The TI team will continue to support ADHS goals of streamlining data applications by migrating the Hospital Compare application to the EPHT Data Explorer. Delegation of work will be led by the EPHT Technology and Informatics Team (GIS Supervisor, GIS Developer, and Web Media Specialist). The GIS Developer will handle a majority of efforts at 1 FTE and rely on the GIS Supervisor and for following state standards and procurement of hardware and software. The GIS Developer will communicate at least weekly by email, phone, and in person meetings with PI to ensure science and content updates are incorporated. The TI team will meet monthly for team website meetings with PI and Science and Content Team staff for exchanging updates. | Activity 1) Grantee will continue to maintain and update the Data Explorer with new NCDM indicators, tools and processes per CDC guidelines. Activity 2) Code will be developed to geocode to subcounty and tract levels using community layers. Imputation methods will be enhanced and maintained. Activity 3) New tool will be created to allow for exploring the data through a simple text based interface, increasing 508 compliance and options for accessing data. Activity 4) The program will evaluate the use of ESRI portal, EM resource api, and esri hub for use in disseminating data to decision makers, stakeholders and the public. Activity 5) The program will conduct feedback surveys and TAG meetings and demos, feedback will be evaluated, prioritized and put into action. Activity 6) The PI and the GIS Developer have access to the CDC EPHT SharePoint Site for downloading newest version of the data validation program (DIVE) and indicator templates, CDC’s Secure Access Management System (SAMS) for secure file transfer and metadata creation tool (MCT) and capability to convert SAS datasets to XML. Activity 7) SAS and SQL and Python scripting will be maintained and developed as needed to ensure that the process of validating and updating data continues to run smoothly. Data and scripts will be integrated into a new EPHT admin site which will serve as the content management system for managing all measures and indicators. Activity 8) Quick reports tool will be updated with new community based indicators, including air quality, birth defects, water quality, and drought. Activity 9) Hospital compare application for viewing locally relevant hospital outcomes will be released and select datasets will be integrated into EPHT. Activity 10) Nationwide community layer will be created and distributed to Tracking Network for use in creating subcounty geographies. Activity 11) EPHT admin site will be enhanced to manage hospital comapre datasets, scripts for automating hospital compare dataset updates will be created. Activity 12) Technology and Informatics team will ensure secure and public Data Explorer are available for Science and Content team to conduct routine descriptive epidemiology of NCDM/Non-NCDM to discover patterns of disease, exposure, and hazards in a timely manner. Epidemiologists will conduct routine analysis. Activity 13) TAG will be asked for feedback during presentations and webinars. Interim emails and surveys to TAG listserve will be conducted as needed to seek input on program decisions. Activity 14) Technology and Informatics team will ensure users have access to the Data Explorer and that internal program staff have access to IT resources for performing NCDM updates/queries.
Supporting Public Health Emergency Response
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
Project Summary below (200 word max)
| The grantee will support the Department's public health emergency response activations for environmental health hazards (heat, wildfires, etc.) and other public health issues (COVID-19, other emergent pathogens, etc.). The grantee will support the Health Emergency Operations Center (HEOC) by providing technical assistance and personnel. This need will be met by providing IT capacity and GIS mapping capabilities; providing staff to track resources and volunteers; providing epidemiological experitise to manage cases and provide support to local and county health departments in response. Communicating risk of health and environmental hazards will be crafted for social media messaging and through phone calls, emails, and webinars as needed. NCDM and non-NCDM data will be used to help evaluate risk in the community. | Activity 1) Support the Health Emergency Operations Center with EPHT expertise; such as environmental epidemiology, GIS mapping, and health education for public health emergencies such as COVID-19, wildfires, and heat. Activity 2) Sharing key messaging about emergent environmental health issues of public health concern through EPHT listserv and social media messages. For example, share information on heat related mortality before the beginning of heat season or address community members or stakeholder concerns regarding chemicals levels in their drinking water (PFAS, lead, etc.) or hazardous waste sites. Activity 3) Utilize NCDM and non-NCDM data to assess the initial impact that COVID-19 had on public health and the environment by assessing air quality measures and transportation utilization. Activity 4) TI resources will be deployed to ensure effective response to the COVID-19 pandemic, opioid crisis, and revamped hospital compare application. Activity 5) COVID-19 data will be routinely processed, geocoded, and analysed. Data will be dissemnated to stakeholders and the public.

## Work Plan
EH17-1702 Budget Period: |  |  | August 1, 2020 - July 31, 2021
Date Submitted: |  |  | 2021-03-22
No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activity description. | Anticipated timeline for completion of project. | Continuation Report (Section I)
Project Title | Activity Title | Strategy | Activity | Activity Description | Timeline | Status | Successes | Challenges | CDC Program Support Needed
Conduct Program Marketing and Outreach | 1 | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Review previous year's communication plan and re-evaluate metrics. Update communication plan according to CDC guidance. Communication team (health educator, evaluator, and epidemiologist) will meet monthly to execute communication plan activites. (New epidemiologist Carmen will fulfill CDC medicine fellow Sally Ann's evaluator role and back-up epidemiologist in this new workplan.) | Q1-Q2 | Complete
| 2 | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Participate in Tracking Awareness Week (2020) by posting social media posts and a blog post. | Q3-Q4 | Complete
| 3 | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Post announcements on Tracking Website and Data Explorer to call attention to new data, new features, and new communication products. Several new communication products include audience profiles for tracking users and expanding our How-to-Use video tutorial series will be posted during year 4. Distribute quarterly newsletters communicating new data and applications to relevant audiences. | Q1-Q4 | In Progress
| 4 | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will post social media to Facebook and Twitter regarding grantee portal updates, PHAs, Tracking Awareness Week, and other multi-collaborative grantee communication activities. In addition, grantee will collaborate with internal ADHS staff memembers from Cancer Registry, Climate, Lead, and Birth Defects Prevention to do (social media, newsletter, etc.) outreach during respective awareness weeks. | Q1-Q4 | Complete | 28 social media posts were sent. Tracking collaborated with Lead, Climate, and Birth Defects programs to promote respective health awareness weaks through our EPHT newsletters. | Tracking social media posts were limited this year due to COVID-specific communications taking priority.
| 5 | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | Present on Tracking Program to local and nationally relevant stakeholders (CSTE, NEHA, ASTHO, etc.) and local university students through webinar, conference, or classroom settings. Target local county health departments to collaborate on projects. Send email to all county environmental health departments to provide trainings on Tracking. Distribute existing and new communictions materials during year 4. | Q1-Q4 | In Progress |  | AZ Tracking has continued to participate in conferences and presentations to promote and train stakeholders on the Tracking Network during the pandemic; however efforts to work with county partners were put on hold due to partners prioritizing activities to COVID response.
| 6 | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will post website updates regarding new and and optional NCDM added to the Data Explorer. Content will highlight the relationship between the environment and health as well as supporting resources websites (internal and external to the agency). | Q1-Q4 | In Progress
| 7 | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Hand out tracking materials (AZ Tracking general info infographic, quick reports infographic) at presentations and other outreach events to include local health department trainings, university presentations, and community outreach events. | Q1-Q4 | In Progress
| 8 | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity | The grantee will participate in the PMO West-led quarerly communication campaign, Tracking Awareness Week, and other topics brought up by the group. The program will post social media posts and email newsletters to the listserv. | Q1-Q4 | Complete
| 9 | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Conduct a needs assessment of environmental health needs at the city level and discuss environmental gaps and how the Tracking team can assisst local city governments. Produce 2 custom communication products such as infographics based on needs. | Q3-Q4 | In Progress
| 10 | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Science & Content team will provide Tracking required/optional/non-NCDM written updates on the Data Explorer and information to AZ PMO team for outreach efforts. | Q1-Q4 | Complete
| 11 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | AZ PMO, Science & Content, and Program Services will meet with Technology & Informatics team to address feedback and improve Data Explorer with recommendations by users of the data. Teams will utilize university classes, TAG feedback, and feedback form on Data Explorer for evaluation. | Q1-Q4 | Complete | Took feedback from TAG to evaluate enhancing data portal to add sub-county data and evaluated census tract data submitted during fall data submission. Received support from data stewards to publish census tract data in the future on our data portal. Feedback received from local community college stakeholder: "Without the easy to access information that the EPHT explorer provides (and other dashboard, the Community Profiles Dashboard), finding an answer to students' research questions would be difficult or near impossible. This resource that the team at AZDHS developed helps give opportunities for equitable access for course-based undergraduate research experiences in data science and statistics for students in Arizona. This is also a positive for our community and engagement with the community since students have traditionally not had access to these opportunities, or the available spots to participate in undergraduate research were limited to funding support."
| 12 | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | PMO will do outreach to university students, new internal health department staff, and other areas of the health department (not contacted yet) about EPHT trainings and internship opportunities. | Q1-Q4 | Complete | Hosted one graduate student intern in Summer 2020 to develop a community college EPHT curriculum. We received a Public Health Associate from CDC in Fall 2020. Continued to work with Phoenix College to use Data Explorer for research project and demonstrated it's use and functionality.
Initiate, Maintain, and Expand Partnerships | 1 | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Update partnership plan. Evaluate TAG members to assess partnership status and needs. Identify new/innovative external partners and conduct outreach to propose trainings and resources available. | Q1-Q4 | In Progress |  | Partnerhsip plan was updated on October 31, 2020. Outreach with TAG and reavluation of members will be conducted in the second half of this grant cycle.
| 2 | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Hold at least 2 TAG meetings per year, at least 1 of which will be an in-person meeting. Convene TAG EPHT meeting group to provide quarterly updates to TAG memebers and share how feedback and issues were addressed from past meetings. | Q1-Q4 | In Progress |  | Tracking held first TAG meeting of this grant year on January 26, 2021 by webinar. There were 29 attendess which is lower than previous years but to be expected with COVID challenges. | Suggestion of methods to keep TAG informed and engaged.
| 3 | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Lecture at local universities and host at least one intern. Continue to maintain relationship with University of Arizona College of Public Health Program, Arizona State University, and Northern Arizona University. Expand relationships to community colleges and work to inform university health science librarians about Tracking program. | Q1-Q4 | Complete | The AZ Tracking PI has delivered several guest lectures to AZ unversities. In addition we conducted outreach to community colleges to assess the need for envrionmental health and Tracking related content. Through feedback surveys we are working to put together a Tracking curriculum for community colleges.
| 4 | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | Send out press release through agency media channels (print news, tv, and radio) regarding Data Explorer updates, PHA's, or trends found in data. Respond to any media requests by providing subject matter expert interview. Outreach to media partners with use of EPHT Data Explorer training materials (web-based or in person). | Q1-Q4 | In Progress |  | AZ Tracking completed and scheduled to send out Tracking for media newsletter but this was delayed due to COVID. We are planning to resume this activity in summer of 2021.
| 5 | Communications 2 (C2) | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner | Co-present at a national or regional meeting or webinar (e.g. CSTE, AMS, NEHA, APHA) regarding Tracking related project with PMO West or EPHT Content Workgroups | Q1-Q4 | Complete
| 6 | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Grantee will gather feedback from AZ stakeholders (e.g. users, TAG) on potential new NCDM or non-NCDM. Feedback can be provided via CWGs and locally new data sets and indicators will be explored based on feedback. Grantee will participate in CWGs and help complete CWG activities such as scoping reports, white papers, and piloting of indicators. | Q1-Q4 | Complete | Received feedback from stakeholders in the heat community during spring 2020 to enhance risk factor and comorbidities elements within heat-related illness datasets. Added key variables to heat related illness surveillance report and presented this information in the 2020 Heat Season Recap Webinar and American Meteorological Sociaty Annual Meeting. Data was aggregated by county and different temporal aggregations to determine if it was feasible to display within the Data Explorer. AZ Tracking received support to add COVID-19 case and rate datasets to the Data Explorer once data is finalized. | CWGs were paused over spring/summer/fall due to COVID-19 response.
| 7 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | AZ Technology and Informatics will enlist Tracking team help for guidance on additional features to add to the Data Explorer based on stakeholder feedback of Data Explorer. | Q1-Q4 | In Progress | Addition of COVID datasets is planned | Resources diverted to COVID-19 response
| 8 | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | AZ PMO will work with Science & Content team to create trainings and content for public health & non-public health stakeholders regarding how to use AZ Data Explorer to support their work. | Q1-Q4 | Complete | Developed fact sheets on how public health professionals and general public can use Data Explorer; conducted several trainings at local colleges and universities on how to use Data Explorer like Phoenix College STEAM Day.
Identify and Integrate Public Health and Environmental Data | 1 | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Evaluate each dataset using criteria (CDC EPHTN Tracking Network Profile Version 1.2 for metadata standards) in metadata reports through the CDC Metadata Creation Tool for NCDM. We will participate in projects regarding CWG and evaluate CWG work such as sub-county cancer data. Science and Content team will coordinate with other data stakeholders within the department such as birth defects, cancer, and ADEQ for input. | Q1-Q4 | Complete | Science and Content is part of the Health Equity and Hospitalization CWGs and will work with data stakeholders at ADHS for input in the coming months. Science and Content group reviewed the sub-county data piloted on CDC's secure portal and provided a summary report to ADHS data stewards and Technical Advisory Group. |  | Next steps for the sub-county data submission pilot
| 2 | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC. In conjunction, NCDM will be uploaded into grantee Tracking Data Explorer supported by ESRI GIS software and SAS for data analysis. The program will maintain two epidemiologists for back-up purposes for completing data in a timely manner. | Q1-Q4 | Complete
| 3 | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Required and optional NCDM will be collected, formatted, and submitted using the guide “Standards for Nationally Consistent Data and Measures within the CDC’s National Environmental Public Health Tracking Network Version 4.0.” Data will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC Secure Access Management System (SAMS). | Q1-Q4 | Complete | We had two successful data submissions, including sub-county pilot submission in fall 2020.
| 4 | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | The program will identify indicators needed by local stakeholders by engaging with local partners through TAG meetings and presentations with partners and universities. New indicators will be added to the Data Explorer and communicated to stakeholder groups through newsletters, TAG meetings, and presentations. | Q1-Q4 | In Progress | We received agency approval to display COVID-19 counts and rates in our Data Explorer for 2020. We plan to post this new indicator in the new year once finalized. Based on feedback from the State Heat Meeting, we explored several new risk factors associated with heat-related illness and death to be displayed in the Data Explore. Exploratory work is still in progress for heat deaths. | Resources were diverted to respond to COVID-19
| 5 | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Arizona Science and Content Workgroup staff will participate in grantee teleconference, webinars, and in-person grantee meetings to provide input on improvement and development of NCDMs. Staff will participate in CWGs and work on piloting indicators, scoping reports, etc. | Q1-Q4 | Complete
| 6 | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | The Program will partner with the Arizona Department of Environmental Quality (ADEQ) through a sub-contract in order to gather their perspectives the display of air and water quality data from ADEQ (such as representativeness, data granularity, time scale, and accuracy). The program will also work with the TAG to identify limitations and solutions for data in environmental or public health data sets (e.g. sub-county). | Q1-Q4 | Complete
| 7 | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Technology and Informatics team will ensure that programmers and software are available that Science and Content team can use to create existing & new NCDM in XML for submission. Program will ensure at least .5 FTE staff dedicated for IT and ensure that SAS is purchased or forms completed to get from CDC on timely basis to do work. | Q1-Q4 | Complete | ADHS maintained .5 IT staff. SAS was renewed. | Our Applications Developer position was vacant from 9/22/21 to 2/8/21
| 8 | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | AZ PMO will create website plain messaging language to accompany new NCDM datasets on state portal and meet with AZ Science and Content Team to ensure accuracy of website information. | Q1-Q4 | In Progress
Analyze and Apply Data to Translate Science Into Action | 1 | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Epidemiologists with support from the PI will conduct routine descriptive analysis of NCDM using SAS and epidemiological analysis. Surveillance reports will be generated and posted on the AZ EPHT website, such as for heat-related illness and cold-related illness. Key talking points from descriptive analysis will be developed for planned workshops (1) EPHT in Tribal Lands, (2) State Heat Meeting, and (3) TAG in-person meeting. | Q1-Q4 | Complete | Data from descriptive analyses was presented during the 2020 Heat Season Recap webinar and TAG virtual meeting. Routine descriptive analysis and reports are conducted for heat- and cold-related illnesses and deaths. Additionally, work done to review COVID-19 case investigation metrics and trends supported the state's emergency response in 2020. | The EPHT in Tribal Lands meeting was postponed due to COVID-19.
| 2 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Epidemiologists will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-NCDM data in the Data Explorer. For example, report on trends in numbers, crude rates, age-adjusted rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. | Q1-Q4 | Complete | New SAS programs were written to (1) evaluate heat- and cold- related illness risk factors such as place of injury, preceding activity, substance use and comorbidities; (2) support COVID-19 response by evaluating data trends and internal metrics; and (3) explore occupational health indicators within the available hospital discharge dataset. Results and outputs from these were shared with internal and external stakeholders. |  | Support from journal club to provide processes and sample code for routine analysis of NCDMs
| 3 | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | The Program will partner with (MCDPH) through a sub-contract to gain a program epidemiologist. Scope of work will include developing SAS programs and protocols for conducting routine analysis using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards at the county and sub-county scale. Timely reporting of the epidemiologist's findings will help the program's coordination efforts for further investigation with other state and local partners as well as new insights/solutions. The program's epidemiologist will analyze Tracking Data NCDM and report back quarterly of findings through email, teleconference, or in person meetings. | Q1-Q4 | Complete | Epidemiologist spent time updating surveillance reports, validating county and sub-county datasets during submission windows, reviewing suppression and feasibility of displaying sub-county aggregations on the AZ Data Explorer, enhancing heat-related illness surveillance, and evaluating internal COVID-19 case investigation metrics and trends.
| 4 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Use Tracking Data to support and inform other internal programs and plans such as Climate and Health, CLPP, Birth Defects, and ADEQ. For example, summarize annual air quality data in the state for State Health Assessment Report and help CLPPP evaluate their Childhood Blood Lead Risk Map and utilization. | Q1-Q4 | Complete | Tracking Data was used to support the Arizona Department of Water Resources for their Annual Drought Preparedness Plan 2020.
| 5 | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Tracking data on heat-illness in children will be used to inform the development of recommendations for schools on how to mitigate the effects on students. Impacts of the recommendations will be tracked through evaluation efforts that include a state-wide survey on implementation of school heat policy guidelines in first year. The program will respond to inquiries from partners for new public health action data needed as requested. | Q1-Q4 | In Progress | Tracking Data was used to develop heat thresholds for schools to implement prevention measures and controls during hot temperatures. A new school heat policy guidance document was developed and is under review by the Arizona Department of Education | COVID-19 Response delayed the implementation of new school heat policy guidance document in Arizona schools
| 6 | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Science & Content will work with PMO, Program Services, and Technology and Informatics to develop new tools for the Data Explorer that enhance data display and utility. | Q1-Q4 | In Progress |  | Resources diverted to the COVID-19 response
| 7 | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | PMO team will do a news release and social media regarding EPHT data. Science and Content team will ensure accurate messages. | Q1-Q4 | In Progress
| 8 | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Science & Content will work with PMO, Program Services, and Technology and Informatics to develop tools to track program activities and analyses that support external partners and health outcomes of the jurisdiction. PI or evaluator will submit PHA's and track PHA outcomes with partners as they are finished over long periods of time to gather necessary information. | Q1-Q4 | Complete
Maintain and Enhance Information Technology Infrastructure | 1 | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements | Grantee will continue to maintain and update the Data Explorer with new NCDM indicators, tools and processes per CDC guidelines | Q1-Q4 | Complete
| 2 | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Code will be developed to geocode to subcounty and tract levels using community layers. Imputation methods will be enhanced and maintained | Q1-Q4 | Complete
| 3 | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | New tool will be created to allow for exploring the data through a simple text based interface, increasing 508 compliance and options for accessing data. | Q1-Q4 | Behind Schedule |  | Resources diverted to COVID-19 response
| 4 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | The program will evaluate the use of ESRI portal, EM resource api, and esri hub for use in disseminating data to decision makers, stakeholders and the public | Q1-Q4 | Complete | ESRI Portal was evaluated and deemed non-essential at that time. However new use cases require that we revisit the use of this technology. The EMResource API was purchased from Juvare and we successfully pull data from all AZ hospitals into an EPHT database that is then shared with ADHS staff for analysis and dashboard creation. ESRI HUB was purchased and utilized to create secure user profiles for multiple applications including a funeral home capacity tracker and a post acute care capacity tracker. | The COVID-19 response is ever changing and we must continue to evaluate how these tools can be applied, Including a reevaluation of Portal to provide secure data layers to ADHS partners
| 5 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | The program will conduct feedback surveys and TAG meetings and demos, feedback will be evaluated, prioritized and put into action. | Q1-Q4 | Complete
| 6 | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | The PI and the GIS Developer have access to the CDC EPHT SharePoint Site for downloading newest version of the data validation program (DIVE) and indicator templates, CDC’s Secure Access Management System (SAMS) for secure file transfer and metadata creation tool (MCT) and capability to convert SAS datasets to XML. | Q1-Q4 | Complete | Successfully used SDX gateway | New system to replace SAMS
| 7 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | SAS and SQL and Python scripting will be maintained and developed as needed to ensure that the process of validating and updating data continues to run smoothly. Data and scripts will be integrated into a new EPHT admin site which will serve as the content management system for managing all measures and indicators. | Q1-Q4 | In Progress
| 8 | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Quick reports tool (similar to CDC's Info By Location) will be updated with new community based indicators, including air quality, birth defects, water quality, and drought. | Q1-Q4 | Behind Schedule |  | Resources diverted to COVID-19 response
| 9 | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Hospital compare application for viewing locally relevant hospital outcomes will be released and select datasets will be integrated into EPHT | Q1-Q4 | In Progress | The standalone Hospital Compare application was launched | Adding Hospital Compare data to EPHT has been delayed due to resource diversion to the COVID-19 Response
| 10 | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Nationwide community layer will be created and distributed to Tracking Network for use in creating subcounty geographies. | Q1-Q4 | In Progress | A National Communities group was created and shared with CDC staff and grantees as a place to share GIS work on sub-county data creation. Methodology is mostly complete and many steps have been completed. | Progress was halted due to the COVID-19 response
| 11 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | EPHT admin site will be enhanced to manage hospital comapre datasets, scripts for automating hospital compare dataset updates will be created | Q1-Q4 | Behind Schedule |  | Resources diverted to COVID-19 response
| 12 | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Technology and Informatics team will ensure secure and public Data Explorer are available for Science and Content team to conduct routine descriptive epidemiology of NCDM/Non-NCDM to discover patterns of disease, exposure, and hazards in a timely manner. Epidemiologists will conduct routine analysis. | Q1-Q4 | Complete
| 13 | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | TAG will be asked for feedback during presentations and webinars. Interim emails and surveys to TAG listserve will be conducted as needed to seek input on program decisions. | Q1-Q4 | Complete | In January 2021, AZ EPHT surveyed TAG members on program updates provided throughout the TAG meeting.
| 14 | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Technology and Informatics team will ensure users have access to the Data Explorer and that internal program staff have access to IT resources for performing NCDM updates/queries. | Q1-Q4 | Complete
Increase Organizational Capacity to Support the Tracking Network | 1 | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will maintain appropriate staffing to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the AZ Data Explorer, data analysis support, and data updates. | Q1-Q4 | Complete |  | COVID-19 delayed infrastructure updates to Data Explorer and applications developer position was vacant for several months
| 2 | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Hold Technical Advisory Group Meetings at least twice a year. Additionally, tracking program staff will meet at least once a month to discuss technical capacity and needs. | Q1-Q4 | In Progress | One TAG meeting was held during this reporting period. | COVID-19 response activities postponed a planned meeting
| 3 | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Develop materials and trainings on how to use the Data Explorer. Continue partnerships with University of Arizona to support integration of EPHT into the public health course curriculum | Q1-Q4 | In Progress | College curriculum completed but yet to be implemented in classrooms
| 4 | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Deliver web-based or in-person EPHT trainings for public health staff (such as ADHS "How to trainings") and students | Q1-Q4 | Complete | Presented several topics to Arizona Sanitarian Council virtual conference: EPHT Program, Heat Illness, PFAS, Methanol Poisonings, Wildfires
| 5 | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | EPHT Program staff will meet with and teach other internal and external partners about EPHT NCDM collection and formatting guidance with programs such as ADEQ, CLPPP, Climate and Health, biomonitoring, toxicology, birth defects, SafeWATCH in order to gather data on existing and new NCDM. | Q1-Q4 | Complete
| 6 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Technology and Informatics Teams and Science and Content team will develop scripts and SOPs (e.g. SAS Programs) to help partner programs which support AZ EPHT to help expedite data call uploads (e.g. WQL,CLP2,CLP4,BD, PWS). | Q1-Q4 | In Progress |  | Resources diverted to COVID-19 response
| 7 | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Science and Content Team (epidemiologists and PI) will establish relationship with university for assisting on collaborative public health project using EPHT data and teaching university students about EPHT. | Q1-Q4 | Complete | AZ Tracking has continued to work with the major Arizona Universities through guest lectures. In addition, we hosted a remote summer intern from the University of Arizona. Our intern surveyed community college teachers needs for Tracking content and started to develop this curriculum.
Monitor the Impact and Performance of Program Activities | 1 | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | AZ Science and Content and Program Services teams will develop an evaluation plan for Year 4 to engage tribal involvement within the TAG and EPHT Program. Results and feedback from Year 3's tribal engagement plan will be used to prepare an action plan to engage members of this stakeholder group. | Q1-Q4 | Behind Schedule |  | COVID-19 response activities delayed engagement with tribe members
| 2 | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Epidemiologist and evaluator will develop an evaluation plan to evaluate the impact of 2 previously submitted PHAs (1) Heat Awareness Campaign and (2) Childhood Blood Lead Risk Map. Based upon findings, team will work with PI to recommend improvements that will include a timeline for changes for these two activities. | Q1-Q4 | In Progress |  | COVID-19 response delayed this activity
| 3 | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | AZ Science and Content, Technology and Informatics, Program Marketing and Outreach, and Program Services teams will meet routinely to discuss updates to the Data Explorer and website content | Q1-Q4 | Complete
| 4 | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | AZ PMO Team led by health educator will ask technology and informatics team to use Google Analytics to capture web statistics to submit to CDC and help inform program evaluation. | Q1-Q4 | Complete
| 5 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | AZ Technology and Informatics, Science and Content, Program Marketing and Outreach, and Porgram Services teams will utilize cloud-based services to track performance measures and grant activities, specifically PHAs, indicators, presentaitons/trainings, technical assistance requests, evaluation plans/timelines, etc. | Q1-Q4 | Complete | Google Suite is used to track grant activities and performance measures.
| 6 | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | The Epidemiologist will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-NCDM data in the Data Explorer. For example, report on trends in numbers, crude rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. | Q1-Q4 | Complete | SAS programs are in place to routinely report on trends regarding heat- and cold-related illness and shared in meetings with partners.
| 7 | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | AZ PMO will post updates and announcements about grantee tracking activites to Tracking listserv and on social media about the impact of program activities on public health in AZ. | Q1-Q4 | Complete
Supporting Public Health Emergency Response | 1 | Technology and Informatics 1 (TI1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Support the Health Emergency Operations Center with EPHT expertise; such as environmental epidemiology, GIS mapping, and health education for public health emergencies such as COVID-19, wildfires, and heat. | Q1-Q4 | In Progress | Provided data and created multiple dashboards and GIS maps for the Covid response. Created an application for creating daily maps to track wildfires and provided easily understandable SOPs for any preparedness staff to follow. | Covid-19 is ongoing
| 2 | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Sharing key messaging about emergent environmental health issues of public health concern through EPHT listserv and social media messages. For example, share information on heat related mortality before the beginning of heat season or address community members or stakeholder concerns regarding chemicals levels in their drinking water (PFAS, lead, etc.) or hazardous waste sites. | Q1-Q4 | Complete | AZ Tracking sent out 8 newsletter updates to our listserv .The current number of subscribers is 3,180 which is an increase from 2,423 subscribers last reporting year.
| 3 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Utilize NCDM and non-NCDM data to assess the initial impact that COVID-19 had on public health and the environment by assessing air quality measures and transportation utilization. | Q1-Q4 | In Progress | AZ Tracking has supported the COVID-19 pandemic by (1) conducting an environmental health investigation into recalled methanol-based hand sanitizer products, (2) internal evaluation metrics and trends of case investigation and contact tracing data, and (3) assessing the impact of COVID-19 during 2020 heat season in the state. We plan to continue supporting the COVID-19 response by working with ADEQ to review air quality metrics.
| 4 | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | TI resources will be deployed to ensure effective response to the COVID-19 pandemic, opioid crisis, and revamped hospital compare application. | Q1-Q4 | In Progress | The Hospital Compare application was successfully launched. Resources have been and continue to be deployed for the COVID-19 response and the opioid crisis. | COVID-19 response has not left much time to improve our current opioid crisis activities but we have been able to maintain them.
| 5 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | COVID-19 data will be routinely processed, geocoded, and analysed. Data will be dissemnated to stakeholders and the public. | Q1-Q4 | Complete | EPHT geocodes all COVID data daily, has configured an API to pull Hospital data and created GIS based surveillance systems to gather data daily from post acute care facilities and gather data as it's updated from vaccination and testing sites. This data is then analyzed and fed to dashboards for internal and public use. Some of the dashboards are built by EPHT staff and others just consume data processed by EPHT staff. | COVID-19 is ongoing

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year