## Instructions
  Instructions
  Purpose of the Template
  Please use this workbook to document your Budget Year 5 Work Plan and Project Narrative as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section II of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)."
  This workbook includes tabs containing the finalized EH17-1702 Logic Model (blue tab), EH1702 Strategies & Activities (yellow tab) for reference, Project Narrative (purple tab) to provide greater detail regarding your planned projects, and the standardized Work Plan template (green tab). The only tabs which you should fill out are the Project Narrative tab and the Work Plan tab.
Filling out the Project Narrative tab:
  Required Reporting: Use the Project Narrative tab to provide details on how each project outlined in your work plan correspond to the specific strategies, activities, and tasks listed. In the Project Summary section, please provide an overview of the project; be sure to adhere to the 200 word limit for this section. There are no limits on the number of projects proposed. Please keep in mind that some of these projects may be an extension of the project proposed and approved in Budget Year 1 or 2 (i.e. initial EH17-1702 application). The planned projects must support the intent of the original EH17-1702 Notice of Funding Opportunity (NOFO).
  Optional Reporting: Use the right-hand side of each project area (Activity Description) to provide additional details which may not be captured in the work plan or in the project summary section. There is no word limit for this section. You may note comments pertaining to budgetary issues that might hamper the success or completion of the project as originally proposed and approved in Budget Year 1.
Filling out the Work Plan tab:
1. Project Title Create a short title for your project, no more than ten words. Examples include “Asthma Prevention”, “Improving Outdoor Air Quality,” "Improving Portal Infrastructure," "Expanding University Partnerships," etc. You may repeat the same project title in subsequent rows depending on the number of supporting strategies and activities for that project, or combine rows in that column to include the same title. You will provide a detailed description of each project on the Project Narrative tab.
2. Strategy Select a strategy from the drop-down list. Each project should fall into one primary strategy. While you can select supporting strategies and activities related to that primary strategy (ex. A Communications strategy/activity supporting the primary Science strategy/activity for that project), the first strategy you select will be the main focus of your project.
3. Activity Select an activity from the drop-down list. The activity should relate to the strategy you previously selected for that project. Each project should list at least two activities to be implemented in the budget year.
4. Activity Description In five sentences or less, describe the activity you are implementing in Column E.
5. Output Select a prospective output from the drop-down list. You may select one output per activity, or one overall output for the project. If you select multiple outputs for the project, you may find not all activities will correspond with an output.
6. Short-Term Outcome Select a prospective short-term outcome from the dropdown list. You may select one outcome per activity, or one outcome overall for the project.
7. Timeline Select when the specific activity will be accomplished from the drop-down list. Options include Quarter 1 (Q1) through Quarter 4 (Q4), meaning the activity will be accompished at the end of the budget year, or a specific time period (ex. Q1, Q2) .
Technical Support
If you need technical support when using this template, email your project officer.
            EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
      EH17-1702 Annual Performance Report (APR) - Section II only
      Budget Period: August 1, 2021 - July 31, 2022 (Budget Year 5)
      Reporting Period: August 1, 2021 - July 31, 2022

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
Arizona Environmental Public Health Tracking Program's Project Narrative Budget Year 5
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan" (green tab). Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
SCIENCE AND CONTENT | Conduct Program Marketing and Outreach
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Grantee will update and implement annual communication plan. Communication activites implemented will include regular updates to internal staff, stakeholders,university partners, TAG members and the general public on Tracking activites including new data uploads and other new features on the Data Explorer. This will be done through call out boxes on the website, newsletter updates, and social media posts. Grantee will also participate in program wide communcation activities including Tracking Awareness Week 2021. Grantee will continue to promote and market the Tracking Network (local & national) to new audiences to include health science librarians , ADHS legislative liasion, and city level officials. These presentations will include content on data avaliable on both networks, how to use the Data Explorer, and potential uses for the data. Additional Tracking communication messages will be developed and disseminated to inform Tracking users and agency social media followers about program activities and new resources. These communication products will include audience profiles for Tracking users and factsheets on health outcomes prioritized by TAG and needs assessments. Efforts will be led by our EPHT health education team (lead: Health Educator, Risk Communication Specialist, and IT Web Designer). In addition, a comunication team will work monthly to discuss social media content, webstat reviews, and planning out other communication activites outlined in the communication plan. The group will communicate by meeting at least monthly. Overall team meetings with other EPHT teams including Science and Content, Technology and Informatics, and Program Services will occur at least monthly to ensure a shared vision. | Activity 1) Review previous year's communication plan and re-evaluate metrics. Update communication plan according to CDC guidance. Communication team (health educator, evaluator, and epidemiologist) will meet monthly to execute communication plan activities. Activity 2) Participate in Tracking Awareness Week (2021) by posting social media posts and a blog post. Activity 3) Post announcements on Tracking Website and Data Explorer to call attention to new data, new features, and new communication products. Distribute quarterly newsletters communicating new data and applications to relevant audiences. Activity 4) Grantee will post social media to Facebook and Twitter regarding grantee portal updates, PHAs, Tracking Awareness Week, and other multi-collaborative grantee communication activities. In addition, grantee will collaborate with internal ADHS staff members from Cancer Registry, Climate, Lead, and Birth Defects Prevention to do (social media, newsletter, etc.) outreach during respective awareness weeks. Activity 5) Present on Tracking Program to local and nationally relevant stakeholders (CSTE, NEHA, ASTHO, etc.) and local university students through webinar, conference, or classroom settings. Target local county health departments to collaborate on projects. Activity 6) Grantee will post website updates regarding new and optional NCDM added to the Data Explorer. Content will highlight the relationship between the environment and health as well as supporting resources websites (internal and external to the agency). Activity 7) Hand out tracking materials (AZ Tracking general info infographic, quick reports infographic) at presentations and other outreach events to include local health department trainings, university presentations, and community outreach events. Activity 8) The grantee will participate in the PMO West-led quarterly communication campaign, Tracking Awareness Week, and other topics brought up by the group. The program will post social media posts and email newsletters to the listserv. Activity 9) Conduct a needs assessment of non-profits/community-based organizations. Produce 2 custom communication products such as infographics based on needs. Activity 10) Science & Content team will provide Tracking required/optional/non-NCDM written updates on the Data Explorer and information to AZ PMO team for outreach efforts. Activity 11) AZ PMO, Science & Content, and Program Services will meet with Technology & Informatics team to address feedback and improve Data Explorer with recommendations by users of the data. Teams will utilize university classes, TAG feedback, and feedback form on Data Explorer for evaluation. Activity 12) PMO will do outreach to university students, new internal health department staff, and other areas of the health department (not contacted yet) about EPHT trainings and internship opportunities. | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 5
|  |  | 2 | 2 | 2 | 2 | 8
Initiate, Maintain, and Expand Partnerships
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Grantee will update and implement partnership plan to develop and maintain relationships with previous and new partners. Grantee will continue to communicate with ADHS tribal liason to ensure Tribal connections are maintained and enhanced. We will continue to maintain and expand our internal partners including: Childhood Lead Poisoning Prevention Program, Enviromental Toxicology, Climate and Health Program, Office of Cancer Registry, Birth Defects Program, Safe WATCH, Biomonitoring Program, Public Health Emergency Prepardeness Program, and Arizona Radiation Regulatory Agency. We will also expand our external partnerships with traditonal partners like county health departments (e.g. Maricopa County Public Health Department), universities (Arizona State University, University of Arizona, Northern Arizona University), and Arizona Department of Enviromental Quality as well as non-traditional partners like Arizona Department of Transportation, non-profit organizations, healthcare organizations, and tribal governments. The grantee will send out press releases and EPHT training materials (e.g. how-to-video) to media and provide responses and interviews to reporters regarding data, PHAs, and other partner activities. The grantee will also partner on national conferences and webinars with PMO West or EPHT content workgroups. Efforts will be led by our EPHT health education team (lead: Health Educator, Risk Communication Specialist, and IT Web Designer). The group will communicate by in-person meetings at least bi-weekly, telephone, and email. Overall team meetings with other EPHT teams including Science and Content, Technology and Informatics, and Program Services will occur at least monthly to ensure a shared vision. | Activity 1) Update partnership plan. Evaluate TAG members to assess partnership status and needs. Identify new/innovative external partners and conduct outreach to propose trainings and resources available. Activity 2) Hold at least 2 TAG meetings per year. Convene TAG EPHT meeting group to provide quarterly updates to TAG members and share how feedback and issues were addressed from past meetings. Activity 3) Lecture at local universities and host at least one intern. Continue to maintain relationship with University of Arizona College of Public Health Program, Arizona State University, and Northern Arizona University. Activity 4) Send out press release through agency media channels (print news, tv, and radio) regarding Data Explorer updates, PHA's, or trends found in data. Respond to any media requests by providing subject matter expert interview. Outreach to media partners with use of EPHT Data Explorer training materials (web-based or in person). Activity 5) Co-present at a national or regional meeting or webinar (e.g. CSTE, AMS, NEHA, APHA) regarding Tracking related project with PMO West or EPHT Content Workgroups Activity 6) Grantee will gather feedback from AZ stakeholders (e.g. users, TAG) on potential new NCDM or non-NCDM. Feedback can be provided via CWGs and locally new data sets and indicators will be explored based on feedback. Grantee will participate in CWGs and help complete CWG activities such as scoping reports, white papers, and piloting of indicators. Activity 7) AZ Technology and Informatics will enlist Tracking team help for guidance on additional features to add to the Data Explorer based on stakeholder feedback of Data Explorer. Activity 8) AZ PMO will work with Science & Content team to create trainings and content for public health & non-public health stakeholders regarding how to use AZ Data Explorer to support their work.
TECHNOLOGY AND INFORMATICS
Identify and Integrate Public Health and Environmetnal Data
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The grantee will continue to evaluate each dataset as per CDC recommendations through the CDC Metadata Creation Tool and How-to Guides for NCDM. NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC's SDX gateway. Optional NCDM will be collected, formatted, and submitted as per CDC guidance document. NCDM will be uploaded into grantee Data Explorer. The program will identify additional indicators by engaging local partners through TAG meetings, presentations, and outreach. Science and Content Workgroup Staff will participate in grantee CWG. Arizona Science and Content Workgroup staff will participate in grantee meetings. The Program has partnered with MCDPH and ADEQ through a sub-contract in order to gather perspectives in display of air and water quality data and for novel data element additions to Tracking. Analysis will reduce data gaps by creating datasets at sub-county scale (primary care area or other small geographical area). Delegation of work will be led by the Science and Content Team (PI, Epidemiologists, Risk Communication Specialist, Agency Liaison/Policy Advisor, GIS Developer, GIS Manager). | Activity 1) We will evaluate new indicators added to the Data Explorer using the NCDM standards documentation and identify limitations in metadata elements to describe data quality. We will participate in projects regarding CWG and evaluate CWG work such as the effect of transition from ICD-9 to ICD-10 on COPD ED visits and hospitalizations. Science and Content team will coordinate with other data stakeholders within the department such as birth defects, cancer, and ADEQ for input. Activity 2) NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC. In conjunction, NCDM will be uploaded into grantee Tracking Data Explorer supported by ESRI GIS software and SAS for data analysis. The program will maintain two epidemiologists for back-up purposes for completing data in a timely manner. Activity 3) Required and optional NCDM will be collected, formatted, and submitted using the guide “Standards for Nationally Consistent Data and Measures within the CDC’s National Environmental Public Health Tracking Network Version 4.0.” Data will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC SDX secure gateway. Activity 4) The program will identify indicators needed by local stakeholders by engaging with local partners through TAG meetings and presentations with partners and universities. New indicators will be added to the Data Explorer and communicated to stakeholder groups through newsletters, TAG meetings, and presentations, such as pesticide exposures, adult blood lead exposures, and CDC Places. Activity 5) Arizona Science and Content Workgroup staff will participate in grantee teleconference, webinars, and in-person grantee meetings to provide input on improvement and development of NCDMs. Staff will participate in CWGs and work on piloting indicators, scoping reports, etc. Activity 6) The Program will partner with the Arizona Department of Environmental Quality (ADEQ) through a sub-contract in order to gather their perspectives the display of air and water quality data from ADEQ (such as representativeness, data granularity, time scale, and accuracy). The program will also work with the TAG to identify limitations and solutions for data in environmental or public health data sets (e.g. sub-county). Activity 7) Technology and Informatics team will ensure that programmers and software are available that Science and Content team can use to create existing & new NCDM in XML for submission. Program will ensure at least .5 FTE staff dedicated for IT and ensure that SAS is purchased or forms completed to get from CDC on timely basis to do work. Activity 8) AZ PMO will create website plain messaging language to accompany new NCDM datasets on state portal and meet with AZ Science and Content Team to ensure accuracy of website information.
COMMUNICATIONS
Analyze and Apply Data to Translate Science into Action
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Epidemiologists with support from the PI will conduct routine analysis and data-cleaning of required and optional NCDM to evaluate quality and completeness of data using SAS and the CDC DIVE validation tool. Pilot analyses will also be done on CWG indicators under development. The Epidemiologists will develop SAS programs and protocols to routinely use Tracking data to identify vulnerable populations using numbers, rates, and percentages to identify elevated risk areas. Results will be shared with stakeholders via email, media, and meetings. From this information, health education material will be developed to aid in prevention efforts for priority areas. The Program has partnered with MCDPH through a sub-contract to gain a program epidemiologist. Data on heat illness in children will also be used in an advanced time-series analysis to inform the development of recommendations for schools on how to mitigate the effects of extreme heat among students. Routine discriptive analysis will be used on NCDM data for surveillance reports, such as heat-related illness and cold-related illness. Delegation of work will be led by the Science and Content Team (PI, Epidemiologists, Risk Communication Specialist, Agency Liaison/Policy Advisor, GIS Developer, GIS Manager). | Activity 1) Epidemiologists with support from the PI will conduct routine descriptive analysis of NCDM using SAS and epidemiological analysis. Surveillance reports will be generated and posted on the AZ EPHT website, such as for heat-related illness and cold-related illness. Key talking points from descriptive analysis will be developed for planned workshops (1) EPHT in Tribal Lands, (2) State Heat Meeting, and (3) TAG virtual meeting. Activity 2) Epidemiologists will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-NCDM data in the Data Explorer. For example, report on trends in numbers, crude rates, age-adjusted rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. Activity 3) The Program will partner with (MCDPH) through a sub-contract to gain a program epidemiologist. Scope of work will include developing SAS programs and protocols for conducting routine analysis using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards at the county and sub-county scale. Timely reporting of the epidemiologist's findings will help the program's coordination efforts for further investigation with other state and local partners as well as new insights/solutions. The program's epidemiologist will analyze Tracking Data NCDM and report back quarterly of findings through email, teleconference, or in person meetings. Activity 4) Use Tracking Data to support and inform other internal programs and plans such as Climate and Health, CLPP, Birth Defects, and ADEQ. For example, summarize annual heat-related illness heat outcome data for the State Heat Meeting, drought measures for the Arizona Department of Water Resources annual preparedness plans, and help CLPPP evaluate their Childhood Blood Lead Risk Map and utilization. Activity 5) Tracking data on heat-illness in children will be used to inform the development of recommendations for schools on how to mitigate the effects on students. Impacts of the recommendations will be tracked through evaluation efforts that include a state-wide survey on implementation of school heat policy guidelines in first year. The program will respond to inquiries from partners for new public health action data needed as requested. Activity 6) Science & Content will work with PMO, Program Services, and Technology & Informatics to develop new tools for the Data Explorer that enhance data display and utility. Activity 7) PMO team will use news releases and social media to communicate new EPHT data and findings. Science and Content team will ensure accurate messages. Activity 8) Science & Content will work with PMO, Program Services, and Technology & Informatics to develop tools to track program activities and analyses that support external partners and health outcomes of the jurisdiction. PI or evaluator will submit PHA's and track PHA outcomes with partners as they are finished over long periods of time to gather necessary information.
Increase Organizational Capacity to Support the Tracking Network
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program will lead, support, and maintain existing Environmental Public Health Tracking Program within state jurisdiction by staffing appropriately to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the Data Explorer, data analysis support, and data updates. The Program will continue to hold Technical Advisory Group Meetings at least once a year and will encourage Working Groups to meet regularly to address priority projects (e.g. development of a secure Data Explorer, development of community profile reports). The Program will facilitate presentations and webinars with stakeholders that describe how to use the Data Explorer and how to find locally-relevant data. The Program will work with University of Arizona and other local universities to develop web-based or in-person training program-specific training modules regarding use case. Internships will be offered working in either program aspects of epidemiology, communications, or GIS. ADHS has a formal internship process established with required documentation for insurance purposes. Local universities are familiar with the ADHS internship coordinator. | Activity 1) Grantee will maintain appropriate staffing to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the AZ Data Explorer, data analysis support, and data updates. Activity 2) Hold Technical Advisory Group Meetings at least twice a year. Additionally, tracking program staff will meet at least once a month to discuss technical capacity and needs. Activity 3) Develop materials and trainings on how to use the Data Explorer. Continue partnerships with University of Arizona to support integration of EPHT into the public health course curriculum. Activity 4) Deliver web-based or in-person EPHT trainings for public health staff (such as ADHS "How to trainings") and students. Activity 5) EPHT Program staff will meet with and teach other internal and external partners about EPHT NCDM collection and formatting guidance with programs such as ADEQ, CLPPP, Climate and Health, EHC, biomonitoring, toxicology, birth defects, and SafeWATCH in order to gather data on existing and new NCDM. Activity 6) Technology and Informatics Teams and Science and Content team will develop scripts and SOPs (e.g. SAS Programs) to help partner programs which support AZ EPHT to help expedite data call uploads (e.g. WQL,CLP2,CLP4,BD, PWS). Activity 7) Science and Content Team (epidemiologists and PI) will establish and maintain relationship with university for assisting on collaborative public health project using EPHT data and teaching university students about EPHT.
PROGRAM SERVICES
Monitor the Impact and Performance of Program Activities
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Program will submit public health actions twice per year to the project officer through email. PHAs will also be described in an evaluation report & the APR. The PI will assume responsibility for the document. The Program will develop and implement annual evaluation plans, based on the CDC recommendations. The evaluation plan will be coordinated through the Program Service Workgroup led by the Evaluator and supported by the Principal Investigator. The evaluation plan will also include success stories to document program successes which can be shared on the National Portal. The Science and Content Workgroup, Communications Workgroup, and Technology and Informatics Workgroup assigned staff from AZ will participate in workgroups based on area of expertise using teleconferences, webinars, and providing reviews during in-person grantee meetings. The IT Web Designer will provide website statistics and clicks for various subpages of the Tracking Program to identify the most used through Google Analytics which is standard practice for the agency’s websites. Website statistics will be submitted to the project officer by email twice per year and documented in the evaluation plan/ annual progress report. | Activity 1) AZ Science and Content and Program Services teams will develop an evaluation plan for Year 5 to engage tribal involvement within the TAG and EPHT Program. Results and feedback from Year 3's tribal engagement plan will be used to prepare an action plan to engage members of this stakeholder group. Activity 2) Epidemiologist and evaluator will develop an evaluation plan to evaluate the impact of 2 previously submitted PHAs (1) Heat Awareness Campaign and (2) EPHT in Tribal Lands Meeting. Based upon findings, team will work with PI to recommend improvements that will include a timeline for changes for these two activities. Activity 3) AZ Science and Content, Technology and Informatics, Program Marketing and Outreach, and Program Services teams will meet routinely to discuss updates to the Data Explorer and website content. Activity 4) AZ PMO Team led by health educator will ask technology and informatics team to use Google Analytics to capture web statistics to submit to CDC and help inform program evaluation. Activity 5) AZ Technology and Informatics, Science and Content, Program Marketing and Outreach, and Program Services teams will utilize cloud-based services to track performance measures and grant activities, specifically PHAs, indicators, presentations/trainings, technical assistance requests, evaluation plans/timelines, etc. Activity 6) The Epidemiologist will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-NCDM data in the Data Explorer. For example, report on trends in numbers, crude rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. Activity 7) AZ PMO will post updates and announcements about grantee tracking activities to Tracking listserv and on social media about the impact of program activities on public health in AZ.
Maintain and enhance information technology infrastructure
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The Arizona EPHT Data Explorer follows guidance from CDC Tracking Grantee Portal Standards and Recommendations. The Data Explorer will continue to be improved by adding additional features and data visualization options based on user feedback and requests. At the request of the TAG, development of a secure Data Explorer will be further explored with the Data and Research Indicators workgroup of the TAG. The TI team will continue to support ADHS goals of streamlining data applications by migrating the Hospital Compare application to the EPHT Data Explorer. Delegation of work will be led by the EPHT Technology and Informatics Team (GIS Manager, Sr. Applications Developer, Sr. GIS Analyst and Web Media Specialist). The Sr. Applications Developer (.55 FTE) and Sr. GIS Analyst (.40 FTE) will handle a majority of efforts and rely on the GIS Manager (.40 FTE) for following state standards and procurement of hardware and software. The Sr. Applications Developer will communicate at least weekly by email, phone, and in person meetings with PI to ensure science and content updates are incorporated. The TI team will meet monthly for team website meetings with PI and Science and Content Team staff for exchanging updates. | Activity 1) Grantee will continue to maintain and update the Data Explorer with new NCDM indicators, tools and processes per CDC guidelines. Activity 2) Code will be developed to geocode to subcounty and tract levels using community layers. Imputation methods will be enhanced and maintained. Activity 3) New tool will be created to allow for exploring the data through a simple text based interface, increasing 508 compliance and options for accessing data. Activity 4) The program will evaluate the use of ESRI portal, EM resource API, and ESRI hub for use in disseminating data to decision makers, stakeholders and the public. Activity 5) The program will conduct feedback surveys and TAG meetings and demos, feedback will be evaluated, prioritized and put into action. Activity 6) The PI and the Sr. Applications Developer have access to the CDC EPHT SharePoint Site for downloading newest version of the data validation program (DIVE) and indicator templates, CDC’s Secure Access Management System (SAMS) for secure file transfer and metadata creation tool (MCT) and capability to convert SAS datasets to XML. Activity 7) SAS and SQL and Python scripting will be maintained and developed as needed to ensure that the process of validating and updating data continues to run smoothly. Data and scripts will be integrated into a new EPHT admin site which will serve as the content management system for managing all measures and indicators. Activity 8) Quick reports tool will be updated with new community based indicators, including air quality, water quality, and drought. Activity 9) Hospital compare application for viewing locally relevant hospital outcomes will be released and select datasets will be integrated into EPHT. Activity 10) Methodology will be developed to update Arizona's custom sub-county geographies in preparation for release of 2020 Census data and geography. This methodology will be used to complete a nationwide sub-county layer. The layer and methodology will be shared with the Geospatial Data Team as an option for tracking sub-county geography post 2020 Census. Activity 11) EPHT admin site will be enhanced to manage hospital compare datasets, scripts for automating hospital compare dataset updates will be created. Activity 12) Technology and Informatics team will ensure secure and public Data Explorer are available for Science and Content team to conduct routine descriptive epidemiology of NCDM/Non-NCDM to discover patterns of disease, exposure, and hazards in a timely manner. Epidemiologists will conduct routine analysis. Activity 13) TAG will be asked for feedback during presentations and webinars. Interim emails and surveys to TAG listserv will be conducted as needed to seek input on program decisions. Activity 14) Technology and Informatics team will ensure users have access to the Data Explorer and that internal program staff have access to IT resources for performing NCDM updates/queries. Activity 15) The AZ TI team will explore implementing an Open Data Portal for GIS and other data sets. This will include evaluation of ESRI's Open Data Portal applications.
Supporting Public Health Emergency Response
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| The grantee will support the Department's public health emergency response activations for environmental health hazards (heat, wildfires, etc.) and other public health issues (COVID-19, other emergent pathogens, etc.). The grantee will support the Health Emergency Operations Center (HEOC) by providing technical assistance and personnel. This need will be met by providing IT capacity and GIS mapping capabilities; providing staff to track resources and volunteers; providing epidemiological expertise to manage cases and provide support to local and county health departments in response. Communicating risk of health and environmental hazards will be crafted for social media messaging and through phone calls, emails, and webinars as needed. NCDM and non-NCDM data will be used to help evaluate risk in the community. | Activity 1) Support the Health Emergency Operations Center with EPHT expertise; such as environmental epidemiology, GIS mapping (example: for vaccine response), and health education for public health emergencies such as COVID-19, wildfires, and heat. Activity 2) Sharing key messaging about emergent environmental health issues of public health concern through EPHT listserv and social media messages. For example, share information on heat related mortality before the beginning of heat season or address community members or stakeholder concerns regarding chemicals levels in their drinking water (PFAS, lead, etc.) or hazardous waste sites. Activity 3) Utilize NCDM and non-NCDM data to assess the initial impact that COVID-19 had on public health and the environment by assessing air quality measures, transportation utilization, and its affect on non-COVID-19 health conditions. Participate in CDC content workgroups that are relevant to COVID-19 or other emergency response topics. Activity 4) TI resources will be deployed to ensure effective response to the COVID-19 pandemic, opioid crisis, and revamped hospital compare application. Activity 5) COVID-19 data will be routinely processed, geocoded, and analyzed. Data will be disseminated to stakeholders and the public.
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)

## Work Plan
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Work Plan Template
EH17-1702 Budget Period: |  |  |  | August 1, 2021 - July 31, 2022
Date Submitted to CDC: |  |  |  | 2021-03-23
REFERENCE NOTES | No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activty description. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project.
| Project Title | Activity Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline
| Conduct Program Marketing and Outreach | 1 | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Review previous year's communication plan and re-evaluate metrics. Update communication plan according to CDC guidance. Communication team (health educator, evaluator, and epidemiologist) will meet monthly to execute communication plan activities. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2
|  | 2 | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Participate in Tracking Awareness Week (2021) by posting social media posts and a blog post. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4
|  | 3 | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Post announcements on Tracking Website and Data Explorer to call attention to new data, new features, and new communication products. Distribute quarterly newsletters communicating new data and applications to relevant audiences. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | 4 | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Grantee will post social media to Facebook and Twitter regarding grantee portal updates, PHAs, Tracking Awareness Week, and other multi-collaborative grantee communication activities. In addition, grantee will collaborate with internal ADHS staff members from Cancer Registry, Climate, Lead, and Birth Defects Prevention to do (social media, newsletter, etc.) outreach during respective awareness weeks. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | 5 | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | Present on Tracking Program to local and nationally relevant stakeholders (CSTE, NEHA, ASTHO, etc.) and local university students through webinar, conference, or classroom settings. Target local county health departments to collaborate on projects. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | 6 | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Grantee will post website updates regarding new and optional NCDM added to the Data Explorer. Content will highlight the relationship between the environment and health as well as supporting resources websites (internal and external to the agency). | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | 7 | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Hand out tracking materials (AZ Tracking general info infographic, quick reports infographic) at presentations and other outreach events to include local health department trainings, university presentations, and community outreach events. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | 8 | Communications 1 (C1) | C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity | The grantee will participate in the PMO West-led quarterly communication campaign, Tracking Awareness Week, and other topics brought up by the group. The program will post social media posts and email newsletters to the listserv. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | 9 | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Conduct a needs assessment of non-profits/community-based organizations. Produce 2 custom communication products such as infographics based on needs. | Comm- Targeted comm. products & messages | Comm- Engaged partners & users | Q1-Q3
|  | 10 | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Science & Content team will provide Tracking required/optional/non-NCDM written updates on the Data Explorer and information to AZ PMO team for outreach efforts. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | 11 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | AZ PMO, Science & Content, and Program Services will meet with Technology & Informatics team to address feedback and improve Data Explorer with recommendations by users of the data. Teams will utilize university classes, TAG feedback, and feedback form on Data Explorer for evaluation. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 12 | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | PMO will do outreach to university students, new internal health department staff, and other areas of the health department (not contacted yet) about EPHT trainings and internship opportunities. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
| Initiate, Maintain, and Expand Partnerships | 1 | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Update partnership plan. Evaluate TAG members to assess partnership status and needs. Identify new/innovative external partners and conduct outreach to propose trainings and resources available. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q2
|  | 2 | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Hold at least 2 TAG meetings per year. Convene TAG EPHT meeting group to provide quarterly updates to TAG members and share how feedback and issues were addressed from past meetings. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | 3 | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Lecture at local universities and host at least one intern. Continue to maintain relationship with University of Arizona College of Public Health Program, Arizona State University, and Northern Arizona University. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | 4 | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | Send out press release through agency media channels (print news, tv, and radio) regarding Data Explorer updates, PHA's, or trends found in data. Respond to any media requests by providing subject matter expert interview. Outreach to media partners with use of EPHT Data Explorer training materials (web-based or in person). | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q2-Q3
|  | 5 | Communications 2 (C2) | C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner | Co-present at a national or regional meeting or webinar (e.g. CSTE, AMS, NEHA, APHA) regarding Tracking related project with PMO West or EPHT Content Workgroups | Comm- Targeted comm. products & messages | Comm- Engaged partners & users | Q1-Q3
|  | 6 | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Grantee will gather feedback from AZ stakeholders (e.g. users, TAG) on potential new NCDM or non-NCDM. Feedback can be provided via CWGs and locally new data sets and indicators will be explored based on feedback. Grantee will participate in CWGs and help complete CWG activities such as scoping reports, white papers, and piloting of indicators. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | 7 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | AZ Technology and Informatics will enlist Tracking team help for guidance on additional features to add to the Data Explorer based on stakeholder feedback of Data Explorer. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 8 | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | AZ PMO will work with Science & Content team to create trainings and content for public health & non-public health stakeholders regarding how to use AZ Data Explorer to support their work. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
| Identify and Integrate Public Health and Environmental Data | 1 | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | We will evaluate new indicators added to the Data Explorer using the NCDM standards documentation and identify limitations in metadata elements to describe data quality. We will participate in projects regarding CWG and evaluate CWG work such as the effect of transition from ICD-9 to ICD-10 on COPD ED visits and hospitalizations. Science and Content team will coordinate with other data stakeholders within the department such as birth defects, cancer, and ADEQ for input. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | 2 | Science and Content 1 (SC1) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | NCDM will be prepared in accordance with requirements of fall and spring data submission windows of CDC. In conjunction, NCDM will be uploaded into grantee Tracking Data Explorer supported by ESRI GIS software and SAS for data analysis. The program will maintain two epidemiologists for back-up purposes for completing data in a timely manner. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | 3 | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Required and optional NCDM will be collected, formatted, and submitted using the guide “Standards for Nationally Consistent Data and Measures within the CDC’s National Environmental Public Health Tracking Network Version 4.0.” Data will be prepared in accordance with requirements of fall and spring data submission windows of CDC and sent securely through XML using the CDC SDX secure gateway. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | 4 | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | The program will identify indicators needed by local stakeholders by engaging with local partners through TAG meetings and presentations with partners and universities. New indicators will be added to the Data Explorer and communicated to stakeholder groups through newsletters, TAG meetings, and presentations, such as pesticide exposures, adult blood lead exposures, and CDC Places. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | 5 | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Arizona Science and Content Workgroup staff will participate in grantee teleconference, webinars, and in-person grantee meetings to provide input on improvement and development of NCDMs. Staff will participate in CWGs and work on piloting indicators, scoping reports, etc. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | 6 | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | The Program will partner with the Arizona Department of Environmental Quality (ADEQ) through a sub-contract in order to gather their perspectives the display of air and water quality data from ADEQ (such as representativeness, data granularity, time scale, and accuracy). The program will also work with the TAG to identify limitations and solutions for data in environmental or public health data sets (e.g. sub-county). | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | 7 | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Technology and Informatics team will ensure that programmers and software are available that Science and Content team can use to create existing & new NCDM in XML for submission. Program will ensure at least .5 FTE staff dedicated for IT and ensure that SAS is purchased or forms completed to get from CDC on timely basis to do work. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 8 | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | AZ PMO will create website plain messaging language to accompany new NCDM datasets on state portal and meet with AZ Science and Content Team to ensure accuracy of website information. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
| Analyze and Apply Data to Translate Science Into Action | 1 | Science and Content 2 (SC2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | Epidemiologists with support from the PI will conduct routine descriptive analysis of NCDM using SAS and epidemiological analysis. Surveillance reports will be generated and posted on the AZ EPHT website, such as for heat-related illness and cold-related illness. Key talking points from descriptive analysis will be developed for planned workshops (1) EPHT in Tribal Lands, (2) State Heat Meeting, and (3) TAG virtual meeting. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | 2 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Epidemiologists will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-NCDM data in the Data Explorer. For example, report on trends in numbers, crude rates, age-adjusted rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | 3 | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | The Program will partner with (MCDPH) through a sub-contract to gain a program epidemiologist. Scope of work will include developing SAS programs and protocols for conducting routine analysis using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards at the county and sub-county scale. Timely reporting of the epidemiologist's findings will help the program's coordination efforts for further investigation with other state and local partners as well as new insights/solutions. The program's epidemiologist will analyze Tracking Data NCDM and report back quarterly of findings through email, teleconference, or in person meetings. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | 4 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Use Tracking Data to support and inform other internal programs and plans such as Climate and Health, CLPP, Birth Defects, and ADEQ. For example, summarize annual heat-related illness heat outcome data for the State Heat Meeting, drought measures for the Arizona Department of Water Resources annual preparedness plans, and help CLPPP evaluate their Childhood Blood Lead Risk Map and utilization. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | 5 | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Tracking data on heat-illness in children will be used to inform the development of recommendations for schools on how to mitigate the effects on students. Impacts of the recommendations will be tracked through evaluation efforts that include a state-wide survey on implementation of school heat policy guidelines in first year. The program will respond to inquiries from partners for new public health action data needed as requested. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | 6 | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Science & Content will work with PMO, Program Services, and Technology & Informatics to develop new tools for the Data Explorer that enhance data display and utility. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 7 | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | PMO team will use news releases and social media to communicate new EPHT data and findings. Science and Content team will ensure accurate messages. | Comm- Partnerships w/ env. health stakeholders | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | 8 | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Science & Content will work with PMO, Program Services, and Technology & Informatics to develop tools to track program activities and analyses that support external partners and health outcomes of the jurisdiction. PI or evaluator will submit PHA's and track PHA outcomes with partners as they are finished over long periods of time to gather necessary information. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
| Maintain and Enhance Information Technology Infrastructure | 1 | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements | Grantee will continue to maintain and update the Data Explorer with new NCDM indicators, tools and processes per CDC guidelines | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 2 | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Code will be developed to geocode to subcounty and tract levels using community layers. Imputation methods will be enhanced and maintained | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 3 | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | New tool will be created to allow for exploring the data through a simple text based interface, increasing 508 compliance and options for accessing data. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 4 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | The program will evaluate the use of ESRI portal, EM resource API, and ESRI hub for use in disseminating data to decision makers, stakeholders and the public. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 5 | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | The program will conduct feedback surveys and TAG meetings and demos, feedback will be evaluated, prioritized and put into action. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 6 | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | The PI and the Sr. Applications Developer have access to the CDC EPHT SharePoint Site for downloading newest version of the data validation program (DIVE) and indicator templates, CDC’s Secure Access Management System (SAMS) for secure file transfer and metadata creation tool (MCT) and capability to convert SAS datasets to XML. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 7 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | SAS and SQL and Python scripting will be maintained and developed as needed to ensure that the process of validating and updating data continues to run smoothly. Data and scripts will be integrated into a new EPHT admin site which will serve as the content management system for managing all measures and indicators. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 8 | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Quick reports tool will be updated with new community based indicators, including air quality, water quality, and drought. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 9 | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Hospital compare application for viewing locally relevant hospital outcomes select datasets will be integrated into EPHT | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 10 | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | Methodology will be developed to update Arizona's custom sub-county geographies in preparation for release of 2020 Census data and geography. This methodology will be used to complete a nationwide sub-county layer. The layer and methodology will be shared with the Geospatial Data Team as an option for tracking sub-county geography post 2020 Census. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 11 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | EPHT admin site will be enhanced to manage hospital compare datasets, scripts for automating hospital compare dataset updates will be created | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 12 | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Technology and Informatics team will ensure secure and public Data Explorer are available for Science and Content team to conduct routine descriptive epidemiology of NCDM/Non-NCDM to discover patterns of disease, exposure, and hazards in a timely manner. Epidemiologists will conduct routine analysis. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | 13 | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | TAG will be asked for feedback during presentations and webinars. Interim emails and surveys to TAG listserve will be conducted as needed to seek input on program decisions. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  | 14 | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Technology and Informatics team will ensure users have access to the Data Explorer and that internal program staff have access to IT resources for performing NCDM updates/queries. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | 15 | Technology and Informatics 1 (TI1) | TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis | The AZ TI team will explore implementing an Open Data Portal for GIS and other data sets. This will include evaluation of ESRI's Open Data Portal applications. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
| Increase Organizational Capacity to Support the Tracking Network | 1 | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Grantee will maintain appropriate staffing to respond to stakeholder inquiries by phone, email, and in-person, maintaining technology infrastructure of the AZ Data Explorer, data analysis support, and data updates. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | 2 | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Hold Technical Advisory Group Meetings at least twice a year. Additionally, tracking program staff will meet at least once a month to discuss technical capacity and needs. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | 3 | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Develop materials and trainings on how to use the Data Explorer. Continue partnerships with University of Arizona to support integration of EPHT into the public health course curriculum | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | 4 | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Deliver web-based or in-person EPHT trainings for public health staff (such as ADHS "How to trainings") and students | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | 5 | Science and Content 1 (SC1) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | EPHT Program staff will meet with and teach other internal and external partners about EPHT NCDM collection and formatting guidance with programs such as ADEQ, CLPPP, Climate and Health, biomonitoring, toxicology, EHC, birth defects, SafeWATCH in order to gather data on existing and new NCDM. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | 6 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | Technology and Informatics Teams and Science and Content team will develop scripts and SOPs (e.g. SAS Programs) to help partner programs which support AZ EPHT to help expedite data call uploads (e.g. WQL,CLP2,CLP4,BD, PWS). | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 7 | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Science and Content Team (epidemiologists and PI) will establish and maintain relationship with university for assisting on collaborative public health project using EPHT data and teaching university students about EPHT. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q2-Q3
| Monitor the Impact and Performance of Program Activities | 1 | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | AZ Science and Content and Program Services teams will develop an evaluation plan for Year 5 to engage tribal involvement within the TAG and EPHT Program. Results and feedback from Year 3's tribal engagement plan will be used to prepare an action plan to engage members of this stakeholder group. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  | 2 | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Epidemiologist and evaluator will develop an evaluation plan to evaluate the impact of 2 previously submitted PHAs (1) Heat Awareness Campaign and (2) EPHT in Tribal Lands Meeting. Based upon findings, team will work with PI to recommend improvements that will include a timeline for changes for these two activities. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  | 3 | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | AZ Science and Content, Technology and Informatics, Program Marketing and Outreach, and Program Services teams will meet routinely to discuss updates to the Data Explorer and website content | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  | 4 | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | AZ PMO Team led by health educator will ask technology and informatics team to use Google Analytics to capture web statistics to submit to CDC and help inform program evaluation. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  | 5 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | AZ Technology and Informatics, Science and Content, Program Marketing and Outreach, and Program Services teams will utilize cloud-based services to track performance measures and grant activities, specifically PHAs, indicators, presentations/trainings, technical assistance requests, evaluation plans/timelines, etc. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q1-Q4
|  | 6 | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | The Epidemiologist will develop SAS programs and protocols for tracking data to describe patterns in NCDM, optional NCDM, and non-NCDM data in the Data Explorer. For example, report on trends in numbers, crude rates, and percentages will be calculated to prioritize jurisdiction public health concerns/priorities regarding environmental health issues. Information will be shared by email, phone calls, or in person meetings to partners. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 7 | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | AZ PMO will post updates and announcements about grantee tracking activities to Tracking listserv and on social media about the impact of program activities on public health in AZ. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
| Supporting Public Health Emergency Response | 1 | Technology and Informatics 1 (TI1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Support the Health Emergency Operations Center with EPHT expertise; such as environmental epidemiology, GIS mapping (example: for vaccine response), and health education for public health emergencies such as COVID-19, wildfires, and heat. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  | 2 | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Sharing key messaging about emergent environmental health issues of public health concern through EPHT listserv and social media messages. For example, share information on heat related mortality before the beginning of heat season or address community members or stakeholder concerns regarding chemicals levels in their drinking water (PFAS, lead, etc.) or hazardous waste sites. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  | 3 | Science and Content 2 (SC2) | SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities | Utilize NCDM and non-NCDM data to assess the initial impact that COVID-19 had on public health and the environment by assessing air quality measures, transportation utilization, and its affect on non-COVID-19 health conditions. Participate in CDC content workgroups that are relevant to COVID-19 or other emergency response topics. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  | 4 | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | TI resources will be deployed to ensure effective response to the COVID-19 pandemic, opioid crisis, and revamped hospital compare application. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  | 5 | Technology and Informatics 1 (TI1) | TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data | COVID-19 data will be routinely processed, geocoded, and analyzed. Data will be disseminated to stakeholders and the public. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year