## Instructions
  Instructions
  Purpose of the Template
  Please use this workbook to document your Budget Year 5 Work Plan and Project Narrative as part of the EH17-1702 Annual Performance Report (APR) Continuation Application. This workbook corresponds to Section II of the Non-Competing Continuation (NCC) document "Instructions for Preparing an Annual Performance Report (APR)."
  This workbook includes tabs containing the finalized EH17-1702 Logic Model (blue tab), EH1702 Strategies & Activities (yellow tab) for reference, Project Narrative (purple tab) to provide greater detail regarding your planned projects, and the standardized Work Plan template (green tab). The only tabs which you should fill out are the Project Narrative tab and the Work Plan tab.
Filling out the Project Narrative tab:
  Required Reporting: Use the Project Narrative tab to provide details on how each project outlined in your work plan correspond to the specific strategies, activities, and tasks listed. In the Project Summary section, please provide an overview of the project; be sure to adhere to the 200 word limit for this section. There are no limits on the number of projects proposed. Please keep in mind that some of these projects may be an extension of the project proposed and approved in Budget Year 1 or 2 (i.e. initial EH17-1702 application). The planned projects must support the intent of the original EH17-1702 Notice of Funding Opportunity (NOFO).
  Optional Reporting: Use the right-hand side of each project area (Activity Description) to provide additional details which may not be captured in the work plan or in the project summary section. There is no word limit for this section. You may note comments pertaining to budgetary issues that might hamper the success or completion of the project as originally proposed and approved in Budget Year 1.
Filling out the Work Plan tab:
1. Project Title Create a short title for your project, no more than ten words. Examples include “Asthma Prevention”, “Improving Outdoor Air Quality,” "Improving Portal Infrastructure," "Expanding University Partnerships," etc. You may repeat the same project title in subsequent rows depending on the number of supporting strategies and activities for that project, or combine rows in that column to include the same title. You will provide a detailed description of each project on the Project Narrative tab.
2. Strategy Select a strategy from the drop-down list. Each project should fall into one primary strategy. While you can select supporting strategies and activities related to that primary strategy (ex. A Communications strategy/activity supporting the primary Science strategy/activity for that project), the first strategy you select will be the main focus of your project.
3. Activity Select an activity from the drop-down list. The activity should relate to the strategy you previously selected for that project. Each project should list at least two activities to be implemented in the budget year.
4. Activity Description In five sentences or less, describe the activity you are implementing in Column E.
5. Output Select a prospective output from the drop-down list. You may select one output per activity, or one overall output for the project. If you select multiple outputs for the project, you may find not all activities will correspond with an output.
6. Short-Term Outcome Select a prospective short-term outcome from the dropdown list. You may select one outcome per activity, or one outcome overall for the project.
7. Timeline Select when the specific activity will be accomplished from the drop-down list. Options include Quarter 1 (Q1) through Quarter 4 (Q4), meaning the activity will be accompished at the end of the budget year, or a specific time period (ex. Q1, Q2) .
Technical Support
If you need technical support when using this template, email your project officer.
            EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
      EH17-1702 Annual Performance Report (APR) - Section II only
      Budget Period: August 1, 2021 - July 31, 2022 (Budget Year 5)
      Reporting Period: August 1, 2021 - July 31, 2022

## EH1702 Logic Model
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network
EH17-1702 Logic Model
Long-Term
Communities improve certain health outcomes by reducing their exposure to environmental hazards
Short-Term
Science and Content
Health and environmental data are accessed and used by internal and external audiences
Development of targeted jurisdiction-specific program activities based on generated evidence
Technology and Informatics
Efficient, accessible, and higher quality display of data
Communications
Increased awareness of the Tracking Network and environmental health issues
Engaged partners and users
Program Services
Skilled workforce able to collect and interpret data and translate information for action
Improved program activities and increased program effectiveness based on evaluation findings
Science and Content
Standardized and accessible environmental and health surveillance data
Generated and disseminated environmental public health evidence
Technology and Informatics
Comprehensive surveillance system with tools, guides, and best practices
Communications
Targeted communications products and messages
Partnerships with environmental health stakeholders
Program Services
Environmental health workforce participate in workgroups and provide training
Systematic approach to assessing program activities and overall performance
Mid-Term Public health agencies and partners use data to inform decision making and drive measurable public health action (PHA)*
Contextual Factors:
* PHAs are defined using the “10 Essential Public Health Services”
Science and Content (SC)
SC1. Identify and integrate public health and environmental data
SC2. Analyze and apply data to translate science into action
Technology and
Informatics (TI)
TI1. Maintain and enhance information technology infrastructure
Communications (C)
C1. Conduct program marketing and outreach
C2. Initiate, maintain, and expand partnerships
Program Services (PS)
PS1. Increase organizational capacity to support the Tracking Network
PS2. Monitor the impact and performance of program activities
- Funding
- Partners
- Data and data
sharing agreements
- Inventory of standardized tools, resources, and messages
- Existing Tracking Network with secure data exchange gateway
- Workforce expertise
- Public portal for NCDM
OUTCOMES
STRATEGIES
OUTPUTS
INPUTS

## EH1702 Strategies&Activities
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Strategies and Activities
CDC-RFA-EH17-1702 Strategies and Activities
Activities in the EH17-1702 NOFO fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies.Ongoing activities in each strategy should be informed by work across the entire program and grantee’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. These activities should lead to the outputs listed in the logic model. Recipients need to demonstrate that 100% of the core activities are in place by the end of Year 1. Recipients must maintain all core activities each year. Recipients must also select and implement at least two new advanced activities per year. All advanced activities must be implemented and maintained by the end of Year 5.
SCIENCE AND CONTENT | Science and Content Strategy I (SC1)
Identify and Integrate Public Health and Environmental Data
| 5 Core Activities | 1 Advanced Activity
| SC1.A | SC1.F
| Identify and evaluate the strengths and limitations of health, exposure, environmental, and other data for the Network, in addition to work conducted as part of the Content Workgroup | Address gaps or limitations in available data by collaborating with state and local programs to optimize data collection and ensure the inclusion of data elements relevant to environmental public health tracking; integrating novel or non-traditional data determined to be relevant and of sufficient quality (e.g., electronic health record data); conducting analyses and activities that either fills the identified data gap or extends the applicability of the available data; or expanding the availability and utility of sub-county data and measures
SC1.B
Integrate data into grantee’s Tracking Network and ensure the availability and accessibility of data as appropriate for program staff and internal and external partners
SC1.C
Maintain existing and newly adopted Nationally Consistent Data and Measures (NCDM) requirements including maintenance of NCDM data within the grantee tracking network,submission of NCDM data to CDC, and dissemination of required NCDM measures via grantee’s Tracking Network https://www.cdc.gov/nceh/tracking/foa.htm
SC1.D
Disseminate additional indicators and measures to address grantee’s priorities, optional NCDMs or other agreed-upon standards
SC1.E
Collaborate with CDC, data stewards, data users, and other tracking grantees to improve existing NCDMs and, adopt new and optional NCDMs as developed by the Content Workgroup
Science and Content Strategy II (SC2)
Analyze and Apply Data to Translate Science Into Action
| 2 Core Activities | 2 Advanced Activities
| SC2.A | SC2.C
| Conduct routine descriptive analysis of Tracking data to evaluate quality and completeness of data; to examine state and local environmental public health issues; or to generate information for other state and local programs, state and local decision makers, and the general public | Conduct routine analyses using Tracking data for the discovery of spatial, temporal, and demographic patterns of diseases, exposures, or environmental hazards; the timely identification of unusual events signaling the need for further investigation; or the non-research purposes of analyzing or linking health, exposure, and hazard data to help provide new insights or solutions to environmental health issues
| SC2.B | SC2.D
| Use Tracking data to identify and prioritize the jurisdiction’s environmental public health concerns and priorities, and need for action to help direct Tracking program activities including but not limited to those listed in this FOA | Apply and interpret Tracking data to inform the development and evaluation of public health actions
| TOTALCORE ACTIVITIES FOR SCIENCE AND CONTENT: 7 | TOTAL ADVANCED ACTIVITIES FOR SCIENCE AND CONTENT: 3
TECHNOLOGY AND INFORMATICS | Technology and Informatics Strategy I (TI1)
Maintain and Enhance Information Technology Infrastructure
| 5 Core Activities | 2 Advanced Activities
| TI1.A | TI1.F
| Maintain a web-based publicly available environmental health tracking system that complies with CDC grantee portal requirements | Establish repeatable, reliable, and readily accessible electronic access to data sources, including tools and processes to increase the availability and accessibility of timely and locally relevant data (e.g., sub-county and real time data) and any needs discovered as the result of the gap analysis
| TI1.B | TI1.G
| Develop tools and processes to improve and promote the quality, usefulness, availability, and timeliness of data | Increase data management efficiency by developing state/local standard operating procedures and increasing the use of routine, reusable, and electronic processes and scripts for obtaining, validating, and disseminating data, including use of application programming interfaces
TI1.C
Evaluate informatics needs and conduct a gap analysis to address barriers to the effective use of data for environmental public health decision making (or by environmental public health decision makers)
TI1.D
Maintain the technology infrastructure and resources to submit Tracking NCDMs to CDC during scheduled data calls
TI1.E
Work with informatics and IT resources within the grantee’s organization to ensure program informatics/IT activities align with organizational strategies and objectives
| TOTALCORE ACTIVITIES FOR TECHNOLOGY AND INFORMATICS: 5 | TOTALTECHNOLOGY AND INFORMATICS ADVANCED ACTIVITIES: 4
COMMUNICATIONS | Communications Strategy I (C1)
Conduct Program Marketing and Outreach
| 7 Core Activities | 2 Advanced Activities
| C1.A | C1.H
| Develop and implement an annual communication plan that includes a risk communication plan; specific, measurable, achievable, realistic, time-bound (SMART) objectives; and targets key tracking audiences including data stewards, state and local health department staff, policymakers, technical advisory group, relevant community groups or non-governmental organizations | In the communications plan, include at least one collaborative communication activity, in addition to the program-wide activity, with one or more Tracking grantees (e.g., co-presenting at a meeting; coordinated communication about a specific topic or awarness event)
| C1.B | C1.I
| Participate in one coordinated, program-wide communication activity (e.g., Tracking Awareness Week) each year | Conduct a needs assessment with target audience(s) to inform development of at least two custom communication products (e.g., messages, tools) to communicate Tracking data and information. Products may include, but are not limited to fact sheets, environmental health snapshots, infographics, newsletter articles, and social media posts
C1.C
Provide regular, periodic updates and announcements at least quarterly about grantee tracking activities to partners and stakeholders via email distribution (e.g., list-serv, e-newsletter) or other mechanism
C1.D
Utilize social media (e.g., Facebook, Twitter, blogs) at least quarterly, either from program accounts, agency accounts, or partner accounts
C1.E
Present information about the Tracking Program (national and grantee), national and local Tracking Networks, data, data use (e.g., public health actions), and activities annually including: exhibiting at a meeting or conference; conducting at least one webinar to an external (outside the health department) audience; and presenting at national, regional, or local meetings or conferences
C1.F
Maintain existing and add new content/messaging about NCDM and other data as needed to Tracking Network websites in order to provide plain language interpretations of data and results to target audiences
C1.G
Disseminate existing Tracking communication messages and products (e.g., grantee profile, data highlights, community health reports, communication toolkits) to appropriate audiences
Communications Strategy II (C2)
Initiate, Maintain, and Expand Partnerships
| 3 Core Activities | 2 Advanced Activities
| C2.A | C2.D
| Develop and implement a partnership plan to engage new/innovative external partners (e.g., accountable care organizations, big data providers, new commercial technology and service providers in consumer-driven healthcare); and non-traditional public sector organizations (e.g., Tribal Nations, Department of Transportation) | Establish and maintain relationships with local media (i.e., newspapers, magazines, TV to promote Tracking through earned media)
| C2.B | C2.E
| Maintain Technical Advisory Group to inform decisions about Tracking Program data, data analysis, communication messages and products, etc. (minimum of one meeting per year) | Co-present/co-sponsor a national or regional meeting/conference or webinar with other grantees or partners
C2.C
Establish and maintain relationship with at least one university/college program. Possible collaborations could include, but are not limited to, guest lecturing; mentoring students; co-presenting (webinar/meeting/conference); collaborating on GIS, data analysis, or other projects
| TOTAL CORE ACTIVITIES FOR COMMUNICATIONS: 10 | TOTAL ADVANCED ACTIVITIES FOR COMMUNICATIONS: 4
PROGRAM SERVICES | Program Services Strategy I (PS1)
Increase Organizational Capacity to Support the Tracking Network
| 3 Core Activities | 1 Advanced Activity
| PS1.A | PS1.D
| Lead, support, and maintain existing Environmental Public Health Tracking Program within state and/or local jurisdictions | Develop and implement program-specific training opportunities, through Web-based or in-person training modules or other product (e.g., video tutorial) and internships/fellowships/mentorships for students in environmental public health tracking
PS1.B
Identify and prioritize technical and capacity needs among state and local Tracking Program staff to inform provision of more targeted resources and training opportunities
PS1.C
Support and facilitate training of the state and local public health workforce and partners on basic Tracking principles to establish a common understanding of the Tracking Program
Program Services Strategy II (PS2)
Monitor the Impact and Performance of Program Activities
| 4 Core Activities | No Advanced Activities
PS2.A
Document and submit public health actions quarterly (if available), but at a minimum of twice a year, to show program impact
PS2.B
Develop and implement an annual evaluation plan, based on CDC's provided template, that clearly identifies accomplishments and guides implementation efforts
PS2.C
Assist the CDC Tracking Program in conducting annual portal reviews
PS2.D
Collect and submit a report of website statistics on the public Tracking website using standard web statistics established by the Tracking Program twice a year
| TOTALCORE ACTIVITIES FOR PROGRAM SERVICES: 7 | TOTAL ADVANCED ACTIVITIES FOR PROGRAM SERVICES: 1
TOTAL CORE ACTIVITIES FOR ALL CATEGORIES: 29 |  | TOTAL ADVANCED ACTIVITIES FOR ALL CATEGORIES: 12

## Project Narrative
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Project Narrative
[Recipient] Project Narrative Budget Year 5
Type your project narrative below. Please limit your narrative to 200 words per project. Each project should fall into one primary strategy. Each project will have at least two supporting activities. Multiple activities encompassing one or more strategy is acceptable. You will note your strategy/strategies as well as your supporting activities on the "Work Plan" (green tab). Activities in CDC-RFA-EH17-1702 fall into four broad categories: Science and Content, Technology and Informatics, Communications, and Program Services and encompass several strategies. Ongoing activities in each strategy should be informed by work across the entire program and recipient’s priorities. For example, Communications activities should be tailored to reflect activities in Science and Content. You are not limited on the number of projects proposed. If you need to add more projects, simply paste a new project box to the end of your worksheet.
Project 1-Maintain and Update Existing and Newly Adopted NCDMs as Part of Tracking Network
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking California will continue to maintain NCDMs on its state portal for air pollution, asthma, cancer, carbon monoxide poisoning, childhood lead poisoning, drinking water, heat-related illness and mortality, housing, maternal and infant health, myocardial infarction, COPD, and poverty. By the end of PY3, we will update portal data for these NCDMs. We will continue to submit data to the CDC during the fall and spring data calls. | During PY5, Staff will add new years of spatially modeled rates for MI and Asthma. By the end of PY5, spatially modeled rates will be added as a new measure for COPD. | Total # of projects for Science and Content | Total # of projects for Technology and Informatics | Total # of projects for Communications | Total # of projects for Program Services | Total # of projects for Year 5
|  |  | 8 | 3 | 2 | 3 | 16
Project 2-Improve Existing Data and Develop New Nationally Consistent Data and Measures (NCDMs)
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking California will continue to collaborate with the CDC and other Tracking grantees via CWGs. We will engage with Tracking California data stewards and data users via our stakeholder advisory group (TIAG) or other partnerships in order to improve and adopt NCDMs. This will ensure that Tracking California understands the strengths and limitations of its data, can fill any data gaps, and can continue to adopt new data measures as needed. Data improvements will include additional sub-county data measures. | During PY5, Staff will continue to particupate in CWGs. By the end of PY5, new data on PFOS/PFAS will be incorporated into the state portal.
Project 3-Harmful Algal Bloom Health Impact Surveillance
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| California has recognized the negative impact of the growing number of harmful algal blooms (HABs) in the state's fresh water bodies. The HAB events negatively impact normal functioning of community health, recreation, economy, and ecology. Many state and local agencies have been working to monitor bloom activity in fresh water lakes and rivers, but there has not been a systematic effort to collect data regarding health impacts from exposures to HABs. Tracking California has implemented CDC's One Health Harmful Algal Bloom Surveillance System (OH HABS) in the state in calendar/bloom year 2018, and seeks to expand outreach and reporting in future years. | In 2021, we will continue to grow the reach and activities of our HABs work in California. We will conduct more outreach to regional staff at the state's Water Resources Control Boards to educate them on reporting human and animal health impacts due to HABs and to improve communication flow. We are also working closely with one area in California that is highly impacted by HABs, Lake County's Clear Lake. It is the largest lake entirely within California, home to several Native Tribes as well as a significant population of low income workers serving the tourism industry in the area. Drinking water quality is of particular concern in the area, and with supportive funding from CDC's EHC grant, we are collaborating with the Big Valley Rancheria to determine the impact of HABs on the drinking water supply for those who are not part of a public water system. This project involves identifying homes with no other source of household water, outreach, water testing, and community-wide health education. This collaboration came about due to the work CEHTP has been doing since 2018, and will lead to further expansion of activities and reach.
Project 4-Water Quality Viewer Enhancements
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Our water quality dataset currently includes data on eight contaminants. We propose to expand and include an additional four contaminants that are found in multiple California water systems: Hexavalent chromium, perchlorate, chromium, and 1,2,3-trichloropropane. We will also update the supporting content and include information on the health effects of each chemical. | We propose to incorporate data on at least four additional drinking water pollutants (hexavalent chromium, perchlorate, chromium, and 1,2,3-trichloropropane (TCP) into the Water Quality Dataset. This will involve assessing data availability, incorporating the most recent data on these chemicals when available, updating the data on the other chemicals that are already present, and including information about each chemical on the “What are water contaminants?” section of the site. We will explore the possibility of displaying 90th percentile lead data on our portal.
Project 5-Documentation and Updating of Pesticide Linkage Services
Science and Content 1 (SC1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| We will be reviewing, assessing, and amending the underlying code and calculations used in our Pesticide Linkage Service (PLS). The goal is to guarantee the sustainability of the tool in terms of data updates and staff transitions. This project will ensure that the institutional history of the tool is documented, the coding is up to date, calculations are clearly documented, and, thus, the tools remain sustainable. We will extensively document the code and calculations used in the PLS, and produce internal documentation for current and future staff. This will also enhance our ability to communicate with stakeholders about the tool, its strengths, and limitations. | In our last grant year, staff worked to update both the Pesticide Mapping Tool and Pesticide Linkage Service to increase the tools' transparency and sustainability. Documentation for the PMT was completed, and we had begun researching historical documentation for the PLS as the COVID-19 pandemic began. Work on this project slowed, and was ultimately halted as key project staff diverted to COVID-related research. As COVID research winds down over the summer, we intend to return to PLS research and documentation in the Fall of 2021. With additional perspective from our initial research on the PLS, we will first spend some time to reconsider our project goals, and the methods needed to reach those goals, in order to add more structure to what will be a complex data discovery project.
Project 6-Estimate the Risk of PTB Using Community-Collected Air Monitor Data
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| We will use community air monitor data from the Imperial County Community Air Monitoring Project to quantify the relationship between PM2.5 and preterm birth (a Tracking NCDM) in Imperial County. Results based on the community monitor data will be compared to ARB regulatory monitor data, as feasible. Costs of preterm birth will be included in the analysis. Results may be able to inform community air plans that are required as part of Assembly Bill 617. | This project is a carryover from the previous grant year. While we made substantial progress on the project--we've collected and geocoded the birth data, and have created air surface layers using the community monitor data--it was placed on hold in March of 2020 as project staff diverted to COVID-related research. In the meantime, we have received an IRB extension until December of 2021. Given ongoing COVID research and continued demands associated with working from home, it is unclear when program staff can restart this project as a research priority. In addition, the community in Imperial has been hard hit by the COVID-19 pandemic; we would want to ensure this project is still of interest to local community partners before reengaging with the data. In addition, a new year of preterm birth data and air monitor data may be available by the time staff are able to return to the project -- updating this data to a more recent year may make more sense than continuning with older data. Given the uncertainty on if or when this project should recommence, we acknowledge it may be pushed again this year.
Project 7-Healthcare Utilization of Individuals who are Homeless
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Currently, records for homeless individuals are excluded from California’s NCDM statistics because they are not assigned a residential zip code. Tracking California will explore hospitalization, emergency department, and ambulatory surgery data records for individuals who are homeless to describe patterns of asthma, heat-related illness, MI, and other conditions. This population is especially vulnerable because they lack the resources to mitigate environmental exposures, such as poor air quality from wildfires. Potential products may include a peer-reviewed article, a short report, and/or fact sheets.
SCIENCE AND CONTENT
Project 8-Long-term air pollution exposure and COVID-19
Science and Content 2 (SC2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking, in partnership with PHI and UCSF, successfully applied for and received research funding from the California Air Resources Board--with in-kind support from Tracking's CDC grant--to research the relationship between long-term PM2.5 exposure and the incidence and severity of COVID-19. We fast-tracked this research beginning in March 2020 as evidence began to emerge of the relationship between air pollution and COVID-19. We will examine associations between long-term exposure to PM2.5 and multiple COVID-19 outcomes--case positivity, hospitalizations, ICU admissions, and deaths. We will include multiple demographic, economic, and health covariates, and examine the impact on environmental justice communities. | Tracking partnered with UCSF and PHI to submit a research proposal to ARB in Spring 2020. Data analysis was intended to commence by June 2020, with project completion by November 2020. Because of delays in IRB approval, data were not received until February 2021. The timeline has now been extended to the end of 2021, with analysis expected to be completed by the Fall of 2021.
Project 9-Evaluate Stakeholder Data Needs
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| To increase the accessibility, comprehensibility, and utility of the program's data, Tracking California will continue to engage key program stakeholders, including the TIAG, in interviews and discussions to evaluate their needs, capacities, and interests with regard to using Tracking data. This will also include user testing of the redesigned portal. | This coming year we will continue to engage our TIAG, partners, and other stakeholders, as appropriate, in discussions to assess data gaps and needs that we could contribute to addressing with existing and potential new data resources and tools. We will also convene 2 in-person day-long meetings of our TIAG and hold at least 1 webinar to inform program planning and implementation. These stakeholders include state and local government agencies, community-based organizations, policymakers, data stewards, media, and users of our data resources and tools.
Project 10-Maintain and Improve Tracking California Portal
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking California will continue to maintain a portal that complies with CDC portal requirements, add new data content to the portal, and ensure that the data and information on the portal meets stakeholder needs. In addition, Tracking California will ensure that the data are disseminated appropriately to our various diverse data users. As part of this effort, Tracking California will continue to enhance the newly developed Content Management System (CMS) to further enable staff to control data flow, content, and design. This will help users to find information and data more easily, as well as explore new content offerings. | The focus of the grant cycle will move towards making updates to the content management system so that we can further enable all staff to create more ways to visualize data, track, and measure engagement, and accommodate the ever-changing needs of users of our portal to access the data we produce. We will also be making additional enhancements to existing data visualizations to make them load faster for users.
Project 11-Maintain and Enhance Technology Infrastructure and Administrative Demands
Technology and Informatics 1 (TI1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking California will maintain various data sharing agreements (DSA), as needed, to ensure data can flow from data stewards to the state portal in a timely and efficient manner. To ensure Tracking California's technical needs are maintained, staff will continue to systematically document hardware requirements, business cases, and justifications for non-standard software installations to increase understanding of program needs by ITSD. | Tracking California has maintained data sharing agreements (DSA) with the Center for Health Statistics and Information (CHSI) in order to access the most recent ED, hospitalizations, mortality, and vital records, and with the California Birth Defects Monitoring Program (CBDMP) to access birth defects data. DSAs are not necessary for childhood BLL data or air data.
PROGRAM SERVICES | Project 12-Program Outreach and Communications
Communications 1 (C1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking California will continue its program outreach and communications activities in PY5 to increase the awareness and use of Tracking data and resources. Tracking California will implement its annual communication plan, participate in coordinated program-wide and national communication activities, provide regular program announcements via newsletters, and release timely information via social media platforms. Additional outreach will occur via virtual meetings, presentations, and trainings (and at in-person events once safe to do so). We will continue to maintain and add plain language information on our portal. Tracking California will add a Data Directory to the Portal Help Center to assist users in understanding environment and health data publicaly available. Our communications work will continue to be informed by ongoing engagement with stakeholders to evaluate their interests, needs, and capacities. | Informed by past community needs assessment results, we will implement and evaluate a basic data directory on our portal aimed at making information about various environmental health data sources for California more accessible to lay audiences. As part of our ongoing needs assessment activities, we will also develop and implement new web user surveys for general and specific components of our portal, as informed by past web surveys and web user statistics.
Project 13-Establish and Maintain Partnerships and Collaborations
Communications 2 (C2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking California will engage staff, TIAG members, and partners, as appropriate, in developing and providing feedback on stakeholder engagement plan activities to build and strengthen relationships with key stakeholders, with an emphasis on activities that can be conducted online or remotely. These stakeholders include community-based organizations, local and state government agencies, academics, and users of our data resources and tools. | We will summarize and share results with TIAG of an internal survey of TIAG members to expand representation of key stakeholders, such as communities directly impacted by health inequities, on our TIAG.
Project 14-Program Services Enhancement
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking California will continue to develop and implement audience-specific trainings on Tracking to support the public health workforce and to grow Tracking's users. | Tracking California will increase training opportunities by updating the Portal Training Center to host and centralize new and existing training materials and links to web-based presentations.
Project 15-Maintaining and Strengthening Tracking Program
Program Services 1 (PS1)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking California will continue the process of transitioning to a more independent structure as PI Paul English begins employment with PHI. Sub teams within the program will continue to work on issues of data access independent of CDPH, strengthen our technological infrastructure outside the CDPH firewall, coordinate strategic planning, and work on issues of staff professional development, cross-training, and leadership succession. A significant emphasis this year will be on examination of issues of Diversity, Equity and inclusion both in our internal program structure and in our program work. Additionally, we continue to identify and address technical and capacity needs of Tracking California staff, facilitated through annual reviews of each staff member, annual retreats, and quarterly strategic planning meetings. | To address staff capacity needs identified through an internal program survey, Tracking California staff will engage in externally-facilitated Diversity, Equity, and Inclusion training and strategic action planning sessions to strengthen how our program selects and implements activities that address racial health inequities, partners and serves diverse communities and partners, and supports equitable professional/career development for a diverse public health workforce. Additionally, we will continue to work on strengthening management and leadership of the program and planning for succession, looking at professional development possibilities for other staff.
Project 16-Monitoring of Program Impact
Program Services 2 (PS2)
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
| Tracking California will continue work to assess program impact and to evaluate program activities. We will continue to identify and document public health actions that Tracking California has contributed to; these public health actions will be submitted to the CDC. We will also collect data for CDC's required performance measures, and will support portal reviews conducted by the national program. Assessments of web traffic will continue using web analytics as another measure of program impact. | We will develop, test, and implement the use of a inquiry feedback form/follow-up survey to better assess how data and information provided by Tracking California was used. We will also will explore methods to better track user demographics, inquiry topics, and the community/population that they serve. This may include the development of a standardized data request form or improved documentation methods.
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)
Project Title
<Select Primary Strategy Here (E.g. "SC1")>
TYPE PROJECT NARRATIVE BELOW
| Project Summary below (200 word max) | Optional: Activity Description below (no word limit)

## Work Plan
EH17-1702 Enhancing Innovation and Capabilities of the Environmental Public Health Tracking Network Work Plan Template
EH17-1702 Budget Period: |  |  |  | August 1, 2021 - July 31, 2022
Date Submitted to CDC:
Note: work plan is for final CDC grant year 08/01/2021 – 07/31/2022
REFERENCE NOTES | No more than 10 words per project title. Describe full project in Project Narrative tab. |  | Reference EH1702 Strategies & Activities tab for detailed descriptions. | Reference EH1702 Strategies & Activities tab for detailed descriptions. | One activity per row; no more than 5 sentences per activity description. | Reference EH1702 Logic Model tab. | Reference EH1702 Logic Model tab. | Anticipated timeline for completion of project.
| Project Title | Activity Title | Strategy | Activity | Activity Description | Output | Short-Term Outcome | Timeline
| Maintain and Update Existing and Newly Adopted NCDMs as part of Tracking Network | Maintain and Update Existing and Newly Adopted NCDMs as part of Tracking Network | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Update all NCDMs and submit to CDC during Data Calls. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  |  | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Upload NCDM updates and data to Tracking Portal. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  |  | Science and Content 1 (SC1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | Tracking California will add new years of modeled data for Asthma and MI and include new modeled rates for COPD. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
| Improve Existing Data and Develop New Nationally Consistent Data and Measures (NCDMs) | Improve Existing Data and Develop New Nationally Consistent Data and Measures (NCDMs) | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | Tracking California staff continue to participate in the CWG calls and discussions on new NCDMS. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  |  | Science and Content 1 (SC1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Tracking California will incorporate new data (July 2019-June 2020) for PFAS/PFOS testing results to the interactive map viewer on the portal. Results will be summarized by Public Water System and will include minimum, maximum, average, and most recent detections. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
| Harmful Algal Bloom Health Impact Surveillance | Harmful Algal Bloom Health Impact Surveillance | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Work with state and local agencies to receive case reports of human and animal illness impacts related to HABs. Investigate reports, and report those that may be due to exposure to CDC's OH HABS system. Use data to inform state and local stakeholders. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  |  | Science and Content 1 (SC1) | SC1.F Address gaps & limitations in data | Work with Big Valley Tribe in Lake County to assess drinking water threats from HABs in households not on public water systems. Use data to inform state and local stakeholders. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
| Water Quality Viewer Enhancements | Water Quality Viewer Enhancements | Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | We propose to incorporate data on at least four additional drinking water pollutants (hexavalent chromium, perchlorate, chromium, and 1,2,3-trichloropropane (TCP)) into the Water Quality Dataset. This will involve assessing data availability, incorporating the most recent data on these chemicals when available, updating the data on the other chemicals that are already present, and including information about each chemical on the “What are water contaminants?” section of the site. Additionally, we will explore ways to integrate our various water quality and water system maps and data; those data are currently displayed separately. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4
|  |  | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | We will assess user needs and provide recommendations to inform the display and communication of the water quality data. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q2
|  |  | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | We will develop and update water quality data messaging to include information about the new drinking water pollutants and to address any communication needs defined during the user assessment phase. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q3-Q4
| Documentation and Updating of Pesticide Linkage Services | Documentation and Updating of Pesticide Linkage Services | Science and Content 2 (SC2) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | We will be reviewing, assessing, and amending the underlying code and calculations used in our Pesticide Linkage Service (PLS). This project will ensure that the institutional history of the tool is documented, the coding is up to date, calculations are clearly documented, and, thus, the tools remain sustainable. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
|  |  | Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | Extensively document the code and calculations used in the PLS, and produce internal documentation for current and future staff. This will also enhance our ability to communicate with stakeholders about the tool, its strengths, and limitations. | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
| Estimate the Risk of PTB Using Community-Collected Air Monitor Data | Estimate the Risk of PTB Using Community-Collected Air Monitor Data | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | We will use community air monitor data from the Imperial County Community Air Monitoring Project to quantify the relationship between PM2.5 and preterm birth (a Tracking NCDM) in Imperial County. Results based on the community monitor data will be compared to ARB regulatory monitor data, as feasible. Costs of preterm birth will be included in the analysis. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q3-Q4
|  |  | Science and Content 2 (SC2) | SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions | Disseminate results to community and use results toinform coummunity air action plans that are required as part of AB 617. | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence | Q3-Q4
| Healthcare Utilization of Individuals who are Homeless | Healthcare Utilization of Individuals who are Homeless | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Tracking California will utilize the data on the healthcare utilization of the homeless population to look at patterns of asthma, heat-related Illness, MI as well as other conditions. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
| Long-term air pollution exposure and COVID-19 | Long-term air pollution exposure and COVID-19 | Science and Content 2 (SC2) | SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards | Tracking will use a cross-sectional design similar to research the association between long-term air pollution and COVID-19 positivity and severity. The analysis will include more spatially-refined effects estimates than previosuly published, and will examine COVID-19 deaths, confirmed/unconfirmed case counts, and counts of COVID-19 cases which have been hospitalized and in the ICU. The study will assess the relationship of PM2.5 with COVID-19 case/death rates in California, focusing on long-term exposures. | SC-Generated & disseminated env. Public health evidence | SC- Health & Env. Data are accessed & used by internal/external audiences | Q1-Q4
| Evaluate Stakeholder Data Needs | Evaluate Stakeholder Data Needs | Technology and Informatics 1 (TI1) | TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making | We will gather and apply feedback from our TIAG, partners, and stakeholders received at TIAG meetings and project evaluation meetings as well as the outcomes of all-staff Diversity, Equity and Inclusion trainings to inform portal content development and user testing to better align our work with health equity goals. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
| Maintain and Improve Tracking California Portal | Maintain and Improve Tracking California Portal | Technology and Informatics 1 (TI1) | TI1.A Maintain public portal that complies with CDC portal requirements | Continue to implement new portal design and continue to develop new content for the portal that helps users the connections between health and the environment. Create portal features that assist in the navigation and engagement of the portal. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  |  | Technology and Informatics 1 (TI1) | TI1.B Develop tools and processes to improve data qualities | Continue development of the content management system and related tools which separate the dependencies each group has on another when making updates to data on the portal, thus improving data quality and deployment time. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
| Maintain and Enhance Technology Infrastructure and Administrative Demands | Maintain and Enhance Technology Infrastructure and Administrative Demands | Technology and Informatics 1 (TI1) | TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls | Maintain data sharing agreements (DSA), as needed. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
|  |  | Technology and Informatics 1 (TI1) | TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives | Continue to systematically document hardware requirements, business cases, and justifications for non-standard software installations to increase understanding of program needs by CDPH's ITSD. Continue managing resources already provided by ITSD so we can limit the amount of dependency on ITSD which allows us to better control project estimates and scope. | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal | Q1-Q4
| Program Outreach and Communications | Program Outreach and Communications | Communications 1 (C1) | C1.A Develop & Implement annual comm plan | Implement our annual plan to guide activities related to materials development, outreach, risk communication, and dissemination. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  |  | Communications 1 (C1) | C1.B Participate in one coordinated, program-wide comm activity each year | Participate in tracking awareness week in coordination with the National Tracking Program and other grantees. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  |  | Communications 1 (C1) | C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution | Provide regular announcements at least quarterly via e-newsletters and ad-hoc emails. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  |  | Communications 1 (C1) | C1.D Utilize social media at least quarterly | Use Facebook and Twitter accounts to share news about the program or relevant program topics. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  |  | Communications 1 (C1) | C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences. | Conduct outreach by delivering virtual and, when safe, in-person presentations and trainings at conferences and meetings. These activities will focus both on general information about Tracking and the state and national programs, as well as on timely project activities such as the release of new data or findings. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  |  | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Complete review and updating of portal messaging using a style that is consistent across all content areas. Develop messaging to accompany new indicators. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  |  | Communications 1 (C1) | C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences | Design and develop a "Data Directory" on our Portal Help Center to describe environmental and health data available in California. The directory will list data sources and may describe aspects of the data such as years of data available, groupings of data available (e.g., race, age, sex), data visualization methods (e.g. column chart, time trends, map , tables). In the Data Directory there will be narrative description of each data source that may include information about the unique benefits, the limitations, and the questions that can be answered by each data source. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  |  | Communications 1 (C1) | C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences | Develop, deliver and disseminate in-person and online trainings, verbal presentations, written communication products to key stakeholders and other target audiences. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
|  |  | Communications 1 (C1) | C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info | Develop and implement new web user surveys for general and specific components of our portal, as informed by past web surveys and web user statistics. | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues | Q1-Q4
| Establish and Maintain Partnerships and Collaborations | Establish and Maintain Partnerships and Collaborations | Communications 2 (C2) | C2.A Develop & Implement partnership plan to engage new/innovative external partners | Engage TIAG members in providing feedback on partnership and stakeholder engagement plan activities (such as expanding representation of communities directly impacted by health inequities on our TIAG), and implement prioritized activities to build and strengthen relationships with external partners and other key stakeholders with an emphasis on virtual (online) engagement activities. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  |  | Communications 2 (C2) | C2.B Maintain TAG to inform Tracking Program decisions | Continue to convene TIAG through 2 meetings per year (in-person if safe, otherwise virtual) and at least 1 webinar to inform program planning and implementation. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  |  | Communications 2 (C2) | C2.C Establish, Maintain relationship & collaborate with at least 1 university | Continue to engage academic partners in program planning and implementation through TIAG meetings, webinars, and project-based collaborations. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
|  |  | Communications 2 (C2) | C2.D Establish & Maintain relationship with local media | Engage with local media to publicize and disseminate our work by developing press releases, media advisories, and other targeted communications products on our projects and publications, and by responding to media inquiries. | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users | Q1-Q4
| Maintaining and Strengthening Tracking Program | Maintaining and Strengthening Tracking Program | Program Services 1 (PS1) | PS1.A Lead, support & maintain existing Tracking Program in jurisdiction | Continue the process of transitioning to a more independent structure as PI Paul English begins employment with PHI after retirement from CDPH: explore options for and address barriers to data access independent of CDPH and strengthen our technological infrastructure outside the CDPH firewall. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  |  | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Identify and address technical and capacity needs of California tracking staff team, facilitated through annual reviews of each staff member, annual retreats, and quarterly strategic planning meetings. Continue strengthening of program structure to coordinate strategic planning and work on issues of staff professional development, cross-training, leadership succession and sustainability of program. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  |  | Program Services 1 (PS1) | PS1.B ID & prioritize technical & capacity needs among staff for training needs | Engage in externally-facilitated Diversity, Equity, and Inclusion training and strategic action planning sessions, and begin a process to bring these elements to the forefront in all areas of our work. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
| Program Services Enhancement | Program Services Enhancement | Program Services 1 (PS1) | PS1.C Support training of public health workforce on basic Tracking principles | Continue to develop, implement, and assess audience-specific training activities on Tracking principles and other related topics for state and local health department staff; public health students, interns, and fellows; and public health-focused NGOs, community-based organizations, and academia. | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
|  |  | Program Services 1 (PS1) | PS1.D Develop & implement program-specific training opportunities | Update the Portal Training Center to host and centralize new and existing training materials and links to web-based presentations. Adding a section on videos that have been produced by the program with short summary descriptions of the | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed | Q1-Q4
| Monitoring of Program Impact | Monitoring of Program Impact | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | Continue to identify and document PHAs that Tracking California has contributed to and submit to CDC. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  |  | Program Services 2 (PS2) | PS2.A Document & submit PHAs quarterly, minimum twice a year | We will improve inquiry tracking and identification of PHAs by developing a feedback form/follow-up survey on the portal and will establish methods to better track user demographics, topics and data they are interested in learning more about, and how best we can provide support to communities/populations they serve. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  |  | Program Services 2 (PS2) | PS2.B Develop & implement annual evaluation plan | Continue to integrate stakeholder engagement plan activities into evaluation plan and associated performance measures. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  |  | Program Services 2 (PS2) | PS2.C Assist CDC Tracking Program in conducting annual portal reviews | Support portal reviews conducted by the national program upon request, including portal content surveys and participation in review meetings by phone. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4
|  |  | Program Services 2 (PS2) | PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year | To assess use of our portal, we will continue to collect and review the analytics data associated with the website. We will submit standardized analytics data according to CDC guidelines. | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings | Q1-Q4

## DONT DELETE Ranges for Workplan (hidden)
Strategies | Activities | Outputs | Short Term Outcomes
Science and Content 1 (SC1) | SC1.A ID and Evaluate Strengths and limitations of Network Data in Addition to CWG work | SC- Standardized & accessible env. & health surveillance data | SC- Health & Env. Data are accessed & used by internal/external audiences
Science and Content 2 (SC2) | SC1.B Integrate Data into Grantee Tracking Network and ensure availability and accessibility | SC-Generated & disseminated env. Public health evidence | SC- Development of targeted jurisdiction specific program activities based on generated evidence
Technology and Informatics 1 (TI1) | SC1.C Maintain existing/newly adopted NCDMs and disseminate via grantee network | TI- Comprehensive surveillance system w. tools, guides & best practices | TI- Efficient, accessible & higher quality display of data on public portal
Communications 1 (C1) | SC1.D Disseminate additional indicators & measures to address grantee priorities | Comm- Targeted comm. products & messages | Comm- Increased awareness of the Trackign Network & env. health issues
Communications 2 (C2) | SC1.E Collaborate to improve existing NCDMs & adopt new NCDMs developed by CWG | Comm- Partnerships w/ env. health stakeholders | Comm- Engaged partners & users
Program Services 1 (PS1) | SC1.F Address gaps & limitations in data | PS- Env. health workforce participates in workgroups and provide training | PS- Skilled workforce able to collect, interpret data, translate info for action, provide tech assistance to other programs when needed
Program Services 2 (PS2) | SC2.A Conduct routine descriptive analyses of Tracking Data to evaluate data quality & completeness | PS- Systematic approach to assessing program activities & overall performance | PS- Improved program activities & increased program effectiveness based on eval findings
SC2.B Use Tracking Data to ID & prioritize jurisdiction public health concerns & priorities
SC2.C Conduct Routine Tracking Data analyses for discovery of patterns of disease, exposures, hazards
SC2.D Apply & Interpret Tracking Data to develop & evaluate Public Health Actions
TI1.A Maintain public portal that complies with CDC portal requirements
TI1.B Develop tools and processes to improve data qualities
TI1.C Evaluate informatics needs and conduct gap analysis to address barriers to effective use of data for public health decision making
TI1.D Maintain the technology infrastructure & resources to submit Tracking NCDMs during datacalls
TI1.E Work with TI resources within grantee org to ensure program TI activities align with org objectives
TI1.F Establish electronic access to data sources, including tools and processes to increase availability of locally relevant data, and any needs discovered as a result of the gap analysis
TI1.G Increase data mgmt efficiency by developing SOPs and increasing use of routine processes & scripts for obtaining, validating & disseminating data
C1.A Develop & Implement annual comm plan
C1.B Participate in one coordinated, program-wide comm activity each year
C1.C Provide regular updates & announcements at least quarterly about grantee tracking activities to partners via email distribution
C1.D Utilize social media at least quarterly
C1.E Present info about National & grantee Tracking Program exhibiting at meetings/conferences, conducting at least one webinar to external audiences, & presenting at meetings/ conferences.
C1.F Maintain existing & add new plain language messaging about NCDMs and other data to target audiences
C1.G Disseminate existing Tracking comm messages/ products to appropriate audiences
C1.H In comm plan, include at least one collaborative activitiy with 1 or more Tracking grantees in addition to program-wide activity
C1.I Conduct needs assessment with target audiences to inform development of at least 2 custom comm products to communicate Tracking data/ info
C2.A Develop & Implement partnership plan to engage new/innovative external partners
C2.B Maintain TAG to inform Tracking Program decisions
C2.C Establish, Maintain relationship & collaborate with at least 1 university
C2.D Establish & Maintain relationship with local media
C2.E Co-present/Co-sponsor nat'l or regional meeting/conference/webinar with other grantees or partner
PS1.A Lead, support & maintain existing Tracking Program in jurisdiction
PS1.B ID & prioritize technical & capacity needs among staff for training needs
PS1.C Support training of public health workforce on basic Tracking principles
PS1.D Develop & implement program-specific training opportunities
PS2.A Document & submit PHAs quarterly, minimum twice a year
PS2.B Develop & implement annual evaluation plan
PS2.C Assist CDC Tracking Program in conducting annual portal reviews
PS2.D Collect & submit standardized webstatistics on public Tracking website twice a year